Food Crisis Emergency Response Kenya-External Situation Report

Number: 8

Date: 26 August 2011

Prepared by: Amanda Lundy (alundy@oxfam.org.uk)

1. Key Issues

- Kambioss is experiencing ongoing difficulties as host communities dispute wages, disrupting construction. Relocation has been temporarily suspended.

- Water trucks are not able to reach Kambioss because there are no roads and the trucks are getting stuck. Oxfam is now building a tank at a point the trucks can reach, and we will construct a pumping system between this tank and Kambioss.

- WFP has reported that their inability to import GMOs has severely impacted their ability to meet pipeline needs. There is as yet no clear solution to this issue.

2. Security

- Nairobi is on high alert for a terror attack, as Al-Shabaab (AS) could attack a country in the region to demonstrate their strength despite having pulled out of Mogadishu. Oxfam staff have been instructed to avoid places frequented by expats.

- The UN received reports that AS was intending to attack the Dadaab camp and police station with explosives. Strict security measures are now in place at the camp.

- Relocation has been suspended to Kambioss due to ongoing host community disruptions to construction.

- In Mandera and Elwak, government security reported discovering plans to kidnap expats and hijack vehicles belonging to humanitarian agencies.

- Banditry continues on the Liboi-Dadaab road that refugees take from Somalia to Dadaab. These bandits are allegedly from the Kenyan Somali community.

- In Turkana, a heavy military presence exists in Turkana North between Lawregag and Kataboi.

3. General Humanitarian Situation

- FEWSNET forecasts that food insecurity will continue into the first quarter of 2012 due to projected below average rains for October-December 2011.

- WFP projects a 5,000 ton shortfall (25% of need) in cereals for August. Local and regional supplies are limited given competing needs in the Horn.

- 37.2% of the 790 confirmed measles cases in 2011 are from North Eastern province, while Nairobi accounts for 44.7%.

- The Long Rains Assessment highlighted the following:

  - Rainfall in Wajir was 0-20% of normal amounts

  - Pasture in Wajir will be depleted soon. Browse will last another month.

  - Maize prices in Wajir are 40-60% above average. Terms of trade have deteriorated by 50-60% compared to long term averages.

  - Rainfall in Turkana is less than 50% of normal amounts

  - Pasture and browse in Turkana are expected to last 2-3 months.

  - Maize prices in Turkana are 110-170% above the long term average. Terms of trade have reduced by 50-80% compared to long term averages.

4. General Political Relations/Context

- The government’s key line is that Ministry of Special programmes and Northern Kenya Development continue to be actively engaging stakeholders to ensure better response.

- GoK is considering holding a Horn of Africa Summit in 8/9th September. The proposed theme is ‘'Ending Drought Emergencies: A Call for Sustainable Solutions'.

- The report from the long rains food security assessment indicated that the number of those requiring relief is now officially 3.75m, up from the government’s reported 2.7m. The initial agreement on how to meet these needs is that GoK should channel all relief supplies for ASALs (arid and semi-arid lands) through the WFP pipeline, leaving the GoK to meet needs in other areas.

- The Treasury released 400m KSh ($4.3m) to the Ministry of Education, half of which will support school feeding in the new school year.

5. Humanitarian Community

- In Wajir, WESCOORD meeting took place on 22 August, attended by 4 District Water Offices, Oxfam, Mercy Corps, Save the Children, Kenya Red Cross, Islamic Relief, ALDEF, WASDA, DPA, ENNDA, Council of Imams/Wajir. Outcome – started mapping on Who, What, Where (avoiding overlap, overview on gaps).

- WASH cluster in Kenya is preparing for possible cholera and AWD outbreaks due to refugee movements from Somalia.

6. Sexual Exploitation and Abuse

- The UN reports increasing sex-for-food and transactional sex activities among women and girls in Turkana, with a particularly increase in involvement of police and military in these activities.

7. Programme Activities

Dadaab

Ifo II (est. population now 5,600)

- 5 tapstands (30 taps) built this week, bringing the total to 20. No stress yet on water points, so coverage is over SPHERE standard.

- 42 toilets were constructed this week, bringing the total to 264. Coverage is 22 people per latrine, meeting the SPHERE standard.

- Hygiene campaigns on handwashing and jerrycan cleaning continue.

Ifo III (est. population now 26,000)

- 4km of pipeline have been laid between Ifo II and Ifo III to deliver water to Ifo III.

- 200,000L of water are trucked daily from Ifo II to Ifo III. CARE is supporting with an additional 100,000L distributed.

- 28 toilets were completed this week, bringing the total to 268 toilets and 77 trench latrines. The coverage in Ifo III is about 30 people per latrine, meeting the SPHERE standard.

- 5 existing tapstands have been supplied with drainage this wk. All 15 tapstands (90 taps) now have drainage.

Kambioss (est. population 1,137)

- Water trucking is ongoing using 2 trucks. Water coverage is well over the SPHERE standard, with coverage at 35L pppd.

- 22 toilets completed this week, bringing total to 64. SPHERE standards are met at 25 people per latrine.

- WASH committee members (8/block) have been identified in Kambioss to promote sanitation and public health.

- Goal to construct 10 latrines per day (25/day subject to host community interruptions) in the coming week. The nature of the soil (collapsible) slows latrine construction.

Turkana

EFSL

- Emergency Cash Transfer Programme

  - 132 traders were trained on the modalities of the cash transfer and market support programme, 52% of whom were women.

  - The OFDA project baseline data was collected, including beneficiary household baseline data and key information on the traders and the rural market dynamics

  - Preparatory work for the initial cash transfer to the target families was finalised. This included sign off of the contract between the participating traders and Oxfam

  - A total of 13,228,800Kshs (Approx. £86, 519) was transferred to the bank accounts of the participating traders to facilitate the disbursement of cash entitlements for the 1st cycle of payment.

- Cash for work:  A total of 970 households receive 7000Kshs each. In sum, this transfer was 6,790,000Kshs (approx. £44,408).

- Livestock deworming:  A total of 186,912 goats and sheep were dewormed in Turkana north. The deworming exercise supported 3,738 households, each family having an average of 50 goats and sheep dewormed. This will continue next week.

WASH

- Water quality testing for 7 water points (shallow wells) was conducted.

- 2 pumps were serviced in 2 locations. The pumps serve a total population of 6274 (55% women)

- A survey on the linkage of nutrition and hygiene promotion was conducted.

- Next week will request an Environmental Impact Assessment (EIA) and Hydro geological survey for the works related to the emergency response.

Wajir

EFSL

- More than 2/3 of vouchers have been stamped. Serial numbers and quality has been checked and no major flaws detected.

- The schedule for the 1st batch of the voucher distribution including 11 sites in Wajir South was completed, including 910 households. Voucher distribution started Thursday 25th August.

- After receiving green-light for including HSNP sites in the emergency food security response, two teams were sent to conduct a rapid registration of the remaining 6,000 households.

WASH

Water trucking

- 25 of the initial 27 sites targeted received water this week. The amount of water provided per person was raised from 3.3 litres from the previous week to an average of 6.3 litres per person per day. In total the partners WASDA and ALDEF delivered a total of 3,301,000 litres (6.37l/p/d) up from 1,641,600 litres delivered last week, an increase of about 100%.

Borehole operation and maintenance

- Two rapid response teams repaired 5 boreholes this week. The team are ensuring that there are at two functional generator sets per site to cope with 24-hr borehole use.

- Currently DPA are using the stock of spare parts in their stores. These will be replenished after completion of the ongoing inventory of the equipment in the entire county.

Fuel subsidies

- Deliveries for the fuel subsidies have been completed by WASDA and ALDEF has completed deliveries in Wajir North. Partners have now delivered a total of 37,200 litres of diesel to serve communities for 1 month. The estimated total population assisted is 159,321.

PHP

- Oxfam GB PHP visited 8 field sites with partners, demonstrating cleaning of jerrycans, environmental cleaning, and training on water chlorination.

- The team held focus group discussions with community members on the existing community structures, existence of public facilities like schools, dispensaries, sanitation facilities, and public health risks.

- The team identified Community Health Workers and Water User Committees.

- 8. Beneficiary numbers

- *As 2009 census figures from Wajir have been invalidated, from next week disaggregation figures will be altered to reflect the 1999 census, which is regarded as the best available data for Wajir County as a whole.

- **This figure is 205,150 less than last week, reflecting an error in earlier reporting.