Minutes of Education Working Group – Akkar

UNICEF- Qobayat Office- 24th of April   2014:

13:00 – 14:30

## Participants:

UNHCR, UNICEF, Caritas, SCI, NRC, CONCERN, R& R, UOB , ANERE, R& R, REACH, SDC, WCH, IRC, OTI

Summary of action points

|  | What |  |  | Who | When |
| --- | --- | --- | --- | --- | --- |
| 1. | First shift public schools payment and reimbursements : -Caritas : Complete Payment for Syrians and Vulnerable Lebanese in three schools - SCI: complete payment for 92 Syrian students and 18 Syrian Secondary School students -SCI to share bi weekly monitoring report for first shift public schools |  |  | Caritas and SCI | ASAP |
| 2. | Monitoring first shift : -SCI to share student attendance monitoring tool for first shift with UNHCR and members of EWG |  |  | SCI | By next meeting |
| 3. | Fuel Distribution for first shift public schools : -UNICEF will distribute fuel to all schools on MEHE’s list not covered by UNHCR |  |  | UNICEF | ASAP |
| 4. | Participation of Syrian Parents in PTA at first shift public schools -All Education partners to share any success stories on the participation of Syrian parents in PTA in public schools in Akkar. |  |  | All | By next meeting |
| 5 |  | Second Shift Public Schools: -SCI to finalize payments of tuition fees for children attending in all 13 second shift public schools -SCI to review and report a first draft of reasons for dropouts from second shift public schools -SCI to share biweekly monitoring reports of second shift public schools with UNHCR | SCI |  | By Next meeting |
| 6 |  | ProGress Numbers : -Collection and sharing of correct ProGress numbers by all Education partners necessary to track education services provided to children. | All |  | Whenever identified |
| 7 |  | Activity Info Presentation ( Education Activities Focus) : -All Education partners reporting to Activity Info are asked to verify data entry reported. Further support, assistance, and training can be provided to partners upon request. | All |  | Whenever identified |

- NEXT Education Working Group Meeting: Thursday May 29, 2014 at 12:00 PM UNHCR Office Qobayat.