LCRP Livelihoods Working Group – 2016 Work Plan

| - Sector Coordination |  |  |  |
| --- | --- | --- | --- |
| Topic/task | Deliverable | Deadline | Responsible |
| Manage the working group within a structure that includes sector steering committees | National working Group meeting organized every two months Steering committee set up, participants identified and meeting held regularly | Every other month TBC | MOSA Sector lead, MOET and GoL, sector coordinator, Core Group and WG |
| Work closely with NGO focal points for the sectors and ensure that core groups are an active part of decision making | Monthly meeting of core group | Set up in Feb then meeting every month | MOSA Sector lead, sector coordinator, core group members |
| Actively engage in field coordination and support field coordinators. | Monthly meeting of field working groups in 4 locations, and monthly meeting between all field and national coordinators. | Every month | Sector & field coordinators &partners |
| Referrals between sectors to partners and follow up on actions taken | See below on referrals related to skill training programmes, child labour. | Ongoing, with list shared starting March | Sector core group. |
| Ensure standardization, harmonization and coordination through SOPs, guidelines and tracking tools for interventions within the sector | See below on harmonization of assessments. Tracking ensured through monthly 3W mapping, including gap analysis shared at national and field levels. | See below Monthly | Core group Sector IM, based on partners’ reporting. |
| Keep inter-sector coordinators regularly informed of sector developments | Informal information sharing | Continuously ongoing | Sector coordinator, IS coordinators. |
| Working group and core group management | Agenda agreed among co-leads and shared one week before meeting, minutes cleared by co-leads and shared after meetings. Weekly ‘news of the sectors’ to disseminate key documents, information, update | Monthly | Sector lead and sector coordinator |
| Engage actively in cross sectoral work with other sector colleagues | Cross-sector issues to be based on LCRP sector chapter section, one issue to be identified and acted upon at each inter-sector meeting. | continuously | Sector lead and sector coordinator, IM, other coordinators. |
| - Analysis, Monitoring and Reporting |  |  |  |
| Topic/task | Deliverable | Deadline | Responsible |
| Regular gap and trend analysis and sharing of 3W information based on partners reporting | See above on referrals and 3W & gap analysis shared and discussed monthly in WG meetings | Monthly | Sector coordinator (field & national) and IM, partners reporting |
| Identify problems, lead working group in discussing solutions and follow-up on implementation of solutions | See above on working group meeting. Key issues identified below, to be followed up and updated throughout the year. | Throughout the year. | Sector lead and coordinator, core group and working group. |
| Completion of standard M&E/IM products: inter-agency monthly updates, monthly statistics, quarterly dashboards, mid-year and end of year reports | Training of sector members on AI database Reporting by partners Clearing of data at field and national level Compilation of data, reports, and mapping. | Completed Monthly Monthly Monthly/ Quarterly | Sector IM and coordinator, Partners, Field sector coordinators |
| Keep web portal up-to-date with meeting/workshop dates, key documents and minutes of meetings | Share weekly key documents and update through ‘news of the sector’ email, then upload them on webportal. | Weekly | Sector coordinator and IM. |
| Ensure relevant assessments are shared through IA meetings as well as uploaded to the Assessment Registry | Assessments shared and uploaded through news of the sector. Keep registry database updated. | Weekly Monthly | Sector coordinator and IM Partners |
| - Key thematic priorities of the sector for 2016 |  |  |  |
| Topic/task | Deliverable | Deadline | Responsible |
| Output 1- Support to MSMEs and cooperatives |  |  |  |
| Strengthen sector link with the SME strategy | - Present SME strategy by MoET and idenfity linkages between sector support to SMEs and strategy. - Organize follow up meeting between MoET and output 1.1 partners to ensure alignment of activities - Presentation of UNIDO’S projects on strengthening SMEs competitiveness by focusing on clustering cultural and creative industries in Lebanon. | February June July | MoET, MOSA Sector lead, sector coordinator output 1.1 partners UNIDO, MoI. |
| Output 2 – Value Chains development |  |  |  |
| Value chains (cooperatives, MSMEs, Producers association) – consolidation of assessment, identification of priority interventions, comparison of approaches. | - Presentation of ILO’s North Lebanon project on value chain development (ILO VC analysis report will be shared within next days) and other partners engaged in VC (MC, SCI) or micro-level support (ACF); development of agro-industry value-chains. - Presentation of lessons learnt from other VC programmes: EU work on wood, fruit and vegetable, WB work on potatoe, waste management. - Presentation of UNIDO’s support to the MoI towards the development of industrial zones especially in most vulnerable and marginalized areas of the country and formulating a comprehensive industrial strategy. | April WG (ILO VC analysis shared) | ILO, MC, SCI, ACF, UNIDO, MoET, sector coordinator. |
| Output 3 & 4 Public work and Employability |  |  |  |
| Strengthen the sector linkages with Municipality Support Programmes | - In view of the GoL enforced support to municipalities, ensure that livelihoods programmes are aligned with local priorities to increase local capacity and increase opportunities: used MOSA-UNDP Maps of Risks and Resources as a basis for identifying potential municipal livelihoods projects. - Presentation of lessons learnt from past programming: ACF and others. | Pending finalization of MRR by MoSA | Sector coordinator, MOSA-UNDP LHSP staff, ACF and other partners working with municipalities, MoIM. |
| Access to income/employment for women, youth, and person with disabilities | - Mapping of past an ongoing activities and sharing of lessons learned to better figure out how to target women to make progress in child labour. - Presentation of ILO/IRC/Souk el Tayeb collaboration for women employment as part of ILO VCD project - Presentation of UNIDO’s assistance for promoting women and youth economic empowerment for Inclusive and Sustainable Industrial Development . - Identification of specific training and employment programmes for women/youth/PWD –(ex: UNDP Youth employment projects). Based on findings: - Partners to focus on specific sector offering opportunities to women and youth (business and entrepreneurial skills to employers; and training, referrals, apprenticeships, start up funds for youth/women) | June? | Sector coordinator, consultant? ILO, IRC, UNHCR, UNDP, UNIDO and other partners DRC (review of skills programme for UNICEF), MoI |
| Targeting: strengthen link with Lebanese social systems (NPTP, SDCs) | - Establish procedure for partners to access NPTP list of beneficiaries (and their skills) and/or support from SDCs to identify beneficiaries. - Presentation of livelihoods related services available in SDCs | April Centrally first, then in field | MOSA (sector lead and SDC, NPTP Programmes) |
| Skills training: consolidation of programs modalities, referrals pathways with other sectors | - Collect and consolidate information on existing skills training programs offered by partners. - Establish referral mechanisms with other sectors particularly protection, education and other relevant sectors - Ensure that acquired are updated into a common profiling platform e.g. ProGres | April April – May (IS meeting) | Sector coordinator and field coordinators, output 1.4 partners, inter-sector coordinators UNHCR |
| Strengthen link between national employment offices and skills training providers | - Obtain list of certified courses from National Employment Office. - Raise awareness regarding the National employment office with the trainees themselves. | TBC | DRC ( currently checking possibility) |
| Output 5 – Decent work promoted |  |  |  |
| Child Labour – prevention of the worst forms of child labour, with CP, FSS partners. | - Drafting of a National Workplan for 2016 on all CL in Lebanon led by MOL CLU and UN partners - Implementation of workplan including training of govt partners, NGOs, revision of existing agreements between farmers unions, MoL&MoIM, training security forces on working street children, training guide on child labor in agriculture, etc… - Join meeting between sectors to train and educate partners on Lebanese laws on worst form of child labour (with CP, FSS partners and MOL). - Train partners on how to mainstream prevention and response to child labour into their programmes(including referral mechanism) - Map relevant actors | End Feb following release of upcoming CL assessments check during CP retreat | MOL, ILO, UNICEF and partners including CP MoL, ILO, IRC, and relevant actors (Beyond, FAO, UNICEF, MoIM, MoA…) MOSA, MoL, ILO, UNHCR, Sector coordinator with CP, FSS sector coordinators. |
| Support the MoL in areas of labor administration and development of a decent work country programme | - Assist the MoL to formulate and implement a labour market strategy that responds to the current and future needs of the economy - Strengthen MoL capacity to increase outreach of labour inspection and assess and monitor workplace compliance - Support the development of a national occupational and safety hazard profile and updating the list of occupational diseases - Develop criteria for decent work conditions and share with parnters - Based on this, partners to improve awareness within selected enterprises and workers on decent working conditions; | Till end of the year, contingent on dialogue with MoL | ILO, MOL, Employers’ and workers’ organizations Partners |
| Output 6 – Policy and Strategy Development |  |  |  |
| Support to GoL on operationalization of the ‘economic opportunities and jobs’ dimension of the London conference, including on access to work framework. | - Set up sector steering committee. - Support SSC by: - Research on access to work framework, including opportunities and economic benefits - Provide legal advice on accessing work opportunities and develop user-friendly material on laws, processes, etc. - Identification of operational constraints or limitations, definition of the resources needed and milestones to operationalize the programmes. | April Pending post-London developments and SSC set up | GoL Sector leads and co-leads, core group and partners UNHCR |
| Knowledge/assessment gap on poverty, unemployment, labour market & labour forces assessments, needs of SMEs. | -Consolidate previous studies and conduct new ones where information is inadequate; enhance education and skills profiling and monitor and analyse labour market skills gaps. - Consolidate existing market analysis Presentation of key reports filling assessment gaps (UNDP Rapid Poverty Assessment, UNDP labour needs in construction and manufacturing, etc…). Labour Force Survey: Share guidance notes on existing Labour Market Information Based on the findings, partners: - Adjust implementation according to gaps identified, from type of assistance provided to which economic sector to work on. -Reach out to training providers from the relevant economic sectors where the gap is identified. | Done (LCRP sector chapter, Information portal) May Through WG, assessment registry Jan-Dec 2016 WG Discussion following new report presentation | Core group, UNHCR, partners Coordinator, Partners UNDP senior economist, partners ILO&CAS ILO Partners |
| Explore ways to engage the private sector and national vocational/technical institutes | - Chamber of commerce, union of cooperative, incubators and micro-finance institutes’ participation & presentation at field and national meetings. - Strengthen the linkage with Unions, Cooperatives and Associations providing employment opportunities, and build on common interests. - Strengthen linkages with industrial sectors (UNIDO experience). - Strengthen linkages with vocational/technical institutes and explore possibilities to waive or reduce tuition fees at vocation and technical institutes, | Ongoing basis till end of the year | MoSA sector lead, MoET, supported by sector coordinator and field coordinators, IRC, UNIDO and UNHCR |