Nea Kavala Camp / 06.03.2016 / WASH Assessment

The camp was set up by the Army Engineering Battalion and is managed by:

Engineering Battalion Commander Major Ilias Ladopoulos (693 747 98 14)

The following notes were taken during the discussion with the Commander, who showed us round the camp and explained the work in progress and planned. The Major is an experienced camp Engineer and welcomes collaboration with UNHCR and the NGOs.

- EXISTING INFRASTRUCTURE

- WATER SUPPLY

Existing installations:

- SOURCE: Main line water supply from the Municipality of Polykastro

- QUANTITY: There is sufficient water for the planned population of 4000. There may not be sufficient for the summer period.

- QUALITY: Samples have been taken from the Military Sanitation Agency. Results are expected in the next few days.

- DISTRIBUTION: Water is distributed in two lines in trenches running from the main line :-

Line 1) PE pipe, Diameter 25mm (1”), 2 pipes

Line 2) PE pipe, Diameter 32mm, 1 pipe

- TAP STANDS: 22 tap stands completed (three rows of taps). A concrete run-off drain has been completed on one of the rows.

Work in progress:

- DISTRIBUTION: A third distribution line is under construction :-

Line 3) PE pipe, Diameter 32mm, 1 pipe

- TAP STANDS: 5 more tap stands are under construction.

- CHEMICAL TOILETS

- NUMBER: 30

- CLEANING: Cleaned twice a day by a contractor (Antonis Karipidis)

- STAND-ALONE SHOWER UNITS: 15 cubicles, connected to a solar panel unit.

- WASTE WATER

Existing installations (showers):

- WASTE-WATER PIT 1): The waste water from the showers drains into a concrete cylinder (diameter 2.5m, depth 3.00m). The cylinder is placed on and surrounded with a layer of crushed stone (dimeter 50mm), which acts as a drain.

- WASTE WATER PIT 2): A second drain has been built for future toilets/showers.

- GARBAGE: Collected once per day by the Prefecture of Peonia.

- PROPOSED INFRASTRUCTURE (for a population of 4,000)

- PREFABRICATED TOILET CONTAINERS

- NUMBER: 40 containers of 5 toilets each (delivered in 4 phases)

- PREFABRICATED SHOWER CONTAINERS

- NUMBER: 10 containers of 4 showers each (delivered in 4 phases)

- HAND & CLOTHES WASHING FACILITIES

- Sinks with taps to be constructed on the back side of 5 of the shower containers

- SIGNPOSTING (laminated signs)

- Garbage collection

- Cleaning

- Drinking water from tap stands

- Male / Female toilets and showers

- PROPOSED CONSTRUCTION/INSTALLATION SCHEDULE

- TO DO

- SITE PREPARATION: Army

- WASTE WATER PITS: Army

- ELECTRICITY: Army (EXISTING LINE: 200 Amps/400 Volts distributed in 3 phase 4x 2mm cables) – FUTURE LINE: 4 X 4mm cables)

- CHEMICAL TOILETS: 40 units to be immediately installed, but removed as soon as the prefab containers are operational (to coordinate with NGO)

- STAND-ALONE SHOWER UNITS: 20 units to be immediately installed, but removed as soon as the prefab containers are operational (to coordinate with NGO)

- TOILET & SHOWER CONTAINERS: NGOs/UNHCR (to coordinate with NGO)

- PREFABRICATED TOILET & SHOWER CONTAINERS (to discuss/coordinate with supply + NGO)

| Phase 1 |  | Phase 2 |  | Phase 3 |  | Phase 4… |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 10 Toilet containers |  |  |  |  |  |  |  |
|  | 5 Shower containers with washing facilities |  |  |  |  |  |  |
|  |  | 10 Toilet containers |  |  |  |  |  |
|  |  |  | 5 Shower containers |  |  |  |  |
|  |  |  |  | 10 Toilet containers |  |  |  |
|  |  |  |  |  | 5 Shower containers |  |  |