## CCCM
Sector Standard Operating Procedures (SOPs) for Disaster Response ─ Updated May 2016 CCCM
Activity | Lead | Other Organizations | Timeline
Early Warning Phase
Mobilise camp management needs assessment team | CCCM Cluster | Cluster partners | 5 days (maximum)
If population relocated, assess camp management needs | CCCM Cluster | Cluster partners | 5 days (maximum)
Mobilise camp management needs assessment support at national level (as required) | CCCM Cluster | Cluster partners | 5 days (maximum)
Immediately after disaster
Mobilise camp management assessment team | CCCM Cluster | Cluster partners | 24 to 36hrs
Conduct rapid assessments of camp management needs of affected population, which can include security threats/risks, access to affected areas and logistical needs | CCCM Cluster | Cluster partners | 72hrs
Share information on results of rapid assessments with relevant stakeholders and decide on further actions | CCCM Cluster | Cluster partners | 7 days
Organise daily coordination meeting in Yangon, which can include liaising with appropriate government counterpart at national level | CCCM Cluster | Cluster partners | 24 to 36hrs
Attend ICCG meeting in Yangon | CCCM Cluster | OCHA | 24 to 48hrs
Within two weeks
Deploy additional staff from emergency rosters | CCCM Cluster | IOM | within 21 days
If appropriate, adjust plan/strategy | CCCM Cluster | Cluster partners | within 28 days
Up to four weeks
Deploy additional staff from emergency rosters | CCCM Cluster | IOM | within 28 days
If appropriate, adjust plan/strategy | CCCM Cluster | IOM | within 28 days

## Education
Sector Standard Operating Procedures (SOPs) for Disaster Response ─ Updated May 2016 EDUCATION
Activity | Lead | Other Organizations | Timeline
Early Warning Phase
Update and share 3W and contact list with relevant partners | UNICEF, SCI | All relevant actors | Immediately
Initiate agreed emergency coordination mechanisms with the sector partners, including the Education Dept/Office, and other sector/cluster coordinators | UNICEF, SCI | Education Dept/Office, LWF, Plan, MRCS, CFSI, other partners | Immediately
Review/verify with all partners that local EiE preparedness capacity is valid/updated – education stocks, education personnel , pre-identified NGO/CSO education partners | UNICEF, SCI | Education Dept/Office, LWF, Plan, MRCS, CFSI, other partners | Immediately
Immediately after disaster
Co-convene first EiE Sector emergency meeting with available partners, including the Education Dept/Office, and agree initiation of contingency plan (revising aspects if necessary). Agree regular meeting times, places and coordination responsibilities. | UNICEF, SCI | Education Dept/Office, LWF, Plan, MRCS, CFSI, other partners | 24hrs (Continuous)
Compile and share existing information on education services managed or supported by each organization - staff, structures, materials (Continue this throughout crisis, expanding it in line with information available and transitioning into the regular sector sitrep later on). | UNICEF, SCI | Education Dept/Office, LWF, Plan, MRCS, CFSI, other partners | 24 to 48hrs (Continuous)
Obtain initial information on potential damage to education personnel, structures and supplies through the Education Dept/Office and implementing partners, using their existing education staff network (including liaisons, PTAs and community teachers). | UNICEF, SCI | Education Dept/Office, LWF, Plan, MRCS, CFSI, other partners | 24 to 48hrs
Attend ICC meetings to share information on the EiE sector’s initial needs and plans and priorities. Update OCHA 3Ws based on new reality and on an ongoing basis thereafter based on evolving EiE response plans. | UNICEF, SCI | Education Dept/Office, LWF, Plan, MRCS, CFSI, other partners | 24 to 48 hrs (Continuous)
Coordinate initial request for education supplies by partners from their respective in-country preparedness stocks, working with national EiE Sector Coordinator | UNICEF, SCI | Education Dept/Office, LWF, Plan, MRCS, CFSI, other partners | 48 to 72 hrs
Coordinate and support any request for rapid seed funding from pooled funding mechanisms through the best placed organization (or the one lacking funding from its own internal emergency sources). | UNICEF, SCI | OCHA | 48 to 72 hrs (Continuous)
Mobilize EiE sector members able to participate in the Multi-sector Initial Rapid Assessment (MIRA) and (re-)train on education section of tool | UNICEF, SCI | Education Dept/Office, LWF, Plan, MRCS, CFSI, other partners | 48 to 72 hrs
Within two weeks
Share information on progresses/results of initial rapid assessments with relevant stakeholders and decide on priprity actions. | UNICEF, SCI | Education Dept/Office, LWF, Plan, MRCS, CFSI, other partners | 1 week
Update and finalize initial sector response plans and (re-)confirm partners' priorities and capacities | UNICEF, SCI | Education Dept/Office, LWF, Plan, MRCS, CFSI, other partners | 1 to 2 weeks
Coordinate partner’s needs for education response surge capacity. Identify/request additional information management/coordination support as necessary. | UNICEF, SCI | LWF, Plan, MRCS, CFSI, other partners | 2 weeks (+)
Mobilize initial response activities with government and partners using available resources, based on needs identifies | SEO, UNICEF, SCI | Sector partners | 2 weeks (+) (Continuous)
Coordinate and support the preparation of an initial education sectoral needs and damage assessment in the affected communities as necessary, with the Education Dept/Office and through Head teachers and Parent Teacher Associations (PTA). | SED/TEO, UNICEF, SCI | Sector partners | 1 to 2 weeks (+) (Continuous)
Up to four weeks
Further update plans and develop new proposals based on needs identified (to build on initial response plans and concept notes and move toward early recovery phase). | SED/TEO, UNICEF, SCI | Sector partners | 2 to 4 weeks (+)
Consolidate EiE response team so that initial assistance continues to be provided to the most vulnerable groups/villages, with focus on the most vulnerable groups. Deploy additional staff from emergency rosters to top up the response capacity. | SED/TEO, UNICEF, SCI | Sector partners | 2 to 4 weeks (+) (Continuous)
Identify and advocate for financial needs for the coming months and ensure that education is integrated in appeals, donor briefings, and other proposals in order to guarantee the adequate resources are mobilized to ensure the EiE response | UNICEF, SCI | Sector Partners | 3 to 4 weeks (+)
Establish information sharing or dissemination system through websites, bulletin, reports etc. Facilitate the exchange of ideas, information, statistics and other data among new and existing sector partners as well as externally. | UNICEF, SCI | Sector partners | 4 weeks (+)
Continue the conduct of initial sectoral assessments with the government as necessary | UNICEF, SCI | Sector partners | 4 weeks (+)

## Emergency Tele
Sector Standard Operating Procedures (SOPs) for Disaster Response ─ Updated May 2016 Emergency Telecommunications
Activity | Lead | Other Organizations | Timeline
Early Warning Phase
After Disaster
"Simplex" operation on pre-defined emergency channels. Pre-programming of radios to the correct frequency prior to departure is required. | ETC Cluster |  | 1st day
Shared basic internet connectivity distributed from a single location (internet cafe). Access to corporate webmail only. This service is available for a selected list of users only. | ETC Cluster |  | Within 24 hours
Basic voice connectivity to the international phone network for the humanitarian community | ETC Cluster |  | Within 24 hours
All project related activities, including the definition and submission for approval of a project document with well-defined objectives and timeline, a clear budget, regular project report, final handover/closure. | ETC Cluster |  | Ongoing
Within first weeks
Assessment of common security telecommunication infrastructure needs for humanitarian community | ETC Cluster | Government and Inter-Agencies | Week 1
Assessment of common ICT infrastructure needs for humanitarian community | ETC Cluster |  | Week 1
Act as the single focal point with government authorities on behalf of the humanitarian community for all radio, voice and data communications related matters including importation, frequency licensing and customs support. Frequency usage/control and allocation (VHF and HF) | ETC Cluster |  | Week 1
Coordinate with local authorities in the area of operation in order to deploy the equipment. | ETC Cluster |  | Week 1
Call sign management/allocation services are provided | ETC Cluster |  | Week 1
Collaboration with existing, regular ICT working group (inter-organization) meetings | ETC Cluster |  | Week 1
Advice and support in regards to importation, customs and logistics services | ETC Cluster |  | Week 1
Basic coverage around the main operational centre. This service may require re-programming of the equipment. | ETC Cluster |  | Week 1
Establish and maintain COMCEN(s) operating as per MOSS standards. | ETC Cluster |  | Week 1
Programming of radios or other equipment (as per standard) belonging to individual organizations to be provided on best effort basis. | ETC Cluster |  | Week 1
Shared internet connectivity distributed in an internet cafe as well as wider coverage within a common office area. Depending on available bandwidth, some services might be restricted. Access could be provided through a self-registration system or a secret password system. | ETC Cluster |  | From week 1
Voice connectivity to the international phone network through a number of dedicated channels depending on available lines or available/subscribed bandwidth. Voice connectivity between local users is provided. | ETC Cluster |  | Week 1
Within two weeks
Dedicated NGO coordinator to ensure NGO needs are considered in planning ETC operations, Service to be deployed on a case-by-case basis. | ETC Cluster |  | Week 2
Install and maintain a local voice exchange between organizations and individuals independent from (but possibly connected to) lobal or local public services. | ETC Cluster |  | Within 2 weeks
(Optional) Establish a dedicated GSM/WCDMA/LTE mobile network to be used by the humanitarian workers in the operational area(s). | ETC Cluster |  | Within 2 weeks
Within four weeks
Extended coverage within Common Operational Areas, including dedicated channels. | ETC Cluster |  | Week 3
Provide training of users and radio operators, through deployment of a radio trainer. | ETC Cluster |  | Week 3
Automated staff, vehicle and asset tracking based on VHF/UHF, GSM and/or satellite system with/without possibility of geo-fencing and alerting services. | ETC Cluster |  | Week 3
Alerting services to Sell-V VHF/UHF radios GSM and/or other portable devices (depending on available infrastructure). Specification of additional devices to be defined. | ETC Cluster |  | Week 3
Shared internet connectivity distributed to the offices of the individual organizations within the operational area. | ETC Cluster |  | 4 weeks
(Optional) If requested by an organization; provide dedicated internet bandwidth on a cost recovery basis (i.e. VPN, leased-lines, dedicated VSAT capacity to corporate facilities). | ETC Cluster |  | 1-4 weeks after request

## FSS
Sector Standard Operating Procedures (SOPs) for Disaster Response ─ Updated May 2016 FSS
Activity | Lead | Other Organizations | Timeline
Early Warning Phase
Obtain weather forecast from various sources | OCHA | UNDSS | Daily
Identify areas and population at risk | FSS | OCHA | Immediately
Prepare emergency roaster of staff | FSS |  | Immediately
Identify available emergency food stocks | FSS |  | Immediately
Identify emergency seeds, fertilisers and fishing gears stocks | FSS |  | Immediately
Immediately after disaster
Participate in coordination meetings (UN/NGOs, govt) | OCHA | FSS partners | 24hrs
Develop initial assessment plans (including logistics arrangements) | OCHA | FSS partners | 24hrs
Deploy initial assessment team(s) (multi-sector/cluster) | OCHA, FSS | FSS partners | 48hrs
Confirm beneficiary numbers and location | OCHA, FSS | FSS partners | 48 to 72hrs
Check existing stocks (and additional supplies) | FSS | FSS partners | 24hrs
Deliver HEBs | FSS | FSS partners | 72 hrs
Deploy food distribution team | FSS | FSS partners | 48 to 72hrs
Food distribution | FSS | FSS partners | 72hrs
Follow-up meetings (partners, govt) | OCHA | FSS partners | 96hrs
Within two weeks
Plan more detailed assessment (Food security assessment), if required | FSS | FSS partners | Day 5
Deploy Food security assessment team | FSS | FSS partners | Day 6
Check available food stocks | FSS | FSS partners | Day 7
Deliver food or cash assistance | FSS/CWG | FSS partners | Day 9
Food distribution | FSS | FSS partners | Day 9
Distribution of available stocks of seeds, fertiliser and fishing gears | FSS | FSS partners | Day 12
Follow-up meetings for gap analysis in the response (partners, govt) | OCHA | FSS partners | Day 12
Up to four weeks
Development of FSS strategic response plan for winter season and following year rainy season | FSS | FSS partners | Day 16 to 28
Rehabilitation of rice field embankments | FSS | FSS partners | Day 10 to 28
Technical worksession with fishery department to assess risk of overuse of resources | FSS | Gov, FAO, NGO | Day 20
Technical worksession with livestock actors to clarify needs and standards for restocking | FSS | Gov, FAO, NGO | Day 21
Technical worksession with fortestry department to assess need for reforestation | FSS | Gov, FAO, NGO | Day 22
Release of FSS strategy for support until end of following year rainy season | FSS |  | Day 28

## Health
Sector Standard Operating Procedures (SOPs) for Disaster Response ─ Updated May 2016 HEALTH
Activity | Lead | Other Organizations | Timeline
Early Warning (EW) Phase
Update and share 3W and contact list with relevant partners | Health Cluster | Cluster partners | 24 hours after EW
Initiate emergency coordination mechanisms | Health Cluster | Cluster partners | 24 hours after EW
Identify staff available for assessments | Health Cluster | Cluster partners | 24 hours after EW
Check with all partners on the pre-positioning and stock-piling of medical supplies and equipment including medicines and vaccines, hygiene and dignity kits, reproductive health kits and medication for treatment of trauma /acute /chronic diseases | Health Cluster | Cluster partners | 24 hours after EW
Immediately after disaster
Activate pre-identified assessment team | Health Cluster | Cluster partners | 2 days
Organize the health cluster meeting and sharing update information from assessment team | Health Cluster | Cluster partners | 3 days
Launch distribution of emergency supplies to the affected locations as per cluster stock-piling | Health Cluster | Cluster partners | 4 days
Re-establish disrupted health services through the establishment of static and/or mobile clinic (PHC, SRH, Nutrition) and eventually the setup of secondary care emergency facilities | Health Cluster | Cluster partners, UNICEF | 7 days
Activate communication, coordination system between field staff and based health facilities | Health Cluster | Cluster partners | 1 days
Implement Early Warning and Response System (EWARS) | Health Cluster | Cluster partners | 4 days
Within two weeks
Follow up the progress on the initial assessment | Health Cluster | Cluster partners | 2 weeks
Inter-cluster coordination with particular emphasis on Shelter,WaSH, Nutrition and Protection (set up of an effective inter-sectoral information management system) | Health Cluster | Cluster partners, UNICEF, UNHCR | 2 weeks
Provide measles vaccination to 9-months to 15-years old children relocated in the evacuation sites/IDP camps/host families | MoH, Health Cluster | Cluster partners, UNICEF | 2 weeks
To provide psychological first aid to the affected population | Health Cluster | Cluster partners, UNDP | 2 weeks
Up to four weeks
Adjust health sector strategy and response plan based on results of joint assessment | Health Cluster | MoH, Cluster partners, UNICEF | 3 weeks
Come up with a transition plan for the next 6-8 weeks | Health Cluster | MoH, Cluster partners, UNICEF | 4 weeks

## Logistics
Sector Standard Operating Procedures (SOPs) for Disaster Response ─ Updated May 2016 LOGISTICS
Activity | Lead | Other Organizations | Timeline
Early Warning Phase
Update and share the Logistics capacity assessment (including list of transoprters, storage facilities...) with the Logistics cluster members | LOG Cluster lead | UN/NGO | Immediately
Update and share with logistics cluster members information on emergency response equipment available in Yangon and at regional level | LOG Cluster lead | UN/NGO | Immediately
Identify staffs available for the emergency response from local, regional and international logistics rosters | LOG Cluster lead |  | Immediately
Verify Emergency Response Kits (mobile offices) | LOG Cluster lead |  | Immediately
Immediately after disaster
Evaluate staffing requirements to and organise support resources, particularly in the area of information management | LOG Cluster lead |  | within 2 days
Assess of logistics capacity (road, airport, port, storage, logistics service providers, custom clearance…) using decentralized resources, supported with centralized mobile teams (multi-sector/cluster) | LOG Cluster members | UN/NGO | within 2 days
Liaise with the Emergency Operation Center in Naypyidaw and with appropriate governmental counterpart at national and state level | LOG Cluster lead |  | within 2 days
Attend inter cluster coordination meetings in Yangon | LOG Cluster lead | OCHA | within 2 days
Organize regular centralized coordination meeting in Yangon and if required, decentrlaized ones at regional level | LOG Cluster lead | UN/NGO | within 3 days
Consolidate information on logistics gaps in the emergency response | LOG Cluster lead |  | within 4 days
Coordinate logistics assets / address capacity gaps using LOG Cluster member resources (for transport, storage, custom clearance...) | LOG Cluster lead | UN/NGO | within 4 days
If required act as provider of last resort (particularly for transport disaster hit area, setting up storage capacity...) | LOG Cluster lead |  | within 4 days
Coordinate international supply of emergency assets from Global Humanitarian Depots (UNHRD) if needed | LOG Cluster lead | UN/NGO | within 4 days
Share relevant logistic information - setup and maintain information-sharing platform (Logistics Cluster website) and share standard Logistics Cluster situation reports, assessments, concept of operations and other coordination tools | LOG Cluster lead | UN/NGO | within 4 days
Within two weeks
Develop concept of operation, supporting possible funding request to augment logistics response capacity for the humanitarian community | LOG Cluster lead | UN/NGO | within 7 days
Setup a Relief Item Tracking Application to provide visibility on resource movements | LOG Cluster lead | UN/NGO | within 7 days
Develop Standard Operating Procedures to define how to access to shared logistics capacity | LOG Cluster lead | UN/NGO | within 7 days
Up to four weeks
If required, review support staff requirements and adjust | LOG Cluster lead | UN/NGO | wihtin 30 days

## NFIs
Sector Standard Operating Procedures (SOPs) for Disaster Response ─ Updated May 2016 NFIs
Activity | Lead | Other Organizations | Timeline
Early Warning Phase
Mobilise NFI needs assessment team | NFI Cluster | Cluster partners | 5 days (maximum)
If population relocated, NFI distribution in advance of event | NFI Cluster | Cluster partners | 5 days (maximum)
Ensure 100% clarity across all partners/members on minimim NFI standards | NFI Cluster | Cluster partners | 5 days (maximum)
Mobilise NFI needs assessment support from national level (as required) | NFI Cluster | Cluster partners | 5 days (maximum)
Immediately after disaster
Mobilise assessment team, which includes evaluation of need for intersector assessment, led by OCHA | NFI Cluster | Cluster partners | 24 to 36hrs
Conduct rapid assessments of NFI needs for affected population, which can include security threats/risks, access to affected areas and logistical needs | NFI Cluster | Cluster partners | 72hrs
Distribute NFI core kits from contingency stock and any additional relief items demanded due to weather conditions and/or emergency circumstances | NFI Cluster | Cluster partners | 72hrs
Share information on results of rapid assessments with relevant stakeholders and decide on further actions | NFI Cluster | Cluster partners | 7 days
Organise suitably coordination meeting in Yangon, which can include liaising with appropriate government counterpart at national level | NFI Cluster | Cluster partners | 24 to 36hrs
Attend ICCG meeting in Yangon | NFI Cluster | OCHA | 24 to 48hrs
Within two weeks
Initiate procurement to supplement deliveries if initial distrbutionsinadquate | NFI Cluster | Cluster partners | 7 to 10 days
Deploy additional staff from emergency rosters | NFI Cluster | IFRC | 21 days
If appropriate, adjust plan/strategy | NFI Cluster | - | 28 days
Up to four weeks
Deploy additional staff from emergency rosters | NFI Cluster | IFRC | Within 28 days
If appropriate, adjust plan/strategy | NFI Cluster | Cluster partners | Within 28 days

## Nutrition
Sector Standard Operating Procedures (SOPs) for Disaster Response ─ Updated May 2016 NUTRITION
Activity | Lead | Other Organizations | Timeline
Early Warning Phase
Verify existing stocks of essential supplies including RUTF, fortified nutritional products including blended food, and micronutrient supplements and identify resources for gaps | UNICEF | National Nutrition Centre (NNC/MoH), Myanmar Nutrition Technical Network (MNTN) | 3 days
Strengthen/confirm existing coordination mechanisms or, if unavailable, create them in collaboration with national and local authorities to ensure that the humanitarian response is timely and coordinated, and that it conforms to humanitarian principles and agreed-upon standards and benchmarks. | UNICEF | NNC/MoH, MNTN | 5 days
Immediately after disaster
Take part in inter-agency coordination at national level | UNICEF | NNC/MoH, MNTN | 24hrs
Ensure and establish effective coordination mechanism among nutrition partners in Yangon | UNICEF | NNC/MoH, MNTN | 24hrs
Undertake a multi-sectoral rapid assessment, including key priority information for nutrition | UNICEF | MNTN | 48 to 72hrs and within 1 to 2 weeks
Advocate for and mobilize initial funding for the Nutrition Sector response | UNICEF | MNTN | Day 2 and ongoing
Release a joint statement on Breast Milk Substiture (BMS)/ Code to the media and all sectors/clusters to prevent the influx of BMS | UNICEF | NNC/MoH, MNTN | 7 days
Within two weeks
Share information on results of rapid assessments with relevant stakeholders at national level and decide on further actions | UNICEF | NNC/MoH, MNTN | 7 days
Organize coordination meeting, which can include liaising with appropriate government counterpart at national level | UNICEF | NNC/MoH, MNTN | 7 days
Ensure appropriate emergency nutrition response based on the needs of affected population. Response should follow sector/cluster responsibility and national/global humanitarian standards/guidelines | UNICEF | NNC/MoH, MNTN | 2 weeks
Consult with the affected communities for development and implementation of programme communication, and include relevant and evidence-based nutrition messages in all programme communication activities. | UNICEF | NNC/MoH, MNTN | 2 weeks
If necessary, deploy additional staff from emergency rosters to affected areas | UNICEF | NNC/MoH, MNTN | 2 weeks
Nutrition sector/cluster identifies needs and financial resources required for activities among nutrition partners (including advocacy) | UNICEF | NNC/MoH, MNTN | 2 weeks
Support the formulation of draft appeals involving all relevant partners | UNICEF | NNC/MoH, MNTN | 2 weeks
Up to four weeks
Establish and maintain Nutrition Information System | UNICEF |  | From week 1
Conduct joint monitoring | UNICEF | NNC/MoH, MNTN | From week 2
Routinely monitor all CMAM sites to prevent distribution of breast milk substitutes, bottles, teats, and other milk products | UNICEF | NNC/MoH, MNTN | From week 2
Monitor and report on key performance indicators | UNICEF | NNC/MoH, MNTN | Monthly

## Protection
Sector Standard Operating Procedures (SOPs) for Disaster Response ─ Updated May 2016 PROTECTION
Activity | Lead | Other Organizations | Timeline
Early Warning Phase
Mobilise assessment team / team members to participate in the initial multi sector rapid assessment | UNHCR | UNICEF, UNFPA, DRC | 3 days
Update and share 3W and contact list with relevant partners | UNHCR | UNICEF, UNFPA | 3 days
Immediately after disaster
Mobilise assessment team / team members to participate in the initial multi sector rapid assessment | UNHCR | UNICEF, UNFPA, DRC | Immediate
Activate response teams from the Protection Sector national standby emergency list (GBV emergency response teams, family separation screening teams, etc) | UNHCR, UNICEF, UNFPA | Protection WG, CP and GBV SWG | Immediate
Organise coordination meetings with relevant sector members and attend inter-sector coordination meetings | UNHCR | Protection WG. CP and GBV SWG | 24 to 36hrs
Mobilise assessment team / team members to participate in the initial multi sector rapid assessment | UNHCR | UNICEF, UNFPA, DRC | Immediate
Within two weeks
Conduct technical protection assessment and safety audits (to identify and mitigate additional risks across sectors) | UNHCR, UNICEF, UNFPA | Protection WG, CP and GBV SWG | 1 week
Deploy response teams from the Protection WG (GBV emergency response teams, family separation screening teams, etc) | UNHCR, UNICEF, UNFPA | Protection WG, CP and GBV SWG | 1 week
Map main protection issues and provide and assist solutions, based on the available, functioning services. | UNHCR, UNICEF, UNFPA | Protection WG, CP and GBV SWG | 1 week
Map main protection issues and provide for and assist solutions | UNHCR, UNICEF, UNFPA | Protection WG, CP and GBV SWG | 1 to 2 weeks
Map available services for GBV response | UNFPA
Conduct tracing and family reunification for Unaccompanied and Separated Children (UASC) & referral to interim care | UNICEF |  | 1 week
Conduct tracing and family reunification for elderly and persons with disabilities | UNHCR | MRCS, ICRC | 1 week
Reactivate the referral and management system (including GBV and CP) | UNHCR, UNICEF, UNFPA | Protection WG, CP and GBV SWG | 1 week
Establish child friendly spaces and outreach in host communities and in locations of displacement/relocation | UNICEF | SAVE, DRC | 1 week
Establish safe spaces and outreach for women, girls and survivors of GBV in locations of displacement/relocation | UNFPA | IRC | 1 week
Distribute protection related items as needed | UNHCR, UNICEF, UNFPA | Protection WG, CP and GBV SWG | 1 week
Up to four weeks
Establish an emergency complaints mechanism and disseminate information about it through radio messaging | UNHCR | Protection WG, CP and GBV SWG | 4 weeks
Report on initial protection monitoring findings and recommendations to ICCG and HCT to inform humanitarian response | UNHCR | Protection WG, CP and GBV SWG | 4 weeks

## Shelter
Sector Standard Operating Procedures (SOPs) for Disaster Response ─ Updated May 2016 SHELTER
Activity | Lead | Other Organizations | Timeline
Early Warning Phase
Mobilise emergency shelter needs assessment team | Shelter Cluster | Cluster partners | 5 days (maximum)
If population relocated, emergency shelter distribution in advance of event | Shelter Cluster | Cluster partners | 5 days (maximum)
Ensure 100% clarity across all partners/members on emergency shelter specifications & guidelines | Shelter Cluster | Cluster partners | 5 days (maximum)
Mobilise emergency shelter needs assessment support from national level (as required) | Shelter Cluster | Cluster partners | 5 days (maximum)
Immediately after disaster
Mobiliseassessment team, which includes evaluation of need for intersector assessment, led by OCHA | Shelter Cluster | Cluster partners | 24 to 36hrs
Conduct rapid assessments of emergency shelter needs for affected population, which can include security threats/risks, access to affected areas and logistical needs | Shelter Cluster | Cluster partners | 72hrs
Distribute emergency shelter from contingency stock | Shelter Cluster | Cluster partners | 72hrs
Share information on results of rapid assessments with relevant stakeholders and decide on further actions | Shelter Cluster | Cluster partners | 7 days
Organisedaily coordination meeting in Yangon, which can include liaising with appropriate government counterpart at national level | Shelter Cluster | Cluster partners | 24 to 36hrs
Attend ICC meeting in Yangon | Shelter Cluster | OCHA | 24 to 48hrs
Within two weeks
Initiate procurement to supplement deliveries if initial distrbutionsinadquate | Shelter Cluster | Cluster partners | 7 to 10 days
Deploy additional staff from emergency rosters | Shelter Cluster | IFRC | 21 days
If appropriate, adjust plan/strategy | Shelter Cluster |  | 28 days
Up to four weeks
Deploy additional staff from emergency rosters | Shelter Cluster | IFRC | Within 28 days
If appropriate, adjust plan/strategy | Shelter Cluster | Cluster partners | Within 28 days

## WASH
Sector Standard Operating Procedures (SOPs) for Disaster Response ─ Updated May 2016 WASH
Activity | Lead | Other Organizations | Timeline
Early Warning Phase
Mobilize WaSH Cluster team for field support | WASH Cluster | WaSH partners | Immediately
Pre-distribution of water reagent for water purification | WASH Cluster | WaSH partners | Immediately
Hygiene promotion team of partners re-enforced specific messages on good practices in such events | WASH Cluster | WaSH partners | Immediately
If population relocated, Hygiene Kit distribution mechanism set up for reactive distribution for most vulnerable, in evacuation center straight after the events | WASH Cluster | WaSH partners | Immediately
Immediately after disaster
Mobilize assessment team set up to join MIRA teams | WASH Cluster | Pre-listed | 24hrs.
Organize a specific daily coordination meeting in Yangon and the affected area | WASH Cluster | WaSH partners | Daily
Liaise with the appropriate governmental counterpart at national and state/region level | WASH Cluster
WaSH Cluster keeps close liaison with OCHA for update information | WASH Cluster | OCHA | Continous
WaSH Cluster share any relevant information with MIMU/OCHA | WASH Cluster
WaSH Cluster share assessment findings with partners | WASH Cluster
Liaise with OCHA/MIMU for mapping of needs | WASH Cluster | MIMU
Production of regular Wash Situation report and minutes meeting | WASH Cluster |  | Every 2nd day
Close link with either UNHCR or IOM on situation on evacuation sites | WASH Cluster | UNHCR/IOM
Mobilize stock available and define a supply process with UNICEF and other agencies from Yangon | WASH Cluster | UNICEF | 3 days
Identify partners to support distribution of Hygiene Kit and to deploy first WaSH support | WASH Cluster | Concerned organizations | 3 days
Inform UNICEF and OCHA on resource mobilization for WaSH needs | WASH Cluster | UNICEF/OCHA | 3 days
Communicate with Global cluster and UNICEF Bankgok regional office on preliminary analysis, needs and potential foreseen support needed | WASH Cluster | RECA | 3 days
Evaluate and deploy first water supply possibility for affected population and evaluate overall response cost in respect of technical standard pre-defined | WASH Cluster | WaSH partners | 5 days max
Supply emergency sanitation equipment and define first response possible and evaluate overall response cost in respect of technical standard pre-defined | WASH Cluster | WaSH partners | 5 days max.
Daily update of 3W, including capacity response | WASH Cluster |  | Daily
Monitoring of NFI supply | WASH Cluster | Implementing partners | Weekly
Within two weeks
Informed WaSH partners on mobilization of funds and donors support to the response | WASH Cluster | WaSH partners | Continous
Recruitment of additional Cluster staff to support the team in the affected area or coordination at national level | UNICEF | WaSH partners | 1 week
Consolidate the geographical positioning of each WaSH actors | WASH Cluster |  | 2 weeks
Consolidate supply chain for Hygiene Kits and any other equipment | WASH Cluster | WaSH Cluster | 2 weeks
Top-up the response capacity with concern of funding available/needed, HR needs, partners coverage, systematization of the response, consolidation of information management and gap identification | WASH Cluster | WaSH partners | 3 weeks
Upgrade 3W tools to measure the response coverage versus Sphere guide lines | WASH Cluster |  | 3 weeks
Within four weeks
Develop a proper briefing package for the arrival of new actors | WASH Cluster |  | 1 month
Top up the technical standard | WASH Cluster |  | 2 weeks
Re-enforce cross-cutting issue as gender, children access, handicap,… | WASH Cluster | WaSH partners | 1 month
Prepare early recovery phase in approach | WASH Cluster | WaSH partners | 1 month
Define a medium term (3 months) intervention strategy | WASH Cluster | WaSH partners | 1 month
Identify the most appropriate cluster coordination setting with government (co-leadership?) | WASH Cluster |  | 1 month
Support any logistic WaSH challenges with relevant agency (WFP if defined logistic cluster) | WASH Cluster | WaSH partners
Conduct a wash base line survey | WASH Cluster | WaSH partners | 2 weeks
Organize external need assessment if not yet deployed | WASH Cluster | RECA | 2 weeks
Identify and advocate for financial needs for next 3 months | WASH Cluster |  | 3 weeks