Inter-Agency PHC Support Prioritization

Minutes of the Meeting (MoM)

(Beirut and ML) - (10 November 2017)

Actors Present:

|  | Name | Organization | Position | Phone | Email |
| --- | --- | --- | --- | --- | --- |
| 1 | Luis Rosa Sosa | PU-AMI | Health Coordinator | 76435 803 | lib.health@pu-ami.org |
| 2 | Racha | PU-AMI | Project manager Health |  | lib.pm-health.sai@pu-ami.org |
| 3 | Nancy Aslan | IMC | Health Area Manager | 76469551 | naslan@internationalmedicalcorpse.org |
| 4 | Nahil Farran | UNHCR | Senior Programme Assistant | 76421612 | farran@unhcr.org |

List of PHCs prioritized for support in Beirut and ML governorate

|  | District | Name of PHC | MoPH/PHC (Yes/No) | Current support/ till when | Priority | Follow up |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Beirut | -Dar El Fatwa PHCc -Makassed PHCc in Bachoura -Zaharaa PHC - Qarantina PHC Center | -Yes -Yes -Yes -Yes | -RI/till February 2018 (Decision Not final yet) -Not Supported -Not Supported -Not Supported | 2nd priority 1st priority 1st priority- 2nd priority 1st priority | -Dar El Fatwa is considered as a first priority for PU-AMI to be supported in 2018 -After assessment by IMC; the PHC is not considered for support in 2018 -After assessment by IMC and coordination with MoPH; this PHC is considered as a second priority by IMC to be supported in 2018 -After assessment by PU-AMI and coordination with MoPH; this PHC is considered as a first priority by PU-AMI to be supported in 2018 |
| 2 | Jbeil | MoPH Jbeil PHCc | Yes | IMC/till end of December 2017 | 1st priority | Only PHCc contracted in Jbeil district; IMC will be supporting in 2018 |
| 3 | Keserwan | Hrajel PHCc | Yes | RI/ Till end of October 2017 | Not a priority PHCc | Partners to assess PHCc in Zouk for possible support. Half of the registered refugees living in Keserwan reside in coastal areas. However, There are no supported PHCs in Coastal area; mainly Jounieh, Zouk and Ghazir which are populated areas. Three PHC centers in the MoPH network were approached/assessed in Zouk in 2017 by IMC but with no positive outcome. MOPH suggested to assess: -Cedars Medical Center - Zouk Mkeyel -Socio-Medical Center - Zouk Mikael -Fersan Malta dispensary- Zouk Mikael |
| 4 | El Meten | Karagheusian PHCc | Yes | IMC/ Till end of December 2017 | 1st priority | IMC will be supporting in 2018 IMC will also support the following PHCs in 2018: Dr. Wadih El hajj Medical Center- Baskinta Saint Antonios Dispensary – Jdaideh Socio-Medical Center - El Fanar |
| 5 | Baabda | Bent El Hoda PHCc | Yes | RI/ /till February 2018 (Decision Not final yet) | 1st priority | IMC will be supporting in 2018 |
| 6 | Baabda | Ataa Bila Houdoud PHCc | Yes | IMC/ till end of December 2017 | 1st priority | IMC will be supporting in 2018 |
| 7 | Baabda | RHUH PHCc | Yes | IMC/ till end of December 2017 | 1st priority | IMC is considering to support in 2018 |
| 8 | Baabda Baabda | Leb. Association Early Childhood Develop. LRC PHCc in Chiyah | No Yes | IMC/ till end of November 2017 RI/ Till end of October 2017 | 1st priority 1st priority 2nd priority | IMC will be supporting in 2018 |
| 9 | Baabda | Alkayan Medical Center | Yes | IMC /Till end of October 2017 | 1st priority | IMC will be supporting in 2018 |
| 10 | Aley | Aramoun Health Center | Yes | IMC/Till end of October 2017 | 2nd priority | IMC will be supporting in 2018 |
| 11 | Aley | Emir majid arslan | Yes | PU-AMI/till end of September 2017 IMC/ till end of November 2017 | 1st priority | PU-AMI will be supporting in 2018 |
| 12 | Aley | URDA-ALWAFAA | No | URDA/Till end of December 2017 | 1st priority | The center was assessed by MoPH and it is pending the final approval. IMC is considering to support this PHC as a first priority in 2018, pending discussions and MoPH decision. |
| 13 | Aley | HIS- El Imam Zein El-Abiddine Center | No | IMC/Till end pf October 2017 | 1st priority | IMC will be supporting in 2018 |
| 14 | Chouf | Chhim Governmental Health Center | Yes | RI/till end of October 2017 | Not a priority due to accessibility issues | Partner to assess Ikleem PHCc in Chhim for possible support replacing Chhim gov PHCc Barja, Naame and Chhim are densely populated areas and are considered of the most vulnerable. IMC will be supporting Barja Cultural in 2018 |
| 15 | Chouf | Haret Naame MoSA PHCc | Yes | IMC/ till end of November 2017 | Not a priority PHCc | Partners to assess other centers in Khalde and Naameh for support However, there are no supported PHCs in Rmeileh, Jiyeh, Jadra and Damour (costal side) |
| 16 | Chouf | The Awareness and Consolation Association/ Sayer ketermaya PHC | Yes | PU-AMI/ till end of September 2017 | 1st priority | PU-AMI will be supporting in 2018 |

1-An assessment visit will be conducted to a new clinic in Cola- Beirut area. The clinic will be managed by IIROSA (International Islamic Relief Organization of Saudi Arabia) and Dar el Fatwa is supporting in the official documents and permit needed from MOPH

2-One PHC center is supported in Aley city- URDA-Al Mraa aldrzya by MDM and will be supported till 2019.