ECE coordination minutes of meeting

The ECE coordination meeting was held on Jan 12 2017 in the IRC office and all ECE partners for Akkar and T5 were attending: AVSI , Concern, NRC , SCI , IRC , Ana Aqraa, Malak, World vision , war child Holland

First discussion between partners was regarding the targets, and if they think that targets already planned is feasible to be achieved.

The different cycles and number of hours per cycle was also discussed.

Farah representing Concern stated that they are having difficulties in reaching their targets.

Joyce representing Malak NGO was saying that they are finding a lot of ECE students that can be reached easily especially from their experience in Sahel Miniara.

Anas representing IRC stated that according to the assessment done the numbers of ECE age children is high and a lot of children are not reached with education yet.

**ECE Targets in Akkar and T5 of attending NGO s are as following:**

IRC: 1,500 ECE children in Akkar

NRC: 700 ECE Children divided into 350 for Akkar and 350 T5

SAVE THE CHILDREN: 700 (500 in Akkar and 200 in T5)

AVSI: 500 ECE children in T5

MALAAK: 120 ECE children in Akkar

CONCERN: 500 ECE children in Akkar

WAR CHILD Holland: 120 ECE children (40 in Akkar and 80 in T5)

WORLD VISION: 500 ECE children in Akkar

ANA AQRAA: 700 (350 in Akkar and 350 in T5)

According to UNHCR numbers we have around 11,800 (3-5) children in Akkar and 24,102 (3-5) children in T5 and we are hoping to get the numbers of children registered in PS from these numbers !

**Areas where NGOs are implementing ECE in Akkar are as following:**

* IRC : knayseh , hnaider, Rajem issa, Hisheh , Bani sakher , Khalsa , akroum , Kfartoun , halba , mashha, arqa, berqayel , ar2af , sheikh mhammad , ebbet shamra( IS code needed) , abboudiyyeh , bellenit hissa, tal abbas jawhar only ,
* Save the children (350 in akkar ece): Mhammra( with 100 ece children only from mhammara) and Dawseh ,
* NRC( target 350 in akkar ) :Tal bibe ( tal hayat , tal meeyen ), halba,
* Malak : Arqa, Kousha , Minyara , Bahsa
* Concern : Mhammara , Tekrit , kweishra , Bebnine , Kousha , Hweish , Fnaideq

+ Is : wadi jamous p-code 7; 12---tal abbas 42

* War Child: Ar7a , m22aibleh , haizouq, tal bireh , bani sakher , khat l petrole , sweisseh , kherbet l jendi , cheikh zennet, erneh , minyara , rahbeh , bzel , bazbina , bet younes , awedeh
* World vision : der dalloum , smaqli ebbet shamra , rmoul , sammouniyyeh (62,69,70 )

After discussion about the locations and the overlap that may happen between NGOs, the following bilateral coordination is suggested to happen:

|  |  |  |  |
| --- | --- | --- | --- |
| **NGO** | **Needs to coordinate with** | **regarding** |  |
| IRC | * NRC * W.V * Concern | * Halba and Tal Abbas Jawhar * Kobbet Shamra and Bellanit Al Hisa * Bireh and Wadi AL Jamous |  |
| Save The Children | * IRC | * Mhammara |  |
| NRC | * IRC * World vision | * Halba * Tal Bibe ( Tal Hayat and Tal meeyan ) and rmoul |  |
| Malaak | * IRC * Concern | * Miniara and Arqa * Kweishra |  |
| Concern | * IRC * Save the children | * Bebnine and Kweshra and Saadine * Kweshra |  |
| World Vision | * NRC * IRC | * Rmoul * Sammouniyyeh and Semmaqli |  |

**Areas where NGOs are implementing ECE in T5 are as following:**

* AVSI : mina , zehriyyeh , alamoun and beddawi( target 500 )
* NRC: mina ,alamoun , abu samra , beddawi ( target 350\_
* Save : Douma in Batroun , ayrouniyyeh , sir el denniyeh ,jabal al beddawi , wadi l nahleh ,jabal mehsen (target 500)
* Ana aqraa : no potential locations (target 350 )
* War child :Tripoli city , zgharta , koura ( kfar aqqa , kfar hazir , ras masqa), batroun( chekka , kfar abida 3enrin ) , denniyeh( atteen , 7a2let l 3azimeh , ebn l haytham , mechtayel ,azky , l 7a2leh ) (target 80)

Coordination

* AVSI needs to coordinate with NRC and SCI in bedawi , with NRC for Mina and Alamoun
* SCI needs to coordinate with NRC and AVSI for beddawi , and with NRC for wadi nahleh
* War child Holland needs to coordinate with NRC and AVSI for Tripoli city

**Transportation**

AVSI (in some areas not in ISs), SCI, NRC, WV,Concern , WCH,Ana Aqraa, Malak

Procedure for transportation: war child Holland: timesheet, they deal with the bus driver, they pay him

NRC: paying cash support for transportation to the parents based on the attendance through liban post (transfer) only in Tripoli. In Akkar, they pay the bus driver, no cash support

SCI: cash assistance with parents last year, but parents were not paying to the driver so they changed it now. In some areas they do it through direct contact with the supplier, in other location through a card, based on the budget.In Sir, the parents were using their own cars, and the money paid from SCI for gas or something else

Concern: in the pilot project, they paid cash but it was risky because taking cash to the community is risky, transferring money is expensive so now they got companies involved because they have their own safety rules for kids, but recently they took the decision to not use the company because sometimes drivers refuse to drive the kids if payments were late so from now on they are going to pay directly to the driver

Parents are getting money from caritas but they are not paying the driver.

War child Holland: they make the driver sign a code of conduct

SNACK: NRC; SAVE; WV

Malak have a kitchen in the center