## Sheet1
PRIORITY | OBJECTIVE | ACTIVITIES | RESPONSIBILITY | DEADLINE | Remaining Days | STATUS | Legend of Initials:
1 | Rehabilitation of Substandard Building - Technical Assessment | 1- Share the assessment with Core Group members for revision and endorsement. | AA & CG | 2018-04-19 | 1 | Ongoing | AA: Abdulrahman Abdulghani MR: Mazen Riachi MJ: Malcolm Johnstone CB: Clementine Brown CBL: Cyrill Ble MS: Maroun Sader FC: Field Coordinators CS: Carol Sparks CG: Core Group
|  | 2- Digitize the assessment and share with partners for piloting. | AA & CB/MS | 2018-04-25 | 7 | Pending
|  | 3- Revise the assessment based on findings from pilot and revise the shelter vulnerability scoring accordingly. | AA & CG | 2018-04-28 | 10 | Pending
|  | 4- Final endorsement by Core Group and then by Sector members followed by a presentation at the NSWG. | AA & CG | 2018-05-02 | 14 | Pending
2 | Minor Repair of Non-Residential Substandard Building Technical Guidelines | 1- Revise the latest version of the guidelines dating back to 2015 and propose recommendation to SCI to make modifications. | CG | 2018-04-19 | 1 | Pending
|  | 2- Update the guidelines and present an updated draft to the Core Group for endorsement. | SCI | 2018-04-27 | 9 | Pending
|  | 3- Present the final document at the NSWG | SCI | 2018-05-02 | 14 | Pending
1 | Weatherproofing in Informal Settlements - Technical Assessment | 1- Complete the testing of the technical assessment and revise the questionnaire in accordance with findings. | Medair & SCI & UNHCR | 2018-04-16 | -2 | Ongoing
|  | 2- Issue the finalized documents and technical assessment to Shelter sector partners. | UNHCR & AA | 2018-04-23 | 5 | Pending
|  | 3- Organize a technical training for partners that are implementing weatherproofing in informal settlements. | UNHCR & AA | 2018-04-30 | 12 | Pending
2 | Site Improvements Technical Guidelines | 1- Activate the Temporary Technical Committee (TTC7) to revise the Site Improvement technical guidelines. | AA | 2018-03-26 | -23 | Completed
|  | 2- Revise the guidelines in consultation with core group members and WATER sector. | Medair & CG | 2018-04-28 | 10 | Ongoing
|  | 3- Finalize the revision of guidelines and present the updated vesion at the NSWG. | Medair | 2018-05-08 | 20 | Pending
1 | Neighbourhood Profiling Guidelines | 1- Revise the existing guidelines and provide comments/recommendations to UN-Habitat to produce an updated version of the existing document. The revised document should tackle the prioritization process of neighbourhoods as well as the minimum profiling requirements for a profile to be counted under the LCRP. | AA & MR & MJ | 2018-04-30 | 12 | Ongoing
|  | 2- Present the guideline's updated version to the Core Group and involve key sector coordinators (e.g. WATER, Livelihood, Protection) when required in the revision discussions. | AA & MR & MJ & CS & UN-Habitat |  | -43208 | Pending
|  | 3- Present and share the updated guidelines with the Intersector for their comments and endorsement. | UN-Habitat |  | -43208 | Pending
1 | Fire Training for Field Staff - North, South and BML | 1- Compile a list of agencies interested in partaking in the training. | AA | 2018-04-20 | 2 | Pending
|  | 2- Arrange for the training session(s) in cooperation with SCI. | AA |  | -43208 | Pending
2 | Advocacy Strategy | 1- Provide an outline and a template for the advocacy strategy document based on the advocay messages that were produced and endorsed by the Core Group. | NRC & MR & MJ |  | -43208 | Pending
|  | 2- Finalize the advocacy strategy draft and aquire endorsement of Core Group. | CG |  | -43208 | Pending
|  | 3- Present Strategy at NSWG. | AA |  | -43208 | Pending
1 | Shelter Sector Response Strategy | 1- Prepare draft outline to be endorsed by Core Group. | AA & MJ & MR |  | -43208 | Pending
3 | Sector Research Questions | 1- Create an online google doc and share with Core Group for proposing research topics that the shelter would want to investigate. | MJ |  | -43208 | Pending
1 | Impact Measurement Tools | 1- Consult with M&E specialist on the required steps to come up with impact measurement tools. | AA & MJ & MR |  | -43208 | Pending
2 | Shelter Sector Contact List | 1- Compile a Shelter Sector contact list | CBL |  | -43208 | Pending
2 | Clean up of RAIS and AI Rehabilitation Reporting | 1- Clean all false reporting for 2017 and issue a note to partners clarifying common reporting mistakes. | AA & RK | 2018-04-30 | 12 | Pending
1 | Rehabilitation Gap Analysis and Heat Map | 1- Repeat the exercise that was conducted in November 2017. | CBL & AA | 2018-10-15 | 180 | Pending
3 | Collective Site Mapping Tool (COSIMA) | 1- Finalize the mapping tool. | AA & LK & CB | 2018-04-11 | -7 | Completed
|  | 2- Issue the finalized mapping tool, SOPs and concept document with the shelter field coodinators. | AA | 2018-04-13 | -5 | Completed
|  | 3- Schedule training sessions for field staff on how to use the mapping tool. | AA & CB & FC | 2018-04-20 | 2 | Ongoing
Formulas:
Remaining Days = [DEADLINE]-TODAY()

## Sheet2
Status
Completed
Pending
Ongoing