## 2018 Workplan
Health Sector 2018 Workplan
Action identified | Key activities/outcomes | Comments | Updates | Responsible
Health Services Coverage and information dissemination | Ensure the Health Sector 5Ws in updated on a regular basis and shared with partners | Ongoing | Last Update May 2018 | Hala Abou Farhat (IA/UNHCR)
| Ensure the PHC Masterlist is updated on a regular basis and shared with partners | Ongoing | Next round of updates in May-June 2018 | Hala Abou Farhat (IA/UNHCR)
| Ensure the Mobile Medical Units (MMUs) mapping is updated on a regular basis and shared with partners | Ongoing | Next round of updates in June 2018 | Hala Abou Farhat (IA/UNHCR)
| Ensure the Health Gateways Dynamic Map are updated on a regular basis | Ongoing | Next round of updates in June 2018 | Hala Abou Farhat (IA/UNHCR) Maroun Sader (IM/UNHCR)
| Prepare a list of partners supporting access to hospital care/SHC to be shared with partners | Deadline end of April 2018 | To be finalized 1st week of June 2018 | Hala Abou Farhat (IA/UNHCR)
| Prepare a presentation targeting non-health partners on Access to Health Services and referral pathways | Deadline end of April 2018 | To be finalized 1st week of June 2018 | Hala Abou Farhat (IA/UNHCR)
| Ensure the updated Health Leaflets and list of UNHCR/NEXtCARE hospitals are shared on a regular basis with partners and frontliners | Ongoing |  | Hala Abou Farhat (IA/UNHCR)
Engaging with communities | Support UNHCR Communication with Communities Unit is producing updated Health Leaflets on a regular basis and shared with partners | Ongoing- done from May 2018 Update |  | Hala Abou Farhat (IA/UNHCR) Maroun Sader (IM Health Sector FP/UNHCR) Marie Akiki (PHU/ UNHCR) Jerome Seregni (CwCs/UNHCR)
Increase information and tool sharing among members of the HWG | To update the dropbox folder to include all tools/materials developed by Health Partners | An inventory of existing IEC material was produced. | Deadline for it to be updated by partners is End of June 2018 | Hala Abou Farhat (IA/UNHCR) WHO Colleagues
| To develop an inventory of the tools/materials available through the dropbox folder | Deadline to update inventory is mid-July 2018 | Inventory was finalized in May 2018 | Hala Abou Farhat (IA/UNHCR) Hiba Taha (IA/UNHCR)
| To ensure the Inter-Agency Information Sharing Data Portal, Health Sector Working Group Page is up-to-date | Ongoing Deadline: End of May for Q1 documents | All Q1 docs are available on the portal | Hala Abou Farhat (IA/UNHCR) Maroun Sader (IM/UNHCR)
Coordination of Medical Missions | To prepare a list of medical missions planned by partners in 2018. | Deadline 1st week of June 2018 | Info has been provided by partners | Hala Abou Farhat (IA/UNHCR)
Strenghtening Referrals from PHC facilities to SGBV services (including CMR) | Follow-up with the SGBV TF on the development of a draft circular as well as draft posters to be shared with MoPH | Ongoing | 1st deadline is mid-may for messages and draft circular | Hala Abou Farhat (IA/UNHCR) Lorenza Trulli (SGBV TF/UNFPA)
| Follow-up with MoPH and partners re. endorsement of tools and dissemination of the information to facilities | Ongoing |  | Hala Abou Farhat (IA/UNHCR)
Increasing accountability in terms of Health Referrals | Develop an automatized mechanism/tool for Health Referrals | Deadline mid- June 2018 |  | Hala Abou Farhat (IA/UNHCR) Raffi Kouzoudjian (IM/UNHCR)
| Pilot the automatized mechanism/tool for Health Referrals | Deadline mid- June 2018 |  | UNHCR PH Field Colleagues UNHCR PH Unit BO
| Incorporate feedback from field colleagues and launch the automatized mechanism/tool for Health Referrals | Deadline end of July 2018 |  | Hala Abou Farhat (IA/UNHCR) Raffi Kouzoudjian (IM/UNHCR)
Support to PHCs | Launch Survey looking into partners support to PHCs | 2018-06-01 |  | Hala Abou Farhat (IA/UNHCR)
Data Analysis | Prepare a list of gaps in PHC support | Ongoing - Deadline April 2018 | Done! | Hala Abou Farhat (IA/UNHCR) UNHCR PH Unit BO
| Liaise with MHPSS TF to indentify gaps in access to MH services | Ongoing - Deadline April 2018 |  | Hala Abou Farhat (IA/UNHCR)
| Update the funding gaps document on a regular basis | Deadline Q2 2018 |  | Hala Abou Farhat (IA/UNHCR) Health Sector Core Group members
| Keep track of list of studies/assessments planned for 2018 as well as information gaps | Ongoing - Deadline April 2018 | Done! | Hala Abou Farhat (IA/UNHCR)
| Develop a template for detailed financial reporting of Health Sector Partners and disseminate |  | To discuss in Core Group | Health Sector Core Group members
Advocacy | Update the advocay messages on a regular basis | Quaterly basis |  | Hala Abou Farhat (IA/UNHCR) Health Sector Core Group members
Institutional support | Ensure that detailed information on Institutional Support is captured on a regular basis through quarterly reporting of partners | Ongoing for Q1 of 2018 Deadline: Info to be included as an Annex in the first sectoral dashboard of 2018 | Presently being compiled for 1st dashboard of 2018 | Hala Abou Farhat (IA/UNHCR)
Dialysis Support | Maintain an updated list of patients in need of dialysis | Ongoing |  | Hala Abou Farhat (IA/UNHCR)
| Develop advocacy tools aimed at supporting fundraising for dialysis | Ongoing |  | Hala Abou Farhat (IA/UNHCR)