## Workplan 2018
Education Sector Workplan 2018
Thematic Area | Key activities/outcomes | Comments | Responsible Agencies
Access
Rollout Back to School (BTS) outreach campaign | Organise awareness raising, mobilise communities, identify and refer children/youth to the formal and non-formal education facilities. Share BTS findings with MEHE and parnters end of quarter 2 | Ongoing | MEHE, UN and NGOs
Enrolment and registration of childrein and youth into formal education (primary education, secondary education, vocational education and tertiary) | Registration/enrolment, subsidisation of school fee, provision of teaching and learning supplies and transportation support | Sept/Oct | MEHE
Enrolment and registration of children and youth into non-formal education | Registration/enrolment, subsidisation of school fee, provision of text-books. Roll out of vocational trainings in collaboration with line ministries (Ministry of Education, Ministry of Labour etc.) | Ongoing | MEHE, UN and NGOs
Inclusive Education | Children with special needs identified, referred and enrolled in formal and non-formal education facilities | Ongoing | MEHE, UN and NGOs
Construction and rehabilitation of school buildings | School infrastructure needs assessment, construct new classrooms, repair/rehabiliate damage structures to enable learning to take place | Ongoing | MEHE, UN and NGOs
Public school buildings fully furnished in line with MEHE specifications | Provision of equipment, desks, chairs, blackboards and other relevant equipment to enable the class to be utilised for teaching | Ongoing | MEHE, UN and NGOs
Quality
Training of teachers and Education personnel | ToTs for CERD master trainers. Teacher training on inclusive education, psychosocial support, pedagogical skills, classroom managements, positive discipline, life skills, citizenship education programmes, ICT/technology etc. Provision of awareness raising sessions for refugee parents to identify and refer children with specific needs (who have learning disabilities or difficulties) | Ongoing | MEHE
Children and youth attending regulated NFE transitioned to formal education | Conduct data analysis to review transition/success rate of students from last grade to new grade of scholastic year | Ongoing | MEHE, UN and NGOs
Monitor Rentention rates of students | Conduct data analysis, identify children at risk of dropout, early interventions to mitigate risk | Ongoing | MEHE
Monitoring visits in second shift schools | Academic monitoring visits conducted by DOPS counsellors in second shift schools | Ongoing | MEHE
Remedial Education and home work support programme | Provision of regulated Remedial Education and home work/language support to children at risk of dropout inside and outside public schools | Ongoing | MEHE, UN and NGOs
CP violence cases identified and referred for follow up | identification and referral of child protection cases to MEHE by education partners | Ongoing | MEHE, UN and NGOs
Deploy community liaison volunteers | Provision of refugee volunteers inside public schools to contribute to a safer learning environment | Ongoing | UN
Increased parental Engagement in children education | Increase parents engagement in their children’s education through participation in Parents Community Groups | Ongoing | UN
Institutional support and governance
NFE programmes regulated and endorsed by MEHE | Developing guidance, SOPs, text-books, teacher guide for remaining NFE non-regulated programmes to be regulated | Ongoing | MEHE
Child Protection policy guidelines | Implementation of Child Protection policy (capacity building and referrals) | June | MEHE
Ongoing technical support to PMU, CERD and DOPS | Deoplyments of technical advisors, support for recuritment and capacity building | Ongoing | UN Agencies
Quality control standards for planning, procurement and financial management for PMU and CERD endorsed and operational | Provide support to PMU and CERD training on planning and procurement | Ongoing
Information Management and reporting
Data collection and analysis | 1) Education data collection and monitorig platform creation and maintenance on Activity Info. 2) Education service mapping (5W matrix). | Ongoing | Education Sector
Monthly and quarterly dashboards | Education sector data dissemination through monthly/quarterly datasheets, maps, infographics. | Ongoing | MEHE/Education Sector
Education Sector Partners capacity building | Training partner staff members in sector-endorsed tools (e.g. mapping, activity info database). | Ongoing | Education Sector
End of Year and PIST report | Meeting interagency requirements: monthly statistical dashboards; quarterly/EoY dashbords and reports. | Ongoing | MEHE/Education Sector