|  |
| --- |
| **PUBLIC HEALTH SECTOR – UNHCR** **WEEKLY TEAM MEETING****9th July 2018****Time:** 8:30 AM Monday**Venue:** UNHCR office**Attendance:** Dr. Julius, Dr. Ronald, Ibrahim, Emmanuel, Ahmed**Chaired by:** Dr. Julius |
| **Sub-sector updates** | **Actions & way forward** |
|  |  |
| **RH & HIV – Ronald*** Had a meeting with JPIAGO to discuss RH issues, discussed Fistula
* RH performance shared with high neonatal rates in some locations
 | * Cervical cancer screening & Treatment data - Emmanuel
* Need to track HPV vaccination implementation in settlements –Emmanuel
* Need to get data on Fistula from settlements- Emma
* IGAD reporting by 20th of the month – July
* Will meet Marie stopes and RHU
* Pepfar
* Need to organise circumcision camps to increase coverage
 |
| **Pharmacy & Medical logistics – Ahmed*** A balance of the LLIN to be redistributed
* 2019 quantification received
* 60% NDA clearance received
* Redistribution from AIRD will be done this week
* Planning a mission from 9th to 25th in SW & MD
 | * Ahmed to provide summary indicators for Pharmacy to be included on the monthly indicators - Julius
* Follow up on Ebola items
* Review partners orders before they purchase medicines
 |
| Health Information – Emmanuel * Follow up on PEPFAR reporting
 | * Organise monthly meetings to discuss Monthly reports – Friday before 15th
* Follow up on Uganda EMR report from MoH
* Follow up on Master facility list
* VHT reporting tool piloting
 |
| Public health - Ibrahim* Meeting AMREF
* Ministry introduced rotavirus vaccines
* Quantifications for 2019
* LLINs distribution on going in all settlements
* VHT pilot not kicked off well
* Mid-year review coming up
 | * Follow up with IM on fact sheet and website design to include over view – Emmanuel
 |
| Julius* Had a management meeting last week and staff reduction was discussed and organogram will not change
* Coordination meeting tomorrow at MoH
* KW meeting in the week
* Cholera vaccine started and will be extended due to low coverage
 | * Gaps data should be ready before Wednesday – Emmanuel
* Every survey will have refugee component in Uganda
* Cholera vaccination will be intensified
 |

**Compiled by**: Emmanuel Omwony