|  |
| --- |
| **PUBLIC HEALTH SECTOR – UNHCR** **WEEKLY TEAM MEETING****2nd July 2018****Time:** 8:30 AM Monday**Venue:** UNHCR office**Attendance:** Dr. Julius, Dr. Ronald, Ibrahim, Emmanuel, Ahmed & Isaac**Chaired by:** Dr. Julius |
| **Sub-sector updates** | **Actions & way forward** |
| **PH – Ibrahim*** Meeting at UNICEF to fill the gaps in Ebola response
* Red cross will take up Kanungu and Kisoro, support WASH partners in transit centers and receptions
* UNICEF would support partner trainings on Ebola
* Unicef to support waste management facilities
* MoH proposes to use EBOLA vaccine in Uganda but only for study purposes.
* WHO supplied Ebola RDTs to UVRI and will also be supplied to other settlements
* NO VHF tested positive in Mubende following the scare of Ebola outbreak
* Need to develop SOPs for disinfecting registration equipment at the boarder points
* Partners are procuring medicines which UNHCR also has some
* Discussed the VHT voucher scheme
* Multi-antigen campaigns to kick off
 | * Uganda red cross planned to train, community awareness and boarder screening
 |
| **RH & HIV – Ronald*** HTS meeting was held with IPs (AHA & MTI). Assisted partner notification but challenges were lack of trainings for the identifiers and lack of tools
* Had a mission to West Nile with IGAD to revere performance
* Much of the IGAD funds have not been used since they were received late
* UNFPA set up regional points to do FP,,,
 | * Should use trained cadres for APN
* MoH will share the tools for APN
* Kyaka to organise VMMC camps
 |
| **Pharmacy & Medical logistics – Ahmed*** Low stocks of tracer medicines across settlements
* Finalised technical review for local procurement
* Monthly stock status report available
* Need to revise essential medicines list
* Shared a memo on redistribution of medicines
* Medical equipment are non-functional in settlements
 | * Need to have an inventory management of medical equipment
* Should share monthly stock status report by Wednesday 15th together with the HIS reports
 |
| **Health Information – Emmanuel** * HIS mission in West Nile (Bidibidi and Palorinya) and lack of tools & poor documentation were major issues. Rolled out VHT reporting tools and followed up with referral database
* Had a protection meeting at IAU and there were many non-medical cases residing at the medical hostel. Delays in processing funds was a challenge as well.
* Submitted Pepfar reports for Q3
* 6 measles cases in Kyangwali and need follow up

This week:* Compile and submit HIS reports and have a discussion on Tuesday Afternoon
* Compile and share VHT reports from Bidibidi and Palorinya were the pilot is taking place
* Will share the referral database as well
* Fact sheet completed by Friday
 | * Update twine with outbreaks
* Share surveillance data
* Update the gaps matrix
 |
| **Public health - Isaac*** Attended review or IMAM guidelines
* FSNA preparation on going
* Results for mass nutrition screening has been released for Kyangwali
* Commodity reports for RUTF received is needed
 | * Follow up on JAM
* Conduct FSANA in October and share results table by November 2018
* Share results of the Mass nutrition screening in Kyangwali
 |
| **Julius*** ANN Burton is coming to the country, advocacy and address challenges. Will visit locations of rift valley fever.
* Conference on Wednesday and Thursday at Serena
* Training on mental health
* Had a mission on Ebola preparedness in SW
* An audit on coordination, monitoring and import
* Regional public health meeting will be held in Uganda and possibly all will attend
 | * Prepare mission reports, weekly, monthly reports and minutes of coordination meetings for the audit team and file them – Emmanuel
* Ibrahim to attend the mental health training
 |

**Compiled by**: Emmanuel Omwony