| PUBLIC HEALTH SECTOR – UNHCR WEEKLY TEAM MEETING 2nd July 2018 Time: 8:30 AM Monday Venue: UNHCR office Attendance: Dr. Julius, Dr. Ronald, Ibrahim, Emmanuel, Ahmed & Isaac Chaired by: Dr. Julius |  |
| --- | --- |
| Sub-sector updates | Actions & way forward |
| PH – Ibrahim - Meeting at UNICEF to fill the gaps in Ebola response - Red cross will take up Kanungu and Kisoro, support WASH partners in transit centers and receptions - UNICEF would support partner trainings on Ebola - Unicef to support waste management facilities - MoH proposes to use EBOLA vaccine in Uganda but only for study purposes. - WHO supplied Ebola RDTs to UVRI and will also be supplied to other settlements - NO VHF tested positive in Mubende following the scare of Ebola outbreak - Need to develop SOPs for disinfecting registration equipment at the boarder points - Partners are procuring medicines which UNHCR also has some - Discussed the VHT voucher scheme - Multi-antigen campaigns to kick off | - Uganda red cross planned to train, community awareness and boarder screening |
| RH & HIV – Ronald - HTS meeting was held with IPs (AHA & MTI). Assisted partner notification but challenges were lack of trainings for the identifiers and lack of tools - Had a mission to West Nile with IGAD to revere performance - Much of the IGAD funds have not been used since they were received late - UNFPA set up regional points to do FP,,, | - Should use trained cadres for APN - MoH will share the tools for APN - Kyaka to organise VMMC camps |
| Pharmacy & Medical logistics – Ahmed - Low stocks of tracer medicines across settlements - Finalised technical review for local procurement - Monthly stock status report available - Need to revise essential medicines list - Shared a memo on redistribution of medicines - Medical equipment are non-functional in settlements | - Need to have an inventory management of medical equipment - Should share monthly stock status report by Wednesday 15th together with the HIS reports |
| Health Information – Emmanuel - HIS mission in West Nile (Bidibidi and Palorinya) and lack of tools & poor documentation were major issues. Rolled out VHT reporting tools and followed up with referral database - Had a protection meeting at IAU and there were many non-medical cases residing at the medical hostel. Delays in processing funds was a challenge as well. - Submitted Pepfar reports for Q3 - 6 measles cases in Kyangwali and need follow up This week: - Compile and submit HIS reports and have a discussion on Tuesday Afternoon - Compile and share VHT reports from Bidibidi and Palorinya were the pilot is taking place - Will share the referral database as well - Fact sheet completed by Friday | - Update twine with outbreaks - Share surveillance data - Update the gaps matrix |
| Public health - Isaac - Attended review or IMAM guidelines - FSNA preparation on going - Results for mass nutrition screening has been released for Kyangwali - Commodity reports for RUTF received is needed | - Follow up on JAM - Conduct FSANA in October and share results table by November 2018 - Share results of the Mass nutrition screening in Kyangwali |
| Julius - ANN Burton is coming to the country, advocacy and address challenges. Will visit locations of rift valley fever. - Conference on Wednesday and Thursday at Serena - Training on mental health - Had a mission on Ebola preparedness in SW - An audit on coordination, monitoring and import - Regional public health meeting will be held in Uganda and possibly all will attend | - Prepare mission reports, weekly, monthly reports and minutes of coordination meetings for the audit team and file them – Emmanuel - Ibrahim to attend the mental health training |

Compiled by: Emmanuel Omwony