Chios Education Sector sub-Working

Group Meeting Minutes

TUESDAY, 11 DECEMBER  2018 (9.00-10.00AM) @ METADRASI EDUCATION CENTRE,

MEETING AGENDA

- Review of action points

- Updates from Formal Education

- Updates from Non-Formal Education

- Gaps analysis/needs assessment with reference to current demographics

- AOB

CHIOS, GREECE

| AGENDA ITEM | DISCUSSION POINT | ACTION POINTS |
| --- | --- | --- |
| Review of action points | REC: raise with MoE the possibility to establish an additional DYEP kindergarten (4 shifts per day) by ensuring extra space for Kindergarten students and inform the participants RECs: reiterate with MoE the issue of interpretation for their communication with parents and explore the possibility of provision of interpretation services, though interpreters deployed by MoE RECs: Raise the issue of interpretation with the National ESsWG about the situation in other islands. UNHCR: undertake the translation of the information leaflet on the enrolment procedure ESsWG participants: update their services in the Education Services Mapping within the share drive ESsWG participants: Create during the next ESsWG meeting comprehensive information messages on formal and non-formal education activities currently provided on the island AfE: update IOM on their schedule for children who are enrolled in their program AFE/Imagine Centre: update the children's weekly schedule in the file. Open Arms: update the timetable of their activities in order not to coincide with the DYEP classes and kindergarten and shorten their activities on a single line to harmonize the file. Metadrasi/UNHCR: share the draft messages on education services on the island with the ESsWG participants ESsWG participants: provide inputs/comments/amendments to the messages on education services on the island. | Request raised. Pending update on developments Pending Pending Pending under translation Done Done Done Done Done Done Done |
| Updates from Formal Education | DYEP primary/ gymnasium: No updates |  |
| Updates for Non-Formal Education | 6-22 years old (NFE/VIAL RIC and off-site):) Action for Education presented to the ESsWG their project to under a “students teaching” concept, where students of their schools are trained to teach English to new and younger students being enrolled. Imagine Centre informed the ESsWG participants that a 5-day training on “Social Clowing” will be organized in collaboration with "The medical Clowns" for the participants who are enrolled in the center. | Imagine Centre: share the training schedule to the Participant |
| AOB | The draft messages on Education Services provided on Chios were finalized by all participants during the meeting. The Imagine Centre has requested feedback from their students , in order to ensure it is comprehensible. UNHCR informed the participants about a3-day seminar for teachers to take place on 14-16 December on Chios. The seminar is organized by UNHCR Greece in the framework of an awareness raising project on refugees and human rights, and in collaboration with Hellenic Theatre/Drama, Education Network (TENet) and local Education Directorates. All participants agreed that the next Education Working Group will take place on 8 January 2019 at 9:00 in the Education Center of METAdrasi. | Imagine Centre: give feedback until December 14 for the messages on Education Services on Chios UNHCR/Metadrasi: share with the ESsWG Participants the agenda of the seminar. |

# PARTICIPANT LIST

| ORGANIZATION | NAME | E-MAIL |
| --- | --- | --- |
| METAdrasi | Liberta Pola | liberta.pola.metadrasi@gmail.com |
| UNHCR | Natalie Kapsoti | kapsoti@unhcr.org |
| Action for Education | Ayla Estreich | ayla@actionforeducation.co.uk |
| Action for Education | Lutz Sedelmayr | Lutzsedelmayr93@gmail.com |
| METAdrasi | Riskaki Eirianna | eiriannariskaki.metadrasi@gmail.com |
| RIS | Papdogiannaki Aikaterini | a.papadogiannaki@firstreception.gov.gr |
| Imagine | Tamar Dressler | tamardressler@gmail.com |
| Imagine | Ioannis Psichias | ipsichias@gmail.com |

NEXT MEETING:

TUESDAY, 8 JANUARY 2019 (9.00-10.00AM) @ THE EDUCATION CENTER OUTSIDE VIAL- CHIOS. CHIOS, GREECE