## Summary (CHANGE)
FOOD SECURITY SECTOR | Version 1.0
Lead Ministry | MoA
Coordinating Agency | WFP And FAO
Contact Information | Ms. Majida Mcheik Mmcheik@agriculture.gov.lb & Ms. Amal Salibi asalibi@agriculture.gov.lb, Apollo Arara: Apollo.Arara@fao.org;
Budget |  | 2017 | 2018 | 2019 | 2020
| Food Security Sector: Total budget (USD) | 507167007 | 507625200 | 508625200 | 508625200
| % Humanitarian | 68.726 | 63.16% | 63% | 63%
| % Stabilization | 26.5122 | 37.18% | 37% | 37%
In Need (persons) |  | Targeted 2017 | Target 2018 | Indicative Traget 2019 | Indicative Target 2020
All Population | 2079800 | 961388 | 920821 | 1017821 | 1017821
Persons Displaced from Syria | 1371000 | 837207 | 795177 | 795177 | 795177
Vulnerable Lebanese | 500000 | 92679 | 91644 | 91644 | 91644
PRS | 28800 | 28800 | 28800 | 14000 | 14000
PRL | 180000 | 0 | n/a | 117000 | 117000
Institutions (List them) |  | 5 | 5 | 5 | 5
Outcome | Output | 2017 |  |  | 2018 |  |  | 2019 |  |  | 2020
|  | Budget | % Humanitarian | % Stabilization | Budget | % Humanitarian | % Stabilization | Budget | % Humanitarian | % Stabilization | Budget | % Humanitarian | % Stabilization
Outcome 1: Improve FOOD AVAILABILITY through in kind food assistance and sustainable food value chain (69,707,232) | [7 empty] | 69707232 |  |  | 69707232
Output 1.1 In-kind food assistance for the most vulnerable provided to targeted vulnerable individuals monthly. |  | 28240367 | 78% | 22% | 21471232 | 76% | 32% | 21471232 | 76% | 32% | 21471232 | 76% | 32%
Output 1.2 Training and/or inputs support provided to promote sustainable agriculture, livestock production activities and water-use conservation measures. |  | 36800000 | 0% | 100% | 32517000 | 0% | 100% | 32517000 | 0% | 100% | 32517000 | 0% | 100%
Output 1.3 Technical support provided to the small scale/family farmers to enable them increase links to markets for farm produce. |  | 6700000 | 0% | 100% | 6504000 | 0% | 100% | 6504000 | 0% | 100% | 6504000 | 0% | 100%
Output 1.4 Technical support/advice provided to HHs in order to reduce food wastage and losses along the food production chain - from producers to consumers. |  | 750000 | 0% | 100% | 1085000 | 0% | 100% | 1085000 | 0% | 100% | 1085000 | 0% | 100%
Output 1.5 Prevention and control measures (DDR) for transboundary animal and plant diseases supported in order to prevent and control outbreaks. |  | 2500000 | 0% | 100% | 8130000 | 0% | 100% | 8130000 | 0% | 100% | 8130000 | 0% | 100%
Outcome 2: Improve FOOD ACCESS through cash based food assistance and agricultural livelihoods (411,837,968) | [7 empty] | 411837968 |  |  | 411837968
Output 2.1 Direct access to food improved for vulnerable populations using cash-based food assistance modality. |  | 344976640 | 93% | 7% | 324931968 | 93% | 7% | 324931968 | 93% | 7% | 324931968 | 93% | 7%
Output 2.2 Local agricultural groups/ associations/farmer field schools/cooperatives or groups provided financial, technical, and/or materials to support agricultural livelihoods and the capacity of the institutions. |  | 18350000 | 0% | 100% | 15000000 | 0% | 100% | 15000000 | 0% | 100% | 15000000 | 0% | 100%
Output 2.3 The Small scale farmers supported with financial grants/inputs and /or technical support to promote private agriculture investment. |  | 23600000 | 0% | 100% | 13550000 | 0% | 100% | 13550000 | 0% | 100% | 13550000 | 0% | 100%
Output 2.4 Youth aged 15-25 years provided agricultural technical training in agricultural schools; agricultural vocational skills training (interneship, on job training /apprenticeship and literacy and numeracy skills training (non-and agriculture related skills) to enhance employability in the labor market. |  | 29850000 | 0% | 100% | 15000000 | 0% | 100% | 15000000 | 0% | 100% | 15000000 | 0% | 100%
Output 2.5 Agricultural productive infrastructure and Communal assets rehabilitated/built (agricultural roads, irrigation networks, forests, hill lakes, water reservoirs…) and access to labour market for seasonal and casual labour in agriculture enhanced during 2019 period. |  |  | 0% | 100% | 43356000 | 0% | 100% | 43356000 | 0% | 100% | 43356000 | 0% | 100%
Outcome 3: Improve FOOD UTILIZATION: food safety and nutrition practices are improved through the promotion of consumption of diversified and quality food (18,300,000) | [7 empty] | 18130000 |  |  | 18130000
Output 3.1 Optimal nutritional practices improved amongst the targeted populations. |  | 6100000 | 0% | 100% | 10000000 | 10% | 90% | 10000000 | 10% | 90% | 10000000 | 10% | 90%
Output3.2 Training on good practices in food safety and quality provided /promoted to ensure proper nutritional and food utilization practices. |  | 1800000 | 0% | 100% | 8130000 | 0% | 100% | 8130000 | 0% | 100% | 8130000 | 0% | 100%
OUTCOME 4 (REVISED): Promote food security while enhancing access and application of climate - smart practices, promoting resilience of livelihoods and conservation of natural resources and effectively in coordinating with other actors in FSS as well as other sectors, ETWG and MoA departments during 2019 period (7,950,000) | [7 empty] | 8950000 |  |  | 8950000
Output 4.1: Output 4.1 FSS actors/partners supported report data in the Activity info/3Ws monthly, accessing information and sharing assessment results effectively as a team. |  | 1800000 | 0% | 100% | 2250000 | 50% | 50% | 2250000 | 50% | 50% | 2250000 | 50% | 50%
Output 4.2. A: National institutions and actors, community groups, agricultural cooperatives, extension services staff trained in management of soil resources, pest management and efficient use of water resources. |  | 5700000 | 100% | 100% | 5700000 | 0% | 100% | 6700000 | 0% | 100% | 6700000 | 0% | 100%

## FS LOGFRAME
FOOD SECURITY SECTOR LOGFRAME - 2017-2020 - (Revised for 2019)
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results
Outcome 1: Improve FOOD AVAILABILITY using in-kind food assistance modality and sustainable food production value chain during 2019 period. | A | % of targeted HH with borderline or acceptable food consumption score based on the food groups consumed over a recall period of 7 days. | % (HH) | The Food Consumption Score (FCS) is a composite indicator that considers diet diversity, frequency of consumption and nutrient value of the food groups consumed over a recall period of seven days. According to this score, households are classified into three categories: poor, borderline and acceptable food consumption. The UN, NGOs and NGOs will collaborate for collecting and analyzing data during 2019 period. | FSOM | Yearly | SYR | A:49% B: 33% | A;70% B: 25% | A:62 B:24% | A;70% B: 25% | A:66% | A;70% B: 25% |  | A;70% B: 25%
[7 empty] | PRS | A: 59% B: 29% | A; 65% B: 20% |  | A; 65% B: 20% |  | A; 65% B: 20% |  | A; 65% B: 20%
PRL
[7 empty] | LEB | A: 63% B : 25% | A: 90% B: 10% |  | A: 90% B: 10% |  | A: 90% B: 10% |  | A: 90% B: 10%
| B | % of farmers increased production, access to market, reduce produce waste and losses, and those benefitting as a result of Trans-boundary animal and plant disease control and prevention. | % F | Estimation of the level of production and the application of sustainable farming practices. In order to inform the level of food availability and the adoption/practices of the good farming practices: under ouput 1.2, output 1.3,output 1.4 and output 1.5# of assisted farmers . (UN, INGOs, NGOs, MOA- responsible for collecting data) | AI | Quarterly | SYR
PRS
PRL
[7 empty] | LEB | 2379 | 21000 |  | 21000 |  | 21000 |  | 21000
| C | % of main staples/cereals available for food after calculating the amounts for industrial use and exports. | % CBS | The food availability is based on production and supply chains for the main staples. The UN, NNGOs, INGOs will collaborate with the MoA and Mo Trade to collect data; calculate the actual amount of food currently available (Cereal Balance Sheet (CBS)from the total quantity of foodstuffs produced, total amount imported and current stock within a particular period (UN, INGOs, NNGOs - responsible for collecting data) | National or Regional Cereal Balance Sheet / Food Balance Sheet | Quarterly | LEB
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results | Budget | year 2017 | 2018 | 2019 | 2020
Output 1.1 In-kind food assistance for the most vulnerable provided to targeted vulnerable individuals monthly. | A | # of individuals receiving in-kind food assistance disaggregated by gender - female & male and by cohorts. | individuals | The calculation is based on the amount of food sufficient to meet the food needs. The UN, NNGOs, INGOs will collect data to report the quantity of In-kind food assistance distributed in monthly narrative report (ex: food parcels, food kits, ready-to-eat foods, hot meals) while the number of individuals receiving food is reported in the Activity Info. The UN agencies, INGOs and NNGOs (IPs) monitor the actual receipts of each type of In-kind assistance separately during Post Distribution Monitoring (PDM). | partners' reports, Activity Info | yearly | TOTAL | 107105 | 51000 | 112685 | 52966 | 48586 | 67229.2 | 0 | 52966 | 0 | Output Budget (USD) | 28240367 | 21471232 | 21471232 | 21471232
[7 empty] | SYR | 99526 | 40000 | 104744 | 40000 | 36465 | 40000 |  | 40000 |  | % Humanitarian | 0.78 | 0.76 | 0.76 | 0.76
[7 empty] | PRS |  |  | 232 |  | 43 | 2563.2 |  | 0 |  | % Stabilization | 22% | 0.32 | 0.32 | 0.32
[7 empty] | PRL |  |  | 5171 |  | 163 | 11700 |  | 0
[7 empty] | LEB | 7579 | 11000 | 2538 | 12966 | 11915 | 12966 |  | 12966
List Activities under this output 1.1
Activity 1: Provision of food parcels (including food kits, ready-to-eat foods, hot meals, school feeding)
Activity 2: Create and support community kitchen
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results | Budget | year 2017 | 2018 | 2019 | 2020
Output 1.2 Training and/or inputs support provided to promote sustainable agriculture, livestock production activities and water-use conservation measures. | A | # of farmers receiving support (training and/or inputs) to improve farming practices and production disaggregated by gender - female & males and by cohorts. | individuals | The records of trainings and participants/farmers kept and reported in Activity info by INGOs NNGOs, MoA. The records include the amounts of inputs/materials reported in the Narrative report (ex: seeds, livestock, equipment, inputs, machinery…) also practices on sustainable agricultural, livestock and fisheries, energy and water efficient technologies (ex: solar pumps, drip irrigation…) provided. | partners' reports, Activity Info | yearly | TOTAL | 4260 | 21677.75 | 2305 | 21678 | 702 | 21678 | 0 | 21678 | 0 | Output Budget (USD) | 36800000 | 32517000 | 32517000 | 32517000
[7 empty] | SYR | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | % Humanitarian | 0 | 0 | 0 | 0
[7 empty] | PRS | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | % Stabilization | 100% | 1 | 1 | 1
[7 empty] | PRL | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[7 empty] | LEB | 4260 | 21677.75 | 2305 | 21678 | 702 | 21678 |  | 21678
List Activities under this output 1.2
Activity 1: Promoting sustainable agricultural production (fruit, vegetable, crop)
Activity 2: Promoting sustainable livestock production (ex.: dairy, poultry production, fisheries...)
Activity 3: Promoting water use efficiency and conservation (ex.: efficient irrigation practices)
Activity 4: Promote sustainable agriculture and energy saving farming practices (Tolerant cultivars, organic farming, conservation agriculture, mixed farming, crop rotation, unproductive
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results | Budget | year 2017 | 2018 | 2019 | 2020
Output 1.3 Technical support provided to the small scale/family farmers to enable them increase links to markets for farm produce. | A | # of small scale/family farmers supported to access market disaggregated by gender (female and males) and by cohorts. | individuals | The number of farmers participating is recorded and reported by NGOs and INGOs (IPs) who also monitor progress on access to market to report in the Narrative report. The number of those accessing markets is reported in the Activity info. | partners' reports, Activity Info | Yearly | TOTAL | 0 | 5420 | 250 | 5420 | 350 | 5420 |  | 5420 |  | Output Budget (USD) | 6700000 | 6504000 | 6504000 | 6504000
[7 empty] | SYR | 0 | 0 |  | 0 | 0 | 0 |  |  |  | % Humanitarian | 0 | 0 | 0 | 0
[7 empty] | PRS | 0 | 0 |  | 0 | 0 | 0 |  |  |  | % Stabilization | 100% | 1 | 1 | 1
[7 empty] | PRL | 0 | 0 |  | 0 | 0 | 0
[7 empty] | LEB | 0 | 5419.5 | 250 | 5420 | 350 | 5420 |  | 5420
List Activities under this output 1.3
Activity 1: Promotion of food transformation and preservation practices including, production, cooking and storage/servicing etc. .
Activity 2: Create and reinforce linkages between small scale producers and local markets (ex: community kitchens, WFP shops, rehabilitation of roads and markets infrastructure).
Activity 3: Distribution of unsold/unmarketed quality food from producer/retail to local markets
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results | Budget | year 2017 | 2018 | 2019 | 2020
Output 1.4 Technical support/advice provided to HHs in order to reduce food wastage and losses along the food production chain - from producers to consumers. | A | # of households/farmers (disaggregated by gender-female &male) receiving technical support to reduce food wastage and losses (transformation technologies for food preservation. | HH | The NNGOs & INGOs (Is) responsible for recording and reporting the number of farmers/participants (disaggregated by gender - female & male), supported to reduce losses and wastage of food produced. The information from field observations is reported in Narrative by the IPs and uploaded in the Dashboard by IMO by 2019 | partners' reports, Activity Info | Yearly | TOTAL | 0 | 5419.5 | 916 | 1084 | 150 | 1084 | 0 | 0 | 0 | Output Budget (USD) | 750000 | 1085000 | 1085000 | 1085000
[7 empty] | SYR |  |  | 0 | [6 empty] | % Humanitarian | 0 | 0 | 0 | 0
[7 empty] | PRS |  |  | 0 | [6 empty] | % Stabilization | 100% | 1 | 1 | 1
[7 empty] | PRL |  |  | 0
[7 empty] | LEB | 0 | 5419.5 | 0 | 1084 |  | 1084
List Activities under this output 1.4
Activity 1: Provide training to improving post harvest management.
Activity 2: Provision of improved storage (silo, grain bags, cold storage etc)
Activity 3: Valorization of organic waste and least valued products (ex: through processing for animal nutrition; composting, awareness…)
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results | Budget | year 2017 | 2018 | 2019 | 2020
Output 1.5 Prevention and control measures (DDR) for transboundary animal and plant diseases supported in order to prevent and control outbreaks. | A | # of farmers benefitting from prevention and control measures (DDR) of trans-boundary animal and plant diseases disaggregated by gender- female & male and by cohorts. | individuals | The INGOs & NNGOs (Ips) responsible for mapping the population in the areas covered by the Trans-boundary animal and plant diseases activities to estimate the number of people/ farmers benefitting or covered and to report during 2019 period. | partners' reports, Activity Info | adhoc | TOTAL | 2170 | 0 | 408 | 5420 | 69 | 5420 | 0 | 0 | 0 | Output Budget (USD) | 2500000 | 8130000 | 8130000 | 8130000
[7 empty] | SYR | [9 empty] | % Humanitarian | 0 | 0 | 0 | 0
[7 empty] | PRS | [9 empty] | % Stabilization | 100% | 100% | 100% | 100%
PRL
[7 empty] | LEB | 2170 |  |  | 5420 |  | 5420
List Activities under this output 1.5
Activity 1: Supporting the monitoring and early warning systems for plant and animal diseases
Activity 2: Supporting emergency interventions to control the spread of transboundary diseases
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results
Outcome 2: Improve FOOD ACCESS using cash -based food assistance modality and sustainable agricultural livelihoods during 2019 period. | A | % of targeted HH with borderline or acceptable food consumption score disaggregated by gender - female &male and by cohorts. | % (HH) | The UN agencies and NNGOs and INGOs (IPs) collect data to assess the level of food accessibility. The Food Consumption Score (FCS) is a composite indicator that considers diet diversity, frequency of consumption and nutrient value of the food groups consumed over a recall period of seven days. According to this score, households are classified into three categories: poor, borderline and acceptable food consumption during 2019 period. | FSOM | Yearly | SYR | A:49% B: 33% | A;70% B: 25% | A:62 B:24% | A;70% B: 25% | A:66% B:% | A;70% B: 25% |  | A;70% B: 25%
[7 empty] | PRS | A: 59% B: 29% | A; 65% B: 20% |  | A; 65% B: 20% |  | A; 65% B: 20% |  | A; 65% B: 20%
PRL
[7 empty] | LEB | A: 63% B : 25% | A: 90% B: 10% |  | A: 90% B: 10% |  | A: 90% B: 10% |  | A: 90% B: 10%
| B | % of HHS with increased agricultural livelihoods disaggregated by gender - (female & male) and by cohorts. | %hh | The UN agencies, NNGOs and INGOs (IPs) calculates the proportion of the HHs with improved livelihood opportunities as resulting from activities 2.2 2.3 2.4 2.5. It also involves assessing the perception of the households/farmers targeted to understand changes in their livelihoods during 2019. | partners' reporting | Yearly | TOTAL | 855 | 0 | 0 | 1084.6 | 0 | 1084.6 | 0 | 1085 | 0
SYR
PRS
PRL
[7 empty] | LEB | 855 |  |  | 1084.6 |  | 1084.6 |  | 1085
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results | Budget | year 2017 | 2018 | 2019 | 2020
Output 2.1 Direct access to food improved for vulnerable populations using cash-based food assistance modality. | A | # of individuals receiving cash based food assistance disaggregated by gender - (female & male) by cohort. | individuals | The UN agencies, INGOs and NNGOs reconcile disbursement records (ex.: e-cards, ATM, food vouchers). The receipt of each type of Cash reported in the Activity info and the qualitative data is reported in the partners' Narrative reports ( Post Distribution Monitoring -PDM). | partners' reports, Activity Info | yearly | TOTAL | 779078 | 888710 | 769226 | 846177 | 750560 | 846177 | 0 | 0 | 0 | Output Budget (USD) | 344976640 | 324931968 | 324931968 | 324931968
[7 empty] | SYR | 683052 | 797207 | 681903 | 755177 | 663430 | 755177 |  |  |  | % Humanitarian | 0.93 | 0.93 | 0.93 | 0.93
[7 empty] | PRS | 42534 | 31502 | 34531 | 34000 | 34475 | 34000 |  |  |  | % Stabilization | 7% | 0.07 | 0.07 | 0.07
[7 empty] | PRL | 493 |  | 369 |  | 383
[7 empty] | LEB | 52999 | 60001 | 52423 | 57000 | 52272 | 57000
List Activities under this output 2.1
Activity 1: Cash based transfer for food (ex.: e-cards, ATM, food vouchers).
Activity 2: Post Distribution Monitoring (PDM) on Cash based transfer for food (ex.: e-cards, ATM, food vouchers). | [8 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results | Budget | year 2017 | 2018 | 2019 | 2020
Output 2.2 Local agricultural groups/ associations/farmer field schools/cooperatives or groups provided financial, technical, and/or materials to support agricultural livelihoods and the capacity of the institutions. | A | # of local agricultural groups/ associations/ cooperatives and teachers who received financial, technical and/ or material to support agricultural livelihoods disaggregated by governorate. | associations | The UN agencies, INGOs, NNGos and MoA will estimate the amounts of inputs / equipment, materials, financial value and report /show the extent how support to the Associations impacts on agricultural livelihoods in the Narrative report; while the number of trainings and participants to report. | partners' reports, Activity Info | quarterly | INSTIT/groups | 0 | 50 | 17 | 100 | 4 | 100 |  |  |  | Output Budget (USD) | 18350000 | 15000000 | 15000000 | 15000000
[7 empty] | Teachers | [9 empty] | % Humanitarian | 0 | 0 | 0 | 0
[17 empty] | % Stabilization | 100% | 100% | 100% | 100%
List Activities under this output 2.2
Activity 1: Provide farmers associations and/or cooperatives financial, technical and/ or material support for agricultural livelihoods.
Activity 2: Provide financial and technical support to governmental institutions (ex.: MoA offices, centers, schools…)
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results | Budget | year 2017 | 2018 | 2019 | 2020
Output 2.3 The Small scale farmers supported with financial grants/inputs and /or technical support to promote private agriculture investment. | A | # of Small scale farmers who received agricultural inputs in-kind, cash grants/credit and/or technical support disaggregated by gender - females & males and by cohort. | individuals (male and female) | The UN, INGOs and NNGOs reports the actual number of farmers provided inputs against the plan on inputs either in-kind, credit or cash to report in the Activity Info. In the Narrative report to show the progress and impacts on farmers' agricultural livelihoods private investment. | partners' reports, Activity Info | monthly | TOTAL | 0 |  |  |  | 911 |  |  |  |  | Output Budget (USD) | 23600000 | 13550000 | 13550000 | 13550000
[7 empty] | SYR | [9 empty] | % Humanitarian | 0 | 0 | 0 | 0
[7 empty] | PRS | [9 empty] | % Stabilization | 100% | 100% | 100% | 100%
PRL
[7 empty] | LEB | 0 | 5419.5 |  | 5420 |  | 5420
List Activities under this output 2.3
Activity 1: Provision of agriculture inputs (seeds/seedlings, livestock, equipment,…)
Activity 2: provision of Financial and technical support to agriculture private sector investment (ex.: access and utilize unproductive land, terracing, irrigation/water management…)
Activity 3: Raise awareness to promote innovative credit/loan investment schemes for Lebanese farmers
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results | Budget | year 2017 | 2018 | 2019 | 2020
Output 2.4 Youth aged 15-25 years provided agricultural technical training in agricultural schools; agricultural vocational skills training (interneship, on job training /apprenticeship and literacy and numeracy skills training (non-and agriculture related skills) to enhance employability in the labor market. | A | # of youth aged 15-25 years enrolled to enhance employability skills agricultural labour market from any of these: enrolment in agricultural schools, agriculture skills training (internship and on the job training, apprenticeship) or basic numeracy and literacy trainings - disaggregated by gender female and male and by cohort. | Individuals | The UN, INGOs and NNGOs will record the number of individuals/ participants (#youth aged 15 to 25 years) who enrolled, trained and completed the training/course (in basic literacy and numeracy in agriculture related fields). | partners' reports, Activity Info | Yearly | TOTAL | 627 | 1150 | 4669 | 2000 | 1775 | 2000 | 0 | 0 | 0 | Output Budget (USD) | 29850000 | 15000000 | 15000000 | 15000000
[7 empty] | SYR |  | 460 | 2546 | 1000 | 765 | 1000 |  |  |  | % Humanitarian | 0 | 0 | 0 | 0
[7 empty] | PRS | [9 empty] | % Stabilization | 100% | 100% | 100% | 100%
[7 empty] | PRL |  |  | 197 |  | 9
[7 empty] | LEB | 627 | 690 | 1926 | 1000 | 1001 | 1000
List Activities under this output 2.4
Activity 1: Enrolment of the youth aged 15-25 years (adolescent and youth in agriculture schools, agriculture skills training, or basic literacy and numeracy.
Activity 2: Conduct TVET training/courses for the (youth aged 15-25 years) on agriculture skills or related basic numeracy and literacy skills.
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results | Budget | year 2017 | 2018 | 2019 | 2020
Output 2.5 Agricultural productive infrastructure and Communal assets rehabilitated/built (agricultural roads, irrigation networks, forests, hill lakes, water reservoirs…) and access to labour market for seasonal and casual labour in agriculture enhanced during 2019 period. | A | # of farmers benefiting from the rehabilitated agricultural infrastructure and/or communal assets disaggregated by gender (female &male) and by cohort. | Individuals | The UN, INGOs and NNGOs estimate the number of farmers benefitting from agricultural productive infrastructure and communal assets (ex: agricultural roads, irrigation networks, forests, hill lakes, water reservoirs …) rehabilitated or newly established. |  |  | TOTAL | 2541 | 21677.75 |  | 21677.75 | 14071 | 21677.75 | 0 | 21678 | 0 | Output Budget (USD) | 29850000 | 43356000 | 43356000 | 43356000
[7 empty] | SYR |  |  |  |  | 3368 |  |  |  |  | % Humanitarian | 0 | 0 | 0 | 0
[7 empty] | PRS |  |  |  |  | n/a |  |  |  |  | % Stabilization | 100% | 100% | 100% | 100%
[7 empty] | PRL |  |  |  |  | n/a
[7 empty] | LEB | 2541 | 21677.75 |  | 21677.75 | 10703 | 21677.75
| C | # of agricultural productive infrastructure and communal assets rehabilitated/built up during the 2019 period. | # | The estimates of the numbers is done by IPs using the relevant units/measures of the agricultural productive structures/assets rehabilitated or built to support farmers' agricultural livelihoods during 2019. | partners' reports, Activity Info | yearly | INSTIT |  |  |  | 30 | 331
| D | # of targeted individuals (#youth aged 15 to 25 years) employed to provide seasonal labour in agriculture sector - disaggregated by gender (female &male) and by cohort. | individuals (male and female) | The record of number of individuals (#youth aged 15 to 25 years) involved in seasonal agricultural labor/casual labor is reported by the IPs basing the calculations of the actual numbers on the Work-days standards. | partners' reports, Activity Info | monthly | TOTAL | 20000 | 0 | 18368 | 21678 | 2071 | 21678 | 0 | 0 | 0
[7 empty] | SYR | 9000 |  |  | 10000 | 1536 | 10000
PRS
PRL
[7 empty] | LEB | 11000 |  |  | 11678 | 535 | 11678
List Activities under this output 2.5
Activity 1: Rehabilitation and/or creation of agricultural productive infrastructure and communal assets
Activity 2: Support the most vulnerable individuals to access agricultural seasonal labor.
Activity 3: Support access of most vulnerable individuals to agricultural casual labor
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results
Outcome 3: Improve FOOD UTILIZATION: The target population improve food safety, quality and dietary diversity during 2019 period. | A | % of women with a minimum dietary diversity score based on the Household Diet Diversity Scale (HDDS) by cohort | % female. | The UN agencies INGOs and NNGOs will be responsible in collecting data on and analysis done centrally once a year. The dietary diversity is a qualitative measure of the level of food consumption. It reflects the level of access to a variety of foods, and is also a proxy for nutrient adequacy of the diet of individuals or households. The Household Dietary Diversity Scale (HDDS) is based on 5 out of 10 food groups to calculate the proportion of women or individuals with adequate dietary diversity during 2019 period. | PDM | Yearly | SYR | n/a | 90% |  | 90% |  | 90% |  | 90%
PRS
PRL
[7 empty] | LEB |  | 90% |  | 90% |  | 90% |  | 90%
| B | % of beneficiaries supported who improved their food safety, quality and dietary diversity practices. (female &males) and by cohort. | individuals (male /female) | The aim is to evaluate the adoption levels of beneficiaries on improved food safety and quality measures. The IPs will conduct a sample survey to evaluate the level of the practices involving the entire food chain- production, storage, preparation/cooking including hygiene etc.: as resulting from output 3.1 and 3.2 | partners' reports, Activity Info | Yearly | TOTAL | 0 | 0 | 0 | 5420 | 0 | 5420 | 0 | 0 | 0
SYR
PRS
PRL
[7 empty] | LEB |  |  |  | 5420 |  | 5420
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results | Budget | year 2017 | 2018 | 2019 | 2020
Output 3.1 Optimal nutritional practices improved amongst the targeted populations. | A | # of individuals supported improved their nutritional activities and practices - disaggregated by gender - (female & male) and by cohort. | individuals | The UN agencies, INGOs and NNGOs IPs calculate the number of beneficiaries reached for promoting nutritional practices using different methods and activities i.e. through schools, backyard and roof/micro gardens etc. | partners' reports, Activity Info | # supported monthly & | TOTAL | 0 | 35000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | Output Budget (USD) | 6100000 | 10000000 | 10000000 | 10000000
[7 empty] | SYR |  | 26250 |  | 5000 |  | 5000 |  |  |  | % Humanitarian | 0 | 0.1 | 0.1 | 0.1
[7 empty] | PRS | [9 empty] | % Stabilization | 100% | 0.9 | 0.9 | 0.9
PRL
[7 empty] | LEB |  | 8750 |  | 5000 |  | 5000 |  | 5000
List Activities under this output 3.1
Activity 1: Promoting optimal nutrition related behaviours and practices amongst the targeted vulnerable groups
Activity 2: Improving food diversity for vulnerable households through the promotion of small scale production of diversified nutritious food for vulnerable households through schools, backyard and roof/micro gardens
Activity 3: Promote food preservation/ transformation technologies at household and community level
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results | Budget | year 2017 | 2018 | 2019 | 2020
Output3.2 Training on good practices in food safety and quality provided /promoted to ensure proper nutritional and food utilization practices. | A | # of individuals trained demonstrate knowledge and practice on food safety and quality measures disaggregated by gender - female & male and by cohort. | individuals | The UN agencies, INGOs and NNGOs analyze the level of knowledge and practices on nutrition for male/female individuals trained on food safety and quality measures including farmers, staff and consumers where applicable. | partners' reports, Activity Info | monthly | TOTAL | 0 | 10000 | 7079 | 10000 | 2240 | 10000 |  | 10000 |  | Output Budget (USD) |  | 8130000 | 8130000 | 8130000
[7 empty] | SYR |  | 5000 | 4138 | 5000 | 1368 | 5000 |  | 5000 |  | % Humanitarian | 0 | 0 | 0 | 0
[7 empty] | PRS | [9 empty] | % Stabilization | 100% | 100% | 100% | 100%
PRL
[7 empty] | LEB |  | 8750 | 2941 | 5000 | 823 | 5000 |  | 5000
| B | # and types of initiatives in place to improve to ensure good practices, local production, safety and quality of high value nutritious food (female &males)and by cohort. | Initiatives | These include the number and types of initiatives effectively implemented by the IPs to support the local production of high value nutritious foods, such as activities for behaviour change, use of micro gardens, food systems i.e. processing, preservation and transformation technologies. | partners' reports, Activity Info |  | INSTIT |  |  |  | 5 |  | 5 |  | 5
List Activities under this output 3.2
Activity 1: Assisting the Government in improving the food inspection and safety measures, including irrigation practices (i.e.: quality/source of water)
Activity 2: Promoting Integrated Pest Management and Good Agriculture Practices and Standards (i.e. pesticide use)
Activity 3: Support the inherent food systems/value chains - production, processing, storage, preparation /cooking /serving to ensure food safety and quality.
Activity 4: Promote policies supporting the local production of high value nutritious autogenous foods.
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results
Outcome 4: OUTCOME 4 (REVISED): Promote food security while enhancing access and application of climate - smart practices, promoting resilience of livelihoods and conservation of natural resources and effectively in coordinating with other actors in FSS as well as other sectors, ETWG and MoA departments during 2019 period. | A | % of farmers applying climate - smart practices, measures for conserving natural resources in collaboration with other relevant actors.(Lebanese female &male) | % | The UN agencies, INGOs abd NNGOs analyze the extent to which the target farmers apply good practices /measures to control and conserve the environmental resources in ensuring sustainable production and future resilience during 2019 period. | Sample survey | Yearly | Total | 72% | 80% |  | 100% |  | 100%
| B | % of partners /actors in FSS reporting in Activity info/3Ws monthly and satisfactorily sharing information/assessment results with others - by governorate. | % organizations | The FSS coordinator and IMO will develop on-line survey questionnaire sent to partners with a link. The IMO calculates the proportion FSS partners/ actors reporting in Activity info/3Ws monthly. The sector partners will conduct self -evaluation to establish the extent of the collaboration and effectiveness in sharing and accessing information in the sector. | On-line survey | Yearly | Total
partners
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results | Budget | year 2017 | 2018 | 2019 | 2020
Output 4.1 FSS actors/partners supported report data in the Activity info/3Ws monthly, accessing information and sharing assessment results effectively as a team. | A | # of FSS actors/partners reporting in Activity info/3Ws monthly, accessing information for planning, sharing assessment results and are satisfied with the coordination support. | assessments, organizations. | The UN agencies, INGOs and NNGOs will participate in FSS activities. The FFS coordinator and IMO will analyze the number of FSS actors/partners reporting in the Activity info/3Ws monthly; while the analysis of the proportion of those accessing information and sharing assessment results and their views on the effectiveness of the FSS coordination analyzed annually. | partners' reports, Activity Info; online survey with a link to access the page. | quarterly | Total | 32 | 32 |  | 32 | 23 | 32 |  | 32 |  | Output Budget (USD) | 1800000 | 2250000 | 2250000 | 2250000
[7 empty] | partners | [9 empty] | % Humanitarian | 0% | 0.5 | 0.5 | 0.5
[7 empty] | Total |  |  |  | 100% |  | 100% |  | 100% |  | % Stabilization | 1 | 0.5 | 0.5 | 0.5
Satisfaction
List Activities under this output 4.1
Activity 1: Conduct Pre & Post -assistance FS vulnerability and capacity assessments, as well monitoring of the progress - PDM.
Activity 2: FSS Actors report data in the Activity info monthly/ Mapping 3 Ws and sharing assessment results to learn lessons.
[9 empty] | 2017 |  | 2018 |  | 2019 |  | 2020
Result | ID | Indicators | Unit | Description/ definition | MoV / Responsible | Frequency | Beneficiary | Baseline | Target | Results | Target | Results | Target | Results | Target | Results | Budget | year 2017 | 2018 | 2019 | 2020
Output 4.2 National institutions and actors, community groups, agricultural cooperatives, extension services staff trained in relevant areas. in management of soil resources, pest management and efficient use of water resources. | A | # of the National institutions involved in food security supported to develop capacities in i.e. safety nets programs, vulnerability analysis, capacity assessment, disaster risk management (DRM) -ex.: Contingency planning. | institutions | The UN agencies, INGOs and NNGOs involved will report number and capacities/needs of the different institutions, groups, cooperatives, and/ or departments to support i.e. in developing Social safety net policy and programs, vulnerability analysis, capacity assessment, developing MoA (centers/offices/schools) MoSA/NPTP and SDCs staff. Including contingency planning -DRM Unit. Support to GoL, MoA, MoET updating national policies/strategies/action plans in relation to food security. Involvement of Private sector in food security related activities. | partners' reports, Activity Info | monthly | Total | 0 | 5 | 56 | 5 | 7 | 5 |  | 5 |  | Output Budget (USD) | 5700000 | 5700000 | 6700000 | 6700000
[7 empty] | Institutions |  | 5 | 56 | 5 | 7 | 5 |  |  |  | % Humanitarian | 0 | 0 | 0 | 0
[17 empty] | % Stabilization | 100% | 100% | 100% | 100%
| B | # of Farmers, community groups and members of agricultural cooperatives trained on the management of soil resources, pest management and efficient use of water resources (female &male) | # Farmers/associations etc. | The UN agencies, INGOs and NNGOs (IPs) will conduct training and in the process keep records of the number of famers, community groups and members of agricultural cooperatives trained on management of soil resources, pest management and efficient use of water resources. | partners' reports, Activity Info | Monthly | Total | [5 empty] | 200 |  | 200
LEB
| C | # of Extension services staff re-freshed providing extension services on agro-climatic information and guidance on improved cropping practices to make agricultural production systems more resilient (female&male). | # staff | The UN agencies, INGOs and NNGOs (IPs) will facilitate re-fresher training for extension staff on agro-climatic information and guidance to improve cropping practices to make agricultural production systems more resilient. Then, they collaborate with the MoA to establish the number of re-fresher extension services staff to provide services in the governorates /area of operation. | partners' reports, Activity Info |  | Total | [5 empty] | 50 |  | 50
LEB
0
List Activities under this output 4.2
Activity 1: Support national institutions to implement food security to address different needs more effectively (i.e. establishing safety net processes and strategies, vulnerability assessments, capacity assessment i.e. MoA centers/offices/schools -including TVET; MoSA/NPTP and SDCs capacities. Including Disaster Risk Management -DRM, -ex.: Contingency planning, DRM Unit. As well as supporting the GoL, MoA, MoET in updating national policies/strategies/action; and ensuring the involvement of the private sector in food security).
Activity 2: Promote consultative meetings with communities and conduct training for farmers, community groups and members of agricultural cooperatives on management of soil resources, pest management and efficient use of water resources
Activity 3: Provide support and training for the Extension services staff to improve capacity in providing extension services on agro-climatic information and guidance on improved cropping practices to make agricultural production systems more resilient.