## Slide 1
Shelter, Settlements + NFI Sector Working Group
SSNFI WG
Meeting
29th January 2019

## Slide 2: Agenda
Introduce the fabulous Sarah Gilbert as the SSNFI WG’s new co-chair.
CERF ANNOUNCEMENT
PRESENTATION: WFP/UNOPS Rural Access Index
Walk through 5W for 2018 achievements + present draft dashboard for Jan – Sept 2018 (Q1 – Q3).
Semi-permanent shelters
2019-2020 REVISED RRP reporting and Activity INFO.
MEB
AOB.
All documents will be shared after meeting + uploaded on portal.

## Slide 3: CERF FUNDING: 18 million USD
Office of Resident Coordinator will decide how the funds will be broken down by sector.
SSNFI WG will need to determine prioritized activities and agencies who will receive the funds.

## Slide 4: 5W MATRIX: FINAL 2018 SUBMISSION
CHANGES:
NFIs - No reporting on “communal HH kits”. Only report on NFI distributions to new arrivals.
Shelter - Must include total number of individual PSNs supported.
What are the challenges with reporting?
Top down or bottom up? Through UNHCR focal points or by Agency Country Director?
Must report on all achievements in 2018 from 1st January until 31st December.

## Slide 5: 2019 – 2020 REFUGEE RESPONSE PLAN
INTER-AGENCY RESPONSIBILITIES:
FEBRUARY 18TH = Deadline for revised targets based on verified refugee population figures + projections of new arrivals.
March 7th + 8th = Vetting partners’ budget and targets.

## Slide 6
South Sudan |  | DRC and others |  | Burundi |  | Total | 
Refugees | Host | Refugees | Host | Refugees | Host | Refugees | Host
# of individuals (refugees + hosts) receiving sustainable shelter construction training |  |  |  |  |  |  |  |  |  |  | 
2018 baseline |  |  |  | 520 | 157 | 500 | 0 | 0 | 0 | 1,020 | 157
Target 2019 |  |  |  | 3,110 | 900 | 1,390 | 450 | 210 | 90 | 4,710 | 1,440
Target 2020 |  |  |  | 2,100 | 900 | 2,570 | 450 | 210 | 90 | 4,880 | 1,440
Needs 2020 |  |  |  |  |  |  |  |  |  | 6,720 | 2,880
# of refugee and host community households with specific needs assisted with semi-permanent shelters |  |  |  |  |  |  |  |  |  |  | 
2018 baseline |  |  |  |  | Not available |  | Not available |  | Not available | - | Not available
Target 2019 |  |  |  | 7,000 | 1,400 | 6,000 | 1,200 | 500 | 100 | 13,500 | 2,700
Target 2020 |  |  |  | 8,000 | 1,600 | 6,000 | 1,200 | 500 | 100 | 14,500 | 2,900
Needs 2020 |  |  |  |  | Not available |  | Not available |  | Not available | - | Not available
# of refugee households who receive cash-based NFI assistance |  |  |  |  |  |  |  |  | 
2018 baseline |  | Not available | Not applicable | Not available | Not applicable | Not available | Not applicable | Not available | Not applicable
Target 2019 |  |  | Not applicable |  | Not applicable |  | Not applicable | - | Not applicable
Target 2020 |  |  | Not applicable |  | Not applicable |  | Not applicable | - | Not applicable
Needs 2020 |  |  | Not applicable |  | Not applicable |  | Not applicable | - | Not applicable
2019-2020 REVISED RRP TARGETS

## Slide 7
South Sudan |  | DRC and others |  | Burundi |  | Total | 
Refugees | Host | Refugees | Host | Refugees | Host | Refugees | Host
2019-2020 REVISED RRP TARGETS
# of kms of roads rehabilitated (including roadside vegetation) for all-year access to community services |  |  |  |  |  |  |  |  |  |  | 
2018 baseline |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target 2019 |  |  |  | 60 | 60 | 50 | 50 | 10 | 10 | 120 | 120
Target 2020 |  |  |  | 60 | 60 | 50 | 50 | 10 | 10 | 120 | 120
Needs 2020 |  |  |  |  |  |  |  |  |  | 240 | 240
# of energy-saving street lights installed in refugee hosting areas (excluding staff institutions) |  |  |  |  |  |  |  |  |  |  | 
2018 baseline |  |  |  | 833 | 12 | 50 | 23 | 7 | 7 | 890 | 42
Target 2019 |  |  |  | 250 | 250 | 150 | 150 | 50 | 50 | 450 | 450
Target 2020 |  |  |  | 250 | 250 | 150 | 150 | 50 | 50 | 450 | 450
Needs 2020 |  |  |  |  |  |  |  |  |  | 900 | 900

## Slide 8: MINIMUM EXPENDITURE BASKET
ONE OFF BLANKET ENTITLEMENT:
1. Emergency Shelter Kit (averaged between treated and non-treated pole options)
- Type I (HH size 1 – 3 ppl) = 481,987 UGX
- Type II (HH size 4 – 7 ppl) = 633,270 UGX
- Type I + II (HH size ≥ 8 ppl) = 1,115,257 UGX
NB: Added 10% to all packages above for transport.
2. Labour for assemblage (only for vulnerable PSN):
(approx. 20% of total cost - not super skilled)
- Type I (HH size 1 – 3 ppl) = 96,397 UGX
- Type II (HH size 4 – 7 ppl) = 126,654 UGX
- Type I + II (HH size ≥ 8 ppl) = 223,051 UGX

## Slide 9: MINIMUM EXPENDITURE BASKET
ONE-OFF ENTITLEMENT TO VULNERABLE PSN HH:
1. Semi-permanent HH shelter materials + transport (approx. 20% of total cost due to construction materials required)
- Type A (1 – 3 ppl) = 1,800,000 UGX
- Type B (4 – 6 ppl) = 2,400,000 UGX
Type C (≥ 8 ppl)* = 2,881,987 UGX
2. Semi-permanent HH shelter labour (approx. 30% of total material cost due to higher skills required)
- Type A (1 – 3 ppl) = 450,000 UGX
- Type B (4 – 6 ppl) = 600,000 UGX
Type C (≥ 8 ppl)* = 744,596 UGX
* this option is Type B + supply of Emergency Shelter Kit Type I

## Slide 10: MINIMUM EXPENDITURE BASKET
REPEAT SHELTER MAINTENANCE/REPAIRS:
Cannot quantify this with the limited insight we currently have on such expenditure trends.
Could the potential Multi-Sector Market Assessment allow us to devise such a tranche for the MEB?
Results from the MEB can help the SSNFI WG to devise a basic repair/maintenance seasonal/annual/biannual top-up value for ongoing shelter maintenance and repairs?

## Slide 11
AOB?
Next Meeting – let’s set a regular date?
Excel sheet for mailing list clean-up.