| Name | TF | Meeting Date | 17 June 2019 |
| --- | --- | --- | --- |
| Meeting Location | UNHCR Zahle Sub-Office | Meeting Time | 15:30 |
| Co-Chairs | Hussein Salem (MoSA) – Josep Zapater (UNHCR) | Meeting Duration | 2:00 hour |
| Minutes Prepared by | Josep Zapater (UNHCR) |  |
| Purpose of Meeting |  |

Meeting

Meeting agenda

Deir el Ahmar situation

- Updates

- Humanitarian situation, gaps and responses necessary

Arsal situation

- Updates – including on advocacy

- Relocation

- Shelter response and capacity

- Rubble removal

- Pilot site dismantling

- Protection issues, including persons with special needs

- Visit of Deputy Representative (Prot.) UNHCR to Arsal on Wednesday

- Winterization

Litani situation

- Updates and next steps

URDA situation

- Updates and next steps

Discussions – Deir el Ahmar situation

UNHCR updated on developments in Deir el Ahmar during the past weeks, as well as current situation at Maqneh relocation site. A call was made on all humanitarian actors to increase capacity as well as availability for emergencies including during weekends – if necessary through adapting internal policies.

As regards the water situation, landlord is providing water for a few days. GVC is checking water quality and also looking at short and mid-term options.

Action points – Deir el Ahmar situation

| Action needed | Focal point | Deadline | Status |
| --- | --- | --- | --- |
| Joint WASH, protection and shelter technical mission, together with MOSA – discussions with landlord, in particular to ensure availability of water | UNHCR, UNICEF, MOSA | 17 June |  |
| Conduct necessary assessments, for sectors not done yet | All sectors not done yet – including CP and Education | Friday 21 June |  |
| Prepare general action plan | UNHCR (Raffaella) | Monday 24 June |  |

Discussions – Solid structures situation

A briefing was given on specific and important issues, in particular as regards deadlines (1st of July has been given by LAF Labwe – at the same time, an action plan has been submitted by UNHCR centrally) and as regards common walls between type 2 and 3 solid structures – which need to be kept for fire prevention purposes, other options being a technical isolation unit (at an estimated cost of 400,000 USD for the 700 – 800 units involved) or expanding settlement area by 50% on average.

Protection briefed on the level of refugee frustration, given lack of relocation capacities as slowness of response. NRC explained that in some cases refugees refer before demolition starts, which is slowing down the process.

LRC is currently erecting 200 tents for the temporary relocation of Al Abrar 04, Qaryat Hayat, Toun, Al Abrar 02 and Aramel sites. Hussein with liaise with LRC to ensure that these tents can also be used for general relocation purposes. 79 families are currently relocating to the site.

Action points – Solid structures situation

| Action needed | Focal point | Deadline | Status |
| --- | --- | --- | --- |
| Relocation procedure – provide comments | All | 18 June |  |
| Finalize relocation procedure | Protection | 18 June |  |
| Joint UNHCR / MOSA mission to Arsal to fomalize relocation options | UNHCR /MOSA | 18 June |  |
| Finalize relocation plan – including with LRC tents | MOSA | 19 June |  |
| Field mission and discussion to plan organized one settlement dismantlement / rebuilding – taking into account PSWN. Particular recommendations (operational and advocacy) will be developed on PWSN | UNHCR and relevant actors | 18 June |  |
| Field mission to assess alternative site for Salam 1 | MOSA | 18 June |  |
| Check stock quality | NRC, Medair, SDC | Ongoing |  |

Briefing – Litani situation

Permeability tests are no longer needed, as per MOE communication. New relocation sites, as well as category of land use, are still needed.

Action points – Litani situation

| Action needed | Focal point | Deadline | Status |
| --- | --- | --- | --- |
| MOSA to continue identifying relocation sites | MOSA | Ongoing |  |
| MOSA to identify category of land use | MOSA | Ongoing |  |

Action points – URDA situation

| Action needed | Focal point | Deadline | Status |
| --- | --- | --- | --- |
| URDA needs to provide necessary coordination between Shelter and WASH. UNHCR to remind URDA | UNHCR | 18 June |  |

Briefing – Furzol situation

MOIM, MOSA and UNHCR held a meeting with the Mayor of Furzol. He clarified that no further evictions will be carried out and that proper coordination would be held with MOSA and MOIM. He requested more coordination from NGOs and UN agencies. Landlords are requested to communicate with Municipality about the refugees hosted in their land.

Action points – Furzol situation

| Action needed | Focal point | Deadline | Status |
| --- | --- | --- | --- |
| Protection to share family data with Shelter and Wash, for rebuilding of tents, with copy to MOIM | Protection | 18 June |  |

Action points – shelter dismantlement in the rest of the Bekaa

| Action needed | Focal point | Deadline | Status |
| --- | --- | --- | --- |
| Finalize geo-split | UNHCR | ASAP |  |

Next meeting

- To be determined.

# Text boxes

TF – Minutes of Meeting