| Name | Evictions / Litani TF | Meeting Date | 7 October 2019 |
| --- | --- | --- | --- |
| Meeting Location | UNHCR Zahle Sub-Office | Meeting Time | 13:00 |
| Co-Chairs | Hussein Salem (MoSA) – Josep Zapater (UNHCR) | Meeting Duration | 2:00 hours |
| Minutes Prepared by | Josep Zapater (UNHCR) |  |
| Purpose of Meeting | Review current Litani situation and agree on next steps |

Meeting

Discussions – Litani situation

MOSA announced that site 1744 in Anjar has been approved as destination site for the pilot Litani relocation, involving sites 031, 037 and 014. Given that site 1744 does not have capacity for all three sites, that site 014 represents a priority in terms of flood prevention, and that no other relocation sites have been approved, participants agreed to concentrate on relocation of site 014.

Action points – Litani situation

| Action needed | Focal point | Deadline | Status |
| --- | --- | --- | --- |
| Invite ISF to talk to Nasser el Mais to facilitate relocation | MOIM | Tuesday, 8 October |  |
| Explain families next steps as well as expected living conditions in the place of destination | MOSA, Protection, Shelter and WASH | Thursday 10 October |  |
| Provide to MOSA technical advice on HLP and other protection issues on the content of the contract with the landowner | Protection | Tuesday 8 October |  |
| Shawish to negotiate the deal with landowner, with assistance from MOSA | Shawish with MOSA | Week of 14th of October |  |
| MOSA to secure contractual agreement with landlord – taking into account than slightly less families will move than the actual capacity of the site | MOSA | Week of 14th of October |  |
| Start habilitating the site | WASH, Shelter | Week of 14th of October |  |
| Start moving families in batches of 10-12 | MOSA, Protection, Wash, Shelter | Last week of October |  |
| Finalize relocation |  | End of November |  |

Next meeting

- Monday 14 October 11:00 at UNHCR Zahle, to review the above actions and adjust plans as necessary.

# Text boxes

Evictions / Litani  TF – Draft minutes of meeting