Inter-Agency Coordination – Minutes of Meeting

| Name | Inter-Agency Coordination Meeting | Meeting Date | 15 January 2019 |
| --- | --- | --- | --- |
| Meeting Location | UNHCR Zahle Sub-Office | Meeting Time | 16.00 |
| Co-Chairs | Hussein Salem (MoSA) – Josep Zapater (UNHCR) | Meeting Duration | 1 hour |
| Minutes Prepared by | Josep Zapater (UNHCR) |  |  |
| Purpose of Meeting | Coordination around the flood and storm situation |  |  |

Meeting

Summary of Discussions and Action Points

The purpose of the meeting was to discuss a preliminary draft of an action plan for the storm and flood situation in the Bekaa, as well as agree on the next steps. The following was agreed upon:

- Comments will be sent to the draft action plan until Thursday 12:00, after which an amended copy will be circulated to be further discussed and validated at the Emergency Task Force meeting on Friday 13:00.

- As regards coordination, an Emergency Task Force is established composed of:

  - Intersector members,

  - One additional INGO per sector,

  - MSAs from Arsal, Bar Elias and Ghazze.

- Given that there is a Humanitarian Country Team meeting on Thursday, each sector will provide a succinct overview of gaps, by Wednesday COB, to be presented at the HCT. Interagency coordination will provide a simple format to the Intersector.

Bekaa, 15 January 2019