## IS-Coordination
2021 LCRP Sector Workplan - Sector Coordination / Inter-Sector priorities
2021 Timeline
Link to Sector Output and/or Activity Or link to IS priority | Key Priorities | Main Actions | Q1 | Q2 | Q3 | Q4 | Responsible | Main Partners (optional) | Additional Comments | Status
Coordination | Coordination Efforts | Maintain coordination and communication with other Health coordination platforms for COVID-19 & Beirut Port Explosions responses | X | X | X | X | LCRP Health Sector Coordinator
|  | Keep the service mapping (5Ws, PHC, MMU, SHC) updated and available to target population and HWG. | X | X | X | X | LCRP Health Sector Coordinator
|  | Update the drop box folder to include all Guidance and RCCE tools/materials to HWG. | X | X | X | X | LCRP Health Sector Coordinator
|  | Coordinate partner's activities at the PHC level to avoid duplication and gaps and support the IRM model for LPSP protocol. | X | X | X | X | LCRP Health Sector Coordinator
|  | Ensure cross attendance and participation in the other sector's working groups and provide important Health sector updates. | X | X | X | X | LCRP Health Sector Coordinator
|  | Keep monitoring of the key indicators to study the impact of the current crisis on different population cohort. Publish the data trend. Advise on programme designs according to trends. | X | X | X | X | LCRP Health Sector Coordinator
|  | Ensure that all Health partners comply with the guidance of the Ministry of Environment and disseminate any environmental guidance to HWG. | X | X | X | X | LCRP Health Sector Coordinator
| Advocacy Efforts | Work with protection sector on advocacy efforts to reduce confiscation of IDs at hospital level, and to ensure PoCs without CSD or ID have access to PHC & SHCs. | X | X | X | X | LCRP Health Sector Coordinator
|  | Aim for female gynecologist to be available in each health facility. | X | X | X | X | LCRP Health Sector Coordinator
|  | Develop a protocol to support vulnerable Lebanese for hospital care | X |  |  |  | LCRP Health Sector Coordinator
|  | Advocate for fully subsidized delivery costs for pregnant women, and to fast-track delivery appointments at SHCs. | X | X | X | X | LCRP Health Sector Coordinator
IA referrals | Strengthening Referrals | Review and adapt the Inter-Agency minimum standards on referrals. | X |  |  |  | LCRP Health Sector Coordinator
|  | Adapt information leaflets and health awareness products in consultation with PWSN on best communication channels and appropriateness of design. | X |  |  |  | LCRP Health Sector Coordinator
Accountability for Affected Population | Complaints & Feedback Mechanisms | Use data collected through referral and Complaint and Feedback Mechanism (CFM) to inform organizational learning, promote adaption and complement other surveys. |  | X | X | X | LCRP Health Sector Coordinator
|  | Assess and monitor the access of PwSN to information on services, to access PHC services, to reaching CFMs through consultations and assessment |  | X | X | X | LCRP Health Sector Coordinator
|  | Support partners to follow the Inter-Agency minimum standard on complaint & feedback. | X | X | X | X | LCRP Health Sector Coordinator
|  | Review MoPH CFM SOP from an inclusion perspective and to review alignment to best practices. | X |  |  |  | LCRP Health Sector Coordinator
|  | Start discussions on ways to improve the CFM in PHCs. |  |  | X | X | Health & Protection Sectors Coordinators | MoPH
Protection | Risk to SGBV Survivors | Build capacity on clinical care for survivors of sexual abuse (CCSAS) and other forms of SGBV at PHC & SHC, on identification, referral and management of SGBV cases. |  | X | X |  | Health & Protection Sectors Coordinators
Inclusion | Strengthening Inclusion | Strengthen health data collection & analysis to allow for disaggregation of data by age, sex and disability. | X | X | X | X | LCRP Health Sector Coordinator

## Logframe Activities
2021 LCRP Health Sector Workplan - Logframe Activities
2021 Timeline
Sector Output | Key Activities | Q1 | Q2 | Q3 | Q4 | Responsible | Main Partners | Additional Comments | Statute
Outcome 1: Improve access to comprehensive primary healthcare (PHC)
Output 1.1: Financial subsidies and health promotion provided to targeted population for improved access to a comprehensive primary healthcare (PHC) package | Activity 1: Provide subsidized medical consultations (incl. ANC, NCD and MH) and laboratory diagnostics to displaced Syrians, vulnerable Lebanese, PRL and PRS through fixed primary health care outlets | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO) | URDA, AVSI, ARCS, IMC, Rahma Association, LOST, PU-AMI, Caritas, IOM, SIDC, IOCC, LAECD, MEDAIR, Common Effort, RI, Al Midan, Mercy-USA, AMEL, IDRAAC, Thiqah, UNHCR, UNRWA. | Partners are advised to follow the Long Term Subsidization Protocol (LPSP). Focus: Routine immunization, Mental Health & Nutrition.
| Activity 2: Provide emergency primary health care services through mobile medical units where primary health care facilities are hard to reach | X | X | X | X | Health Sector Co-leads (UNHCR & WHO) |  | MMUs have to be used as a last resport and linked to fixed centers.
| Activity 3: Provide health awareness/promotion activities at PHC facility-level and community outreach awareness/promotion activities linked to the health facility | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO)
| Activity 4: Provide family planning counselling to targeted population at PHC facility level | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO)
| Activity 5: Provide children under 5 and pregnant and lactating women (PLW) with micro-nutrients | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO)
Output 1.2: Free of charge chronic disease medication provided at PHC level | Activity 1: Dispense chronic diseases medication to targeted population at primary healthcare level through enrolment in national channels (MoPH/YMCA, UNRWA) | X |  |  |  | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO) | MAGNA, URDA, MAPs, ISWA, HCI Lebanon, PCPM, Rahma Association, Caritas, IOM, QRCS, IOCC, MEDAIR, Common Effort, RI, WHO, AMEL, Thiqah, UNHCR, UNRWA.
| Activity 2: Dispense chronic diseases medication to targeted population at primary healthcare level which are not available through YMCA list (i.e. insulin) nor covered through UNRWA | X |  |  |  | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO)
Output 1.3: Free of charge acute disease medication, medical supplies and reproductive health (RH) commodities provided at PHC level | Activity 1: Provide acute diseases medication to targeted population at primary healthcare level | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO) | HWA, MAGNA, URDA, MAPs, IMC, PU-AMI, Caritas, IOM, Plan-International, IOCC, MEDAIR, Common Effort, WHO, Fondation Mérieux, AMEL, UNICEF, Thiqah, UNHCR, UNFPA, UNRWA.
| Activity 2: Provide medical supplies to primary health care facilities | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO)
| Activity 3: Provide reproductive health commodities including family planning commodities to targeted population at primary healthcare level | X |  |  |  | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO)
| Activity 4: Dispose of expired medications | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO)
Output 1.4: Free of charge routine vaccination provided for all children under 5 at PHC level and through vaccination campaigns | Activity 1: Provide routine vaccination for children under 5 at primary healthcare level | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO) | URDA, HCI Lebanon, DAF, PCPM, Makassed, Caritas, IOM, IOCC, LAECD, MEDAIR, Common Effort, RI, WHO, Al Midan, UNICEF, Thiqah, UNHCR, RMF, UNRWA, Tahaddi Lebanon
| Activity 2: Refer children under 5 who have not completed their vaccination as per EPI calendar to PHCs for vaccination | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO)
Output 1.5: Free of charge COVID-19 vaccine provided to priority groups | Activity 1: Identify priority groups for the COVID-19 vaccine | X |  |  |  | COVID-19 National Task Force | COVID-19 National Task Force
| Activity 2: Provide COVID-19 vaccine for identified priority groups | X | X | X | X | MoPH | Appointed health facilities
Output 1.6: Primary healthcare institutions’ service delivery supported | Activity 1: Provision of equipment and supplies for key primary healthcare institutions | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO) | URDA, MAPs, Intersos, IMC, HCI Lebanon, DAF, PCPM, Rahma Association, Makassed, LOST, PU, AMI, Caritas, IOM, QRCS, IOCC, MEDAIR, Common Effort, RI, IR, Al Midan, Fondation Mérieux, UNICEF, ACTED, UNHCR, UNRWA.
| Activity 2: Provision of staff support for key primary healthcare institutions | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO)
| Activity 3: Provision of capacity building trainings for key primary healthcare institutions | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO)
Outcome 2: Improve access to hospital (incl. ER care) and advanced referral care (advanced diagnostic laboratory & radiology care)
Output 2.1: Financial support provided to targeted population for improved access to hospital and advanced referral care | Activity 1: Provide financial support to targeted population (displaced Syrians, vulnerable Lebanese and PRS) to access hospital care | X | X | X | X | Health Sector Co-lead (UNHCR) & HWG | URDA, MAPs, AVSI, ARCS, ISWA, PU-AMI, Caritas, IOM, SIDC, INARA, Common Effort, RI, IR, Taawon, Mercy-USA, SAMS, IDRAAC, UNHCR, MAP-UK, UNRWA, Tahaddi Lebanon. | The Health sector needs to develop a protocol for supporting hospital care for vulnerable Lebanese.
| Activity 2: Provide financial support to targeted population (displaced Syrians, vulnerable Lebanese and PRS) to access advanced/specialized diagnostic services (on an outpatient basis) | X | X | X | X | Health Sector Co-lead (UNHCR) & HWG
Output 2.2: Public and private hospital service delivery supported | Activity 1: Provide public hospitals with staffing support | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO) | URDA, UNOPS, IOM, QRCS, IOCC, LAECD, INARA, Common Effort, IR, SAMS, UNICEF, UNHCR, UNRWA.
| Activity 2: Provide public hospitals with new/additional equipment | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO)
| Activity 3: Provide public (and private) hospital staff with essential capacity building trainings approved by MoPH | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO)
Outcome 3: Improve Outbreak & Infectious Diseases Control
Output 3.1: The National Early Warning and Response System (EWARS) expanded and reinforced | Activity 1: Decentralize the EWARS sentinel sites (staffing, logistics, IT system development, equipment and technical support missions) | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO) | IOM, MEDAIR, Common Effort, WHO, SI, UNRWA. | Focus: Strengthen & extend EWARS.
| Activity 2: Conduct joint trainings for surveillance and response teams | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO)
Output 3.2: Availability of selected contingency supplies ensured | Activity 1: Maintain the availability of contingency supplies including vaccines, laboratory reagents, response kits and personal protective equipment (PPEs) | X |  |  |  | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO) | MAPs, Caritas, IOM, MEDAIR, Common Effort, WHO, UNICEF, UNRWA.
Output 3.3: National Tuberculosis & AIDS Programmes Strengthened | Activity 1: Provide testing, diagnosis, care, and treatment for TB under NTP | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO) | IOM, Caritas, Common Effort, WHO, Fondation Mérieux, UNRWA.
| Activity 2: Provide testing, diagnosis, care, and treatment for HIV under NAP | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO)
| Activity 3: Conduct trainings / workshops for health care providers of HIV & TB detection and case management | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO)
Outcome 4: Improve Adolescent & Youth Health
Output 4.1: School Health Program (MoPH/WHO/MEHE) maintained | Activity 1: Implement the various components of the School Health Program in public schools | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO) | MAPs, AVSI, HCI Lebanon, Caritas, IOM, IOCC, LAECD, Common Effort, IR, WHO, UNRWA.
Output 4.2: Equitable access to healthcare information to the most vulnerable adolescent and youth increased. | Activity 2: Conduct outreach activities targeting adolescent and youth specifically working and street children (out of school) and adolescent girls. | X | X | X | X | Health Sector Lead (MoPH) & Co-leads (UNHCR & WHO) | MAPs, AVSI, ARCS, Rahma Association, HI, Makassed, PU-AMI, Caritas, Plan-International, SIDC, IOCC, LAECD, MEDAIR, Common Effort, WHO, Al Midan, UNICEF, Thiqah, UNRWA.