## SGBV SWG
2022 SGBV Sub Working Group Work Plan
JRP/3RP Objective: Strengthened inclusive national and sub-national social protection system in line with international protection standards (comprehensive, transparent and equitable) thus ensuring the rights of vulnerable refugees and Jordanians are met and a decent life for all is promoted. [Social services] REF 1.1 Preventing and Responding to Sexual and Gender-Based Violence (and RES 1.1)
Key Areas of Coordination |  | Activities | Expected Output | Indicator | Q1 | Q2 | Q3 | Q4 | Focal point | Comment
A. SGBV SWG Workplan | Supporting service delivery | Update national workplan after mid year analysis or when necessary (at least on an annual basis) and update sub national in line with strategy | workplan and ToRs kept up to date & revised at least on an annual basis | #SGBV SWGcoordination products (ToRs and Workplan ) are updated and finalized and disseminated to sub WG members | x |  | x |  | Coordinators and sub national
|  | Harmonize the coordination structure | Follow up and disseminate subnational ToRs and workplan | # sub national working groups have ToRs and workplan in line with national one | x | x |  |  | Sub national coordinators
|  | Dissemination of english version of SoPs | english version is disseminated | SOPs copies and training opportunities shared with members |  | x | x | x | Coordinators/NCFA
|  |  | Training/information session for focal points | # of focal points trained |  |  | X |  | Senior IM Associate
|  |  | Amalii app function reviewed to respond to remote services | App updated | x | x |  |  | UNHCR in coordination with UNFPA
|  |  | App information are regularly updated and the app is disseminated | # app focal points receiving info | x |  | x | x | national coordinators and all members | sub national coordinator to check the app with group and follow up with members
|  |  | Community based initiatives and social media campaigning for further dissemination of the app | # initiatives #communities covered |  |  | X | X | IFH/JRF/UNHCR/UNFPA
|  | Ensure non specialized actors are equipped with skills to safely refer SGBV survivors | Safe referrals training for frontline workers (non-GBV) is replicated in all field location and guidance disseminated. Trainees from ToT replicate training in all field locations | 100 % field location covered with training (Azraq, Zaatari, Amman, Irbid and South) |  | x | x |  | IRC/IFH/JRF/UNHCR | https://data2.unhcr.org/en/documents/details/63974
|  | Avoid overlapping | 4Ws or national planning/mapping table regularly updated, ensure harmonized approach with field coordination. | 4W update |  | x |  | x | Coordinators
|  | Strengthen role of government in coordination | Advocate for MOSD,FPD and NCFA to join WG, advocate for field coordination structures to involve government counterparts in field WGs. | # meeting attended at national sub national |  | x | x | x | Field and national coordiantors
|  | Ensure participation of refugees and other affected population in coordination structures | Consult communities on strategic documents and products for the development of the app and campaign messages. At field level ensure participation of protection community volunteers | # consultation with communities on coordination issues % of field coordination mechanisms with partecipatory mechanisms for affected population | x | x | x | x | Coordinators | CBOs yes, no volunteers for all. Zaatari will invite next meeting
| Informing Strategic Decision Making | Maintain sector information on UNHCR portal (external) | All information related to SGBV coordination including IM products, ToRs, Sops, MoMs and assessments, etc ..)is uploaded on UNHCR portal and accessible | 100% of MoM uploaded | x | x | x | x | Coordination associate
|  | Information sharing on trends | GBV IMS TF co-chair to present mid year and annual report to SGBV SWG | 2 IMS products disseminated | x | x | x | x | Coordinators | All locations are covered; Amman, Irbid, Mafraq, Zatari and Azraq camps
|  | Identify gaps | SGBV gap analysis updated once a year at field and national level and disseminated to key actors | Gap analysis updated |  |  | X |  | Coordinators and field
| Planning and implementing cluster strategies and funding appeals | Promotion of common standards and guidelines | Global, regional and local tools disseminated on a monthly basis | Minimum 5 tools disseminated | x | x | x | x | Coordintators
|  | Development and/or dissemination of guidance notes on technical issues | Guidance note developed or disseminated on GBV and cash and on GBV mandatory reporting | 2 guidance notes | X | x |  |  | UNFPA
|  | GBV STRATEGY TO BE UPDATED AND DISSEMINATION EVENT | GBV sectoral strategy endorsed and disseminated |  |  |  | X |  | Coordinators
| Monitoring and evaluation | Supporting Monitoring framework for the response as per 3RP | Conduct analysis of reported indicators/production of IM product (dashboards) | Quaretrly analysis for JRP indicators conducted and presented to WG members |  | x |  | x | IMO/ Coordination Associate
|  | Roll out of ME toolkit | ToT ME toolkit disseminated and refresh calls offered | 35 organizations trained on the toolkit | X | X |  |  | Coordinators
|  | Measuring progresses against results and performance | Conduct self evaluation assessment | 1 survey conducted and reccomendations discussed |  |  | x | x | IMO/ Coordination Associate
| Building national capacity and preparedness | Coordinate capacity buidling initiatives | Identity training needs, develop training calendar, provide support to fill gaps in terms of capacity building | 2 Training offered based on matrix and resources available |  | x | x | x | Coordinators, , IMO/Coordination Associate | Activity info (3RP), Coaching
|  | Capacity Building initiative on coaching for case management |  | 30 service providers with improved case management skills | X | X |  |  | GBV IMS TF
|  | Peer to Peer cross learning | Members of the SWG will take turn in presenting to each other their good practices at each SWG meeting. | good practices -including men and boys approaches - on SGBV implementation and programming are presented by SWG members (at least 9) | x | x | x | x | Members
| Supporting advocacy | Advocate with donors and key stakeholders to include SGBV as a key priority for response | Briefings for donors to be provided twice a year. Advocacy with relevant government stakeholders conducted | 1 donor briefing conducted; at least one meeting with government stakeholders |  | x | x | x | Coordinators | Donor briefing for launch of GBV IMS report and 16 days and 2 done for COVID
|  | assess policies and programs to proetc older people in Jordan | policy brief on older people access to protection programs | dissimination of the policy brief on the protection of older people in Jordan through a luanch event and social media |  |  |  | x | Helpage
|  | Advisory role for JHF proposals and laison with OCHA humanitarian section and other resources for fundings | Develop sector prioroties for the call and other relevant documents. | Champion inclusion of GBV in at least 50% of common pool funding allocation |  | x | x |  | Coordinators | GBV in first allocation with 3 partners so we already meet 50%.
|  | Coordinate advocacy activities for the 16 days and International women's day | Develop calendar of activities, develop joint activities/messages on behalf of the SGBV SWG. | Joint initiative conducted | x |  | x | x | SAG
b. Cross sector collaboration | Health/RH SWG | CMR gaps in urban areas are addressed and updated in referral pathways | OUTREACH AWARNESS- COMMUNITY BASED initiatives about services | # mapping updated and presented at SGBV WG meeting |  | X |  | X | RH/GBV Coordinators
| Age, Gender and disability | Support the gender dashboard | Gender dahsboard | Updated Gender Analysis |  |  | x | x | UNWOMEN/Gender focal points
|  | Improving analysis of GBV risks and programming for older women | joint intervention/guidance note | # members of SGBV WG, gov't oficials, CSO and CBOs trained on HelpAge training modules |  | x | x | x | HelpAge
|  | Women and girls with disabilities are consulted on key coordination doc and represented in joint event and disability inclusion is fostred in GBV programming | Improve disability inclusion in GBV programming | # learning session |  | x |  |  | AIDOS/IFH
| Child protection | Strengthen work on adolescent and child survivors of sexual violence | At least one joint meeting on a yearly basis | # joint meeting |  | x |  |  | CP and GBV Coordinators
|  | coordination with the national taskforce on child marriage | At least one joint meeting on a yearly basis | # joint meeting |  |  | x |  | NCFA/CP
| WASH | Learning event GBV CC | Improve knowledge on the impact of climate change on GBV risks | One learning event | X |  |  |  | UNFPA/WASH
| Livelihood | Establish and coordinate a Local Anchor Group of GBV and LLH actors who will develop an integrated GBV/LLH program model | Monthly meetings | # joint meeting Program model for integrated GBV/LLH services developed |  | x | x | x | DRC