## Slide 1: BURUNDI SITUATION EMERGENCY MEETING
OFFICE OF THE PRIME MINISTER
DEPARTMENT OF REFUGEES
BURUNDI INFLUX CONTIGENCY PLAN
26TH MAY 2015

## Slide 2: CONTINGENCY PLAN
Since late November 2014 up to March 2015, Uganda was receiving trickles of Burundian Refugees and about 1352 had been granted refugee status by end of March 2015. As of end of April, the number went to 3000.
This prompted UNHCR and OPM to come up with a contingency plan indicating the likely scenarios and what needs to be done as follows:

## Slide 3: SCENARIO ONE: 5000
This is the current scenario. This Scenario presupposes:
Burundian asylum seekers will continue to enter through recognized border points of Tanzania, DRC and Rwanda up to the time of elections.
Asylum seekers will be received at the Kabazana and Juru Reception Center in Nakivale Settlement where they will be registered and issued with an Asylum Seeker household document and ration card.

## Slide 4: SCENARIO one cont..
All Burundian Asylum seekers subjected to individual Status determination
Upon granting of refugee status, refugees will be settled in Nakivale or Oruchinga Settlements.
Asylum seekers and refugees have access to medical assistance, social services, education and food assistance from the existing IPs.
Rejected asylum seekers may be allowed to remain at the Reception Center pending appeals.

## Slide 5: SCENARIO TWO (most likely):10,000
If the Conflict is not contained and reception conditions are not adequate in the surrounding Countries,
We shall see an increasing numbers of Burundian asylum seekers, particularly those with family/community links will move to Uganda resulting in an influx of up to 10,000 asylum seekers in the next few months.(Olready the trend shows 300 to 400 daily on average)
Asylum seekers will arrive at border points in larger numbers or travel in groups to Settlements or Kampala.

## Slide 6: SCENARIO 2 cont..
Transportation from borderline collection points will be organized should new arrivals collect at border crossing points.
Asylum seekers arriving to South West border Transit Centers and Settlements will be transported to Nakivale Settlement or Oruchinga.

## Slide 7: SCENARIO 2 cont..
Scenario two will see some of the settlement services and facilities stretched hence the need for extra support and more players
Scenario two may compel the Government to consider granting Prima facie refugee status as individual RSD may prove cumbersome because of big numbers

## Slide 8: SCENARIO 3: 20,000 asylum seekers
Should Burundi experience protracted pre and post election unrest or violence with increased out-flows, secondary movement to Uganda could increase significantly.
The third scenario remains likely should numbers in Tanzania and Rwanda continue to increase and reception conditions become strained.

## Slide 9: SCENARIO 3: cont..
Surpassing 15,000 – 20,000 new arrivals from Burundi, in addition to the ongoing influx from DRC will trigger an additional emergency planning.

## Slide 10: Influx Monitoring and Reception
Entry Points | Transit/Reception Location | Receiving Settlement
Kisoro – Kabale border points | Kisoro/ Nyakabande TC | Nakivale/ Oruchinga
Kisoro: Entry from DRC | Kisoro/ Nyakabande TC | Nakivale/ Oruchinga
Kabale to Tanzania border | Nakivale Kabizana Reception Center | Nakivale/ Oruchinga
ROTs/ transfers from Kampala | Nakivale Kabizana Reception Center | Nakivale/Oruchinga
Walk in’s to Settlements | Settlement Reception Center | Nakivale/Oruchings/Kyaka

## Slide 11: Entry Points and Reception Facilities cont..
Asylum seekers entering Uganda through Kisoro border axis points will be transported to Nyakabande Transit Center.
OPM will take a decision on whether asylum seekers will remain at Nyakabande pending RSD procedures or transfer to Nakivale Settlement to await RSD.

## Slide 12: Reception and Settlement facilities cont..
Nakivale is 70Sq miles, with a population of 74000 refugees. Its close to Tanzania and Rwanda border where majority asylum seekers are likely to pass.
Kabazana Reception Centre has existing infrustructure for up to 1000 and can be expanded to 5000 capacity with in a week

## Slide 13: Reception and Settlement facilities cont..
Juru reception Centre: Used in 2014 for assisted return. The transit has infrustructure for up to 1000 people and can be expanded up 5000 capacity
Additional land is available in Nakivale and this can accommodate up to 10.000. WASH and other infrastructure will however be required as well as new Partner Staff to support this process

## Slide 14: Reception and Settlement facilities cont..
Oruchinga Refugee Settlement: In the event that Nakivale is streched, another reception centre will be established in Oruchinga with the capacity of 1000 refugees
New arrivals/ transfers from Kampala will be accomodated in the reception centre and REC cases settled in Kyaka

## Slide 15: PROTECTION AND ASSISTANCE ON ARRIVAL
During this period, asylum seekers who are residing in the Settlement or Transit Centers will be provided with the following;
Bio data Registration as an asylum seeker
Asylum Seeker certificate to each household
Issuance of a ration cards for WFP food distribution

## Slide 16: Protection and Assistance cont..
Accommodation in an OPM designated Transit/ Reception Center (or with relatives/community members in Settlements)
Basic NFI kit (new arrivals kit) based on Household size
Medical assistance through Settlement medical partners

## Slide 17: Protection and Assistance cont..
WFP food rations (100% scale)
Access to education for children
Access to all community services, health, legal, psychosocial support

## Slide 18: Protection and Assistance cont..
Once accorded refugee status, all households will be issued a land plot, NFI kits including a shelter kit and have access to income generation and other programs

## Slide 19: SECTOR RESPONSE STRATEGY
Uganda – Burundi Refugee Influx to South West Uganda |  |  |  |  | 
 | Kisoro | Nakivale | Oruchinga | Rwamanja | Kyaka II
Government | OPM | OPM | OPM | OPM | OPM
UNHCR | UNHCR | UNHCR | UNHCR | UNHCR | UNHCR
Multi-sector | HIJRA | ARC | HIJRA | LWF | DRC
Registration | OPM | OPM | OPM | OPM | OPM
Child Protection | HIJRA, Save the Children UNICEF | ARC, Right to Play, | HIJRA, Right to Play | LWF/ War child | DRC, TPO
SGBV | HIJRA/ MTI | ARC, MTI | HIJRA, MTI | LWF, AHA, War Child | DRC, AHA
Psyco-social | Save the Children | ARC | HIJRA | LWF, | DRC, TPO
Logistics, Warehouse, Transport | HIJRA | AIRD | HIJRA | AIRD | AIRD
Road Rehab |  | AIRD/ARC | AIRD/HIJRA | AIRD/LWF | AIRD/DRC
WASH | HIJRA/ UNICEF | ARC | HIJRA | LWF | DRC
Medical/ Health | MTI | MTI | MTI | AHA | AHA
Livelihood |  | Nsamezi / ARC | Nsamezi/ HIJRA | LWF/ Nsamezi | DRC/ Nsamezi
Education |  | WTU | WTU | WTU | WTU
Environment |  | Nsamezi | Nsamezi | Nsamezi | Nsamezi
Tracing/ Reunification | ICRC/ Red Cross | ICRC / Red Cross | ICRC/ Red Cross | ICRC/ Red Cross | ICRC/ Red Cross
WFP Food Distibution | HIJRA | Samaritans Purse | Samaritans Purse | Samaritans Purse | Samaritans Purse
Transportation: refugees | AIRD, HIJRA | AIRD | AIRD | AIRD | AIRD
Other UN Partners in local communities | UNICEF Save the Children ICRC | SCF, TPO, |  | UNFPA, UNICEF | 

## Slide 20: INFRASTRUCTURE PLANNING FOR SETTLEMENTS:
Nakivale is the main receiving Settlement for Burundians while Rwamanja is the main receiving Settlement for DRC refugees transferred from Nyakabande Settlement, Kisoro.
In addition to transfers, there are many refugees/new arrivals travelling to Settlements and residing with relatives. Some are presenting to OPM for registration while others may be waiting to present. There is need for sensitisation.

## Slide 21: INFRASTRUCTURE PLANNING FOR SETTLEMENTS
OPM and UNHCR will assess current absorption and in structure capacities and of the Settlements based on numbers of persons physically residing in the Settlements versus available land.
UNHCR in coordination with Partners and OPM will undertake an infrastructure mapping and rollout plan to

## Slide 22: BORDER MONITORING:
UNHCR and OPM to maintain regular contact with Uganda borderline officials on DRC, Rwanda and Tanzania border crossing points to monitor the influx.
Border and immigration officers, police, local leaders and communities will be trained by UNHCR/OPM on refugee protection, access to asylum and Uganda legal frameworks to facilitate access to asylum.

## Slide 23: STATISTICS OF NEW ARRIVALS:
Daily statistics on new arrivals from DRC and Burundi will be provided by OPM. A daily/weekly update will be circulated
New arrivals at Reception and Transit Centers are being registered with all the bio data in the Refugee Information Management System (RIMS) .

## Slide 24: WHY SCENARIO 2 AND 3 ARE LIKELY
    3 weeks after the Government put down a military coup, protests have been building again in Bujumbura. Recall that before the Coup thousands were already fleeing the Country
    Government warnings of insecurity and the al-Shabaab threat after the coup attempt haven’t cowed the protesters or the opposition

## Slide 25: Factors for likehoods cont..
A war in Burundi almost certainly means greater conflict in Rwanda or the DRC. it’s likely rebel factions in the country would venture past its borders as they did during the civil war.

## Slide 26: Factors for likehoods cont..
The Government has maintained that Elections will go as planned (June 26th) despite international pressure. Only parliamentary elections have been post-poned to early june 2015.
Mr. Rwasa finds himself stuck in a campaign in which he faces heavy security risks. Many contenders are not campaigning because there is no guarantee for security

## Slide 27: Factors for likehoods cont..
Its alleged that rebel leader who announced the coup has been arrested along with several other Army officers.
Huge Concern on small arms in circulation and the allegation that CNDD-FDD youth wing “Imbonekure” are being armed by the ruling Party to terrorise the people
Closing of the political space is increasing. Opposition and civil society organizations critical of the regime are being hunted and some have died

## Slide 28: Factors for likehoods cont..
Land shortage and high population density have partly contributed to unrest as the current land management frame work has failed to address the returnees and IDPs grievances.
Actually the Committee which was handling land issues has been suspended

## Slide 29: Factors for likehoods cont..
Nakivale Known as a reception area in the region since 1960s
Some refugees have relatives and friends in Uganda
Some claim had no idea of any refugee camp in Rwanda or whether they could be received.

## Slide 30: Factors for likehoods cont..
Some have had of Cholera and deplorable conditions in TZ.
Some claim they could not go to Rwanda or DRC because they feel these two are part of the conflict and the conflict could spread there an unlikely situation in Uganda
Check points and road blocks on the Rwanda border where fleeing refugees are being prevented from Crossing to Rwanda by either Police or Militia

## Slide 31: Factors for likehoods cont..
Killing of an opposition leader Zedi Feruzi on Saturday, the leader of the Union for Peace and Development(UPD) has complicated matters
Suspension of the talks with Government
Opposition vowing to intensify protests against third term.
Grenade attack in a busy market that killed three people and injured around 40 others

## Slide 32: Factors for likehoods cont..
Continued Crack down on anti government forces where about 30 people are believed to have died and thousands now behind doors with out trial.
Cholera out break in Tanzania where about 31 people have died among the total of 3000 cases registered and over.

## Slide 33: Factors for likehoods cont..
Determination by Mr. Nkuruziza to go on with the elections despite the protests.
All these are indicators that the problem is escalating and hence cause for worry amongst humanitarian actors

## Slide 34: So what next