## Collection Points, Way station
Accountability Matrix for Public Health Response in Refugee Emergency (As of 30-08-2015)
Kagunga, Manyovu Entry Points
What (Activity) | Who | When | Status
Provide 24 hours emergency medical/ referral care. | IRC | Ongoing
Screening of children for nutrition status and provision of immediate treatment/referral and prioritized for relocation to camp | IRC | Ongoing
Epidemic preparedness and response (including Cholera treatment centre) | MSF | Ongoing | No new cholera cases. CTC on standby
Ensure continuation/referral for HIV/TB treatment. | IRC | Ongoing
Public health surveillance (Emergency/Basic HIS). | IRC | Ongoing
Ensure basic health care services are available for (child and adult) survivors of sexual violence. | IRC | Ongoing
Good quality condoms to be made available. | IRC | Ongoing
Pregnant women prioritized for relocation/referral to hospital depending on gestation/if in labor | IRC | Ongoing | Speed boat/ambulance through Manyovu
New arrivals to receive food “on-arrival” to last the number of days until relocated to camp. | Caritas | Ongoing
Ensure capacity to provide en route emergency health care. | IRC | Ongoing
Water and HEB provided during transport | IOM | Ongoing
WASH | Oxfam | Ongoing
Kasulu axis entry points
What (Activity) | Who* | When | Status
Provide 24 hours emergency medical/ referral care. | TRCS | Ongoing
Screening of children for nutrition status and provision of immediate treatment/referral and prioritized for relocation to camp | TRCS | Ongoing
Epidemic preparedness and response (list priority activities) | TRCS | Ongoing
Ensure continuation/referral for HIV/TB treatment. | TRCS | Ongoing
Public health surveillance (Emergency/Basic HIS). | TRCS | Ongoing
Ensure basic health care services are available for (child and adult) survivors of sexual violence. | TRCS | Ongoing
Good quality condoms to be made available. | TRCS | Ongoing
Pregnant women prioritized for relocation/referral to hospital depending on gestation/if in labor | TRCS | Ongoing
New arrivals to receive food “on-arrival” to last the number of days until relocated to camp. | TRCS | Ongoing
Ensure capacity to provide en route emergency health care. | TRCS | Ongoing
Water and HEB provided during transport | TRCS | Ongoing
WASH | TRCS | Ongoing
Ngara Axis Entry Points
What (Activity) | Who* | When | Status
Provide 24 hours emergency medical/ referral care. | TRCS | Ongoing
Screening of children for nutrition status and provision of immediate treatment/referral and prioritized for relocation to camp | TRCS | Ongoing
Epidemic preparedness and response (list priority activities) | TRCS | Ongoing
Ensure continuation/referral for HIV/TB treatment. | TRCS | Ongoing
Public health surveillance (Emergency/Basic HIS). | TRCS | Ongoing
Ensure basic health care services are available for (child and adult) survivors of sexual violence. | TRCS | Ongoing
Good quality condoms to be made available. | TRCS | Ongoing
Pregnant women prioritized for relocation/referral to hospital depending on gestation/if in labor | TRCS | Ongoing
New arrivals to receive food “on-arrival” to last the number of days until relocated to camp. | Caritas | Ongoing
Ensure capacity to provide en route emergency health care. | TRCS | Ongoing
Water and HEB provided during transport | IOM | Ongoing
WASH | Oxfam/TRCS | Ongoing

## Transit Centre
Accountability Matrix for Public Health Response in Refugee Emergency (As of 30-08-2015)
Kigoma Transit Centre
What (Activity) | Who | When | Status
Provide 24 hours emergency medical and referral care. | IRC | Ongoing
Screening of children for nutrition status and provision of immediate treatment/referral and prioritized for relocation to camp | IRC | Ongoing | Needs close monitoring
Epidemic preparedness and response (including cholera treatment centre) | IRC | Ongoing
Ensure continuation/referral of HIV/TB treatment. | IRC | Ongoing | Referral to Nyarugusu camp
Public health surveillance (Emergency HIS). | IRC | Ongoing | Ensure UNHCR receiving regular reports
Ensure basic health care services are available for (child and adult) survivors of sexual violence. | IRC | Ongoing
Good quality condoms to be made available. | IRC |  | Reconfirm
Information sharing on access to HIV treatment and SGBV services | IRC | Ongoing
Pregnant women prioritized for relocation/referral to hospital depending on gestation/if in labor | IRC | Ongoing | Maweni Hospital
Ensure capacity to provide en route emergency health care. | IRC | Ongoing
Water and HEB provided during transport | IOM | Ongoing
New arrivals to receive hot meal “on-arrival” to last the number of days until relocated to camp. | Caritas | Ongoing
WASH | CRS/Caritas | Ongoing
Lumasi Transit Centre, Ngara
What (Activity) | Who* | When | Status
Provide 24 hours emergency medical and referral care. | TRCS | Ongoing
Screening of children for nutrition status and provision of immediate treatment/referral and prioritized for relocation to camp | TRCS | Ongoing
Epidemic preparedness and response (including cholera treatment centre) | TRCS | Ongoing
Ensure continuation/referral of HIV/TB treatment. | TRCS | Ongoing
Public health surveillance (Emergency HIS). | TRCS | Ongoing
Ensure basic health care services are available for (child and adult) survivors of sexual violence. | TRCS | Ongoing
Good quality condoms to be made available. | TRCS | Ongoing
Information sharing on access to HIV treatment and SGBV services | TRCS | Ongoing
Pregnant women prioritized for relocation/referral to hospital depending on gestation/if in labor | TRCS | Ongoing
Ensure capacity to provide en route emergency health care. | TRCS | Ongoing
Water and HEB provided during transport | IOM | Ongoing
New arrivals to receive hot meal “on-arrival” to last the number of days until relocated to camp. | REDESO | Ongoing
WASH | REDESO | Ongoing

## Camp
Accountability Matrix for Public Health Response in Refugee Emergency (As of 15-07-2015)
Nyarugusu Camp
Program | What (Activity) | Who | When | Status
Public health | Ensure regular health coordination meetings at camp level | UNHCR | Weekly | Ongoing
| Rapid assessment of extra needs and resources, including staffs & supplies due to increased numbers. | Health Partners | Done | Staff recruitment ongoing
| Provide comprehensive and decentralised PH services (including OPD, EPI, IMCI, non-communicable diseases, mental illness). | TRCS/MSF-CH | Ongoing
| Construct health facility including decentralization (mobile clinic by MSF) | TRCS/MSF-CH | Ongoing | 2 health posts in Zone 8 and 9 respectively
| Review and expand inpatient ward and Pharmacy capacity | TRCS/SRC/IFRC/MSF-CH | Ongoing | New Health post 4 in Zone 8 has 30 bed IPD capacity
| Ensure the essential medicine, medical supplies and lab supplies (including for outbreak investigation) are sufficient. | Health Partners | Ongoing | Annual UNHCR consignment arrived
| Ensure new arrivals are fully integrated into the HIS (Disaggregate data to follow trends in morbidity and mortality). | TRCS | Ongoing
| Ensure new arrivals have information on available PHC services and how to access them. | TRCS | Ongoing
| Ensure all children under 15 receive measles & Polio vaccination and all under 5 receive other routine immunizations. | TRCS | Ongoing
| Establish services for mental health and psychosocial support. | TRCS | Ongoing
| Recruit and train refugee health workers from among new arrivals. | TRCS | Ongoing
| Make provisions for safe blood transfusion in referral health facilities. | TRCS | Ongoing
| Referral of emergency and life-saving conditions (support to national, district and regional hospitals as appropriate). | TRCS | Ongoing
| Develop appropriate behaviour change communication messages and translate to local/refugee languages | UNHCR/UNICEF | Ongoing
| Procure adequate LLINs and plan distribution with clear communication and strict monitoring plan on appropriate use | UNHCR | Ongoing
Epidemic Preparedness and Response | Outbreak control team (OCT) established and active | UNHCR/DMO | Yes | Meets weekly
| Camp specific EPREP available and updated | UNHCR | Yes
| Surveillance systems with an early warning system in place | Health Partners | Yes
| Weekly reporting of diseases of outbreak potential and timely feedback provided at Camp Level. | Health Partners | Yes
| Outbreak investigation capacity including team and kits | MSF-CH | Yes
| Surveillance related training for the staff | MSF-CH | Ongoing
| Sample collection, handling and transport capacity | RMO/WHO | Yes
| Reference lab identified and agreed to testing samples | Maweni hosp | Yes
| Standard treatment protocols available | MOH/WHO/UNHCR | Yes
| Clinical staff trained in case management and treatment protocols | MSF-CH/WHO | Ongoing
| Referral system available | MSF-CH | Yes
| Isolation department/area available for other epidemic prone diseases | MSF-CH | Yes | MSF-CH changed the CTC into stabilization centre
Food | New arrivals to receive food “on-arrival” to last the number of days until integrated into the normal distribution mechanism. | AIRD/WFP | Ongoing
Core relief items | Essential CRI including kitchen sets, soap and cooking fuel is distributed within 24 hours. | UNHCR | Ongoing
Nutrition | Undertake a nutritional screening of new arrivals- children 6-59 months. | TRCS/MSF-CH | Ongoing
| Provide SAM and MAM treatment programs | TRCS/MSF-CH | Ongoing
| Ensure availability of stabilization centre | MSF-CH | Ongoing
| Provide blanket feeding program | TRCS | Ongoing
| Ensure pregnant women are seen by ANC and are integrated into the SFP. | TRCS | Ongoing
| Ensure lactating women receive breast feeding support and are integrated into the SFP. | TRCS | Ongoing
| Give Vitamin A supplementation to new arrivals (children 6-59 and lactating women within 6m of delivery). | TRCS | Ongoing
| Essential micronutrient supplements are given including iron/folate for pregnant/lactating women and children 6-59 months. | TRCS | Ongoing
Reproductive health/HIV | Assess adequacy of existing RH and HIV related supplies and commodities to meet demands of new arrival. | UNHCR/TRCS | Ongoing
| Make available a basic antenatal care package for all pregnant women. | TRCS | Ongoing
| Make available BEMONC services including referral services for CEMONC. | TRCS | Ongoing | CEmONC available in camp
| Family planning counselling and supplies available. | TRCS | Ongoing
| Culture and gender sensitive, youth friendly SRH information and services available for young people (10-24). | TRCS | Ongoing
| VCT and PMTCT services made available. | TRCS | Ongoing
| Identify MARPs and integrate them in on-going targeted interventions. | TRCS | Ongoing | To be verified
| Idenitifcation of PLHIV from new arrivals, register and ensure access to cotrim prophylaxis and determine eligibility for ARVs. | TRCS | Ongoing
| Ensure basic health care services are available for (child and adult) survivors of sexual violence. | TRCS | Ongoing
WASH | Refer to WASH matrix
NOTES
Based on different emergency experiences & documentations UNHCR recommends vaccination of all children under 15 for measles and polio if they have no vaccination card