## H. Consolidated National + Area
STRATEGY at NATIONAL LEVEL | [5 empty] | STRATEGY at AREA LEVEL (Bekaa, North, South, Mt Leb)
| Management, Coordination, Information Management & Fundraising |  |  |  |  | Management, Coordination, Information Management & Fundraising
| Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved | Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Determine & agree upon any special additional coordination mechanisms to manage the response to a mass influx situation, particularly strengthening communication with key actors on GoL side (MoI, MoD, LAF, ISF) | To be determined |  | GoL (MoSA) & UNHCR | Inter-agency partners | Jointly agree coordination modalities with local actors, authorities and NGOs, political parties in some locations (& UNIFIL in the South), for 'remote control response' in certain locations which may become too dangerous for a staff presence, by sharing local focal points / creating local level coordination meetings in these potential 'hot-spots' / by training local NGOs & providing funding to support their activities, prioritising key locations (eg Hermel & Arsal in Bekaa, or south of the Litani River) | To be determined | Funding for local NGO staff training & coordination support | UNHCR | All agencies, working with the Lebanese Red Cross, local NGOs & authorities (& particularly UNIFIL in the South)
2 | Map possible scenarios in case of a mass influx (eg flows from border crossings, official & unofficial), liaise with GoL so as to be prepared in case of limitations of humanitarian access | To be determined |  | UNHCR | Inter-agency partners, OCHA, etc. | Hold simulation exercise for an influx into the respective area with a scenario involving a combination of difficult factors, & ensure GoL involvement | To be determined | Funds to stage a simulation exercise | DRC & the Area 'Crisis Management Team' | GoL, Partners at field level
3 | Agree on early warning signals that will trigger deployment of resources from outside Lebanon to agencies operating here, & from the national to area level | To be determined | To be determined | UNHCR | Inter-agency partners | Consult UNIFIL & verify that it will continue to provide assistance in support of the hosting/local community, as well as emergency medical care to registered Syrian refugees, provided it is with the consent of the local authority | Ongoing |  | UNHCR | UNIFIL
4 | Develop a strategy for agencies to mobilize additional resources quickly (eg a revision of RRP) | To be determined |  | UNHCR to call IA meeting | UN Agencies, NGO partners, GoL (MoSA), donors | Pre-prepare more ERF applications (= OCHA administered life-saving fund) | To be determined |  | INGOs with the support of OCHA | All INGOs
5 | Obtain from all agencies on a regular basis a self-assessment of their current level of preparedness (i.e. how many HH they can support, any physical reserve stocks &/or financial resources above and beyond this), and determine how long these physical stocks &/or funds would last | To be determined | A template for the self-assessment & a Focal Point per agency | UNHCR to design & send out template for 'self-assessment' | All actors | Assess agencies' capacity to respond, resources, & number of staff (also useful for staff safety purposes) in all key locations (N.B. it must be clear whether stocks are national level or area level, & not duplicate this info) | To be determined |  | All agencies to report their 'state of readiness' | UNHCR (Beirut) to design & send out a template for this 'self-assessment'
6 | Continue to discuss the issue of 'Transit Sites' with GoL at high level, to ensure that all actors understand the pros & cons of establishing transit sties to respond to the mass influx situation | Ongoing |  | UNHCR | GoL (MoSA) | Continue to identify additional locations within the area, suitable for potential Transit Sites | Ongoing |  | UNHCR Area Office | GoL (MoSA)
7 | Map possible displacement scenarios, liaise with GoL so as to be prepared in case of limitations of humanitarian access | To be determined |  | UNHCR | GoL (MoSA & HRC) | Establish inter-area agreements on mutual support under various scenarios, particularly for data sharing (eg information on refugee movements from Bekaa to the other areas) | To be determined |  | UNHCR Area Office | GoL (MoSA)
8 | Strengthen the current border monitoring system / introduce it ASAP with GoL support & LAF agreement | To be determined |  | UNHCR | GoL (MoSA) | Agree on modalities for a permanent presence & a public information function at the border - in coordination with Protection staff/working group & agree with LAF on modalities to facilitate the access to the refugees & of service providers to the security belt / sensitive border areas | To be determined |  | UNHCR Area Office | GoL, NRC, UNRWA, Caritas
9 | Continue to enhance coordination with the Red Cross (ICRC, Lebanese Red Cross & other national societies) on contingency planning | Ongoing |  | UNHCR | Lebanese Red Cross, ICRC & Red Cross Movement | Liaise with Lebanese Red Cross, and other national organisations (eg Islamic Scouts, Civil Defence) in every district in the area | Ongoing |  | UNHCR Area Office | MoSA, LRC, Islamic Scouts, Civil Defence
10 | Review & clarify level of decision-making authority of Senior Field Coordinators & their staff in field (area) officers - specifically for managing the contingency response to the scenarios | To be determined | Agencies review TORs & authority levels of field staff | All actors | All actors | Review / agree best approach to strengthen relationships & improve data collection at muncipality level - continue building trust through QIPs / training, eg on protection, emergency registration, & better reporting of achievements | To be determined | Additional support may be needed for Municipalities | UNHCR, UNICEF, UNDP, DRC, NRC, MoSA | UNHCR, UNICEF, DRC, NRC, MoSA
11 | Information Management: review requirements for IM in a contingency response to these scenarios, particularly reporting from and to the field, & continue to develop SOPs & templates | Ongoing | Templates, training, & at least 1 IMO per area office | UNHCR | Sector Leads, IMU, Area Officers, Programme staff | Information Management: review IM requirements, agree & implement reporting protocols / standardized assessment templates & other forms (all web-based if possible) to improve the flow between field & central level | Ongoing | Templates, training, & at least 1 IMO per area office | UNHCR Area Office | IMO posted into each area office
12 | Information Management: complete the 3W mapping, and produce maps of key facilities in each area, including locations of SDCs & Lebanese Red Cross | To be determined |  | UNHCR | Information Management Unit (IMU) | Mass Communication: strengthen info sharing protocols between agencies/service providers, and outreach to local authorities, refugees & host communities, eg the regular Municipality Briefing Note focusing on achievements / success stories / show local 'ownership' | To be determined |  | UNHCR Area Office | All partners plus stakeholders including local authorities, refugees & host communities
13 | Create a core group to oversee 'operationalization' of the CP, and follow-up with Sector Leads & Senior Field Coordinators to ensure they complete all assigned taskings | 2013-07-31 |  | UNHCR, GoL (MoSA) | Sector Leads, nominated key partners at central level | Determine & agree upon the role & composition of a Crisis Management Team for area level (e.g. the MoSA Regional Coordinator), both to follow up on assigned CP preparedness actions & to act as an executive group in a crisis | To be determined |  | UNHCR Area Office & GoL (MoSA), UNDP, DRC, NRC, Amel, IMC, WFP | Key agencies in the current response & that are relevant to the scenarios (eg UNIFIL in the South)
14 | Add contingency planning as a standing item to each sectoral & inter-agency working group meeting agenda | Immediately |  | Sector Leads | Sector working groups | Add contingency planning as a standing item to each sectoral & inter-agency group meeting agenda, at area level | Immediately |  | Area Officers | Sectoral & inter-agency working groups
15 | Pre-agree the vulnerability & targeting criteria for relevant sectors (Protection, Health, Shelter & WASH, Food & NFIs) | Ongoing |  | Sector Leads | Sector working groups | Endorse group level assessment forms reflecting pre-agreement of vulnerability for relevant sectors (Protection, Shelter, WASH, Food, NFIs, Health) | Ongoing |  | UNHCR Area Office | Area-level working groups
16 | Determine the core tasks to be fulfilled in a crisis & prepare rosters of key staff to perform them | To be determined |  | All actors | All actors | Determine the core tasks to be fulfilled in a crisis & prepare rosters of key staff to perform them | To be determined |  | All agencies | All agencies
| Response Actions | Deadline | New resources required ? | Responsible | Actors involved | Response Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | GoL & UNHCR activate CP response after verification of numbers & inform UNSCOL, UNIFIL, OCHA & partners | On Day 1 |  | GoL (MoSA) & UNHCR | GoL, UNHCR, UNSCOL, UNIFIL | Implement the strategy to obtain information directly from the border, 24/7 | Within 2 days | Funds for printing | UNHCR Area Office | GoL, Caritas, UNRWA
2 | GoL to provide population movements on daily basis (entries and exits) | Daily, starting ASAP | UNHCR to support to GoL if needed | GoL | GoL, UNHCR | Liaise with relevant authorities in areas of concern, to ensure humanitarian access (problem is the staff safety issue more than prevention of access per se) | Upon need |  | UNHCR Area Office (Security) | Relevant partners in Protection, especially ICRC
3 | Adjust / re-deploy staffing for initial 24 hrs response by relevant actors / prepare & share lists of staff | Within 24 hrs | staffing lists/rosters | All actors | All actors | Rapidly deploy support staff from central level, from area to area, or within the area to respond adequately, particularly at transit sites | Upon need |  | All agencies | All agencies
4 | Seek urgent authority from the Council of Ministers to establish 'transit sites' at predetermined locations | Within 48 hrs |  | GoL (MoSA) | GoL, UNHCR | Reconfirm the potential of all predetermined locations for 'transit sites', & activate the plans for their establishment, organised sector by sector | Within 48 hrs | Initially by drawing upon stocks | Area Crisis Management Team | Inter-agency fora / Sector Leads
5 | Review existing national / field level coordination structure & adapt as necessary to the actual situation | Within 1 week |  | UNHCR | GoL, UN Agencies, NGO partners | Agree on most important response per sector: whether activities can be reduced in one sector in order to increase in other sectors | Within one week |  | Area Crisis Management Team | Inter-agency fora / Sector Leads
6 | Ensure regular consultation with ICRC, the Red Cross Movement & other relevant actors not formally in the coordination structure | Weekly | Update contact lists | UNHCR | UNHCR, ICRC & other actors | Regular consultation with ICRC, Red Cross Movement & other relevant actors, especially local CBOs | Weekly |  | UNHCR Area Office | UNHCR, ICRC & other actors
7 | Coordinate any inter-agency sectoral or cross-sectoral rapid assessment & present a 'gap analysis' | Within 1 month | Staffing, IM tools, inventory of assessments | GoL, UNHCR | Inter-agency partners engaged in the assessment
8 | Sector working groups review priorities & capacities in the light of the early response to the new emergency, & report any alarming shortcomings | Within 1 month |  | Sector Leads | Sector working groups
9 | Liaise with relevant members of the UNCT to assess impact on other populations (IDPs, Host Communities, Palestine Refugees, TCNs, etc.) | Within 1 month |  | UNHCR, IOM | GoL, UNCT, partners (eg UNRWA)
10 | Assist with any embassy with evacuation plans (at their request) & coordinate issue of travel documents & arrange/establish transit centers to accommodate migrants until time of departure | Within 1 month |  | IOM | Relevant embassies & other partners
| EXTERNAL RELATIONS & PUBLIC INFORMATION |  |  |  |  | EXTERNAL RELATIONSHIPS & PUBLIC INFORMATION
| Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved | Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Revitalise the working group concerned with PI policy, proposals for common messaging, & template Q&As | To be determined |  | All agencies | All agencies | Prepare area-specific PI lines and Q&As for quick response, in accordance with agencies PI policies and the common messaging agreed at national level | To be determined |  | All agencies | All agencies
2 | Develop mass communication capacity, strategy, tools & messages, designed for use in the current emergency but also in case of any heightened crisis | Ongoing | Funds for staff & other resources | UNHCR | UNHCR | Tailor the messages to the area, & communicate systematically with the refugees (at transit sites, community centres & upon registration) on the services they should expect | To be determined |  | UNHCR Area Office | All agencies
3 | Pre-identify a Communication/Reporting Officer, for rapid deployment to any area facing a new emergency | To be determined |  | UNHCR | Other agencies, as appropriate | Prepare to respond to media, by clarification of who is authorised to speak to the press, pre-identification of spokespeople & training if nec. | To be determined |  | UNHCR | Other agencies, as appropriate
| Response Actions | Deadline | New resources required ? | Responsible | Actors involved | Response Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Deplo ypre-identified Communication/Reporting Officer(s) to the affected area(s) | Within 24 hours | Roster of staff | All agencies | All agencies | Call forward Communication/Reporting Officer(s) from national / Beirut level, to support area(s) | Within 48 hours | Roster of staff | All agencies | All agencies
2 | Daily updates issued by PI staff, with information feed from field & sectors through the IMU | Daily, starting ASAP | Inputs from areas & sectors | UNHCR | UNHCR field, sector, & PI staff
3 | Liaise with other agency PI units to prepare & issue a joint press statement / conference in cooperation with GoL | Within 48 hours |  | UNHCR, GoL | All agencies
4 | Initiate joint GoL-UN donor meeting & repeat periodically | Within 1 week |  | GoL, UNHCR | All agencies
| SECURITY OF OPERATIONS (including the physical means of communication) |  |  |  |  | SECURITY OF OPERATIONS (including the physical means of communication)
| Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved | Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Liaise with Lebanese security forces (ISF, LAF) to assess the security situation for refugees, staff and host communities | Ongoing |  | UNDSS | UNDSS, UNIFIL, UNHCR & other agencies' security focal points | Contact local authorities (including security forces) in advance, and arrange an awareness session to ensure they understand IHL and that they are responsible for the safety & security of all humanitarian personnel | To be determined |  | UNHCR, OCHA & ICRC | All agencies
2 | In coordination with the UNDSS & following SMT decisions to establish an internal security plan & SOPs for staff movements & contingency response | Ongoing |  | UNHCR | UNDSS, UNIFIL, UNHCR & other agencies' security focal points | Collect a comprehensive list of satellite telephone numbers in order to set up a satellite 'communication tree' covering each agency/location | To be determined |  | UNHCR Area Office | All agencies
3 | Ensure that the warden system is updated & wardens are properly briefed on the changing environment | Ongoing |  | UNHCR | UNHCR FSU | Establish a clear coordination mechanism between UNHCR, UNRWA, UNIFIL & UNDSS (eg exchange Liaison Officers), and a back-up communications system for support | In process |  | UNHCR Area Office | UNRWA, UNIFIL & UNDSS
4 | Ensure that all staff & partners are briefed on latest security developments | Ongoing |  | UNHCR | UNHCR FSU in coordination with UNDSS & UNIFIL | Agree on a communications & coordination system for rapid passage of security information, to increase the safety of UN & NGO staff in the area | To be determined |  | UNHCR Area Office | Inter-agency group at area level
5 | Seek clarification from GoL on the process NGOs must follow in order to use radio equipment for operations & safety, provided they meet the requirements of the Lebanese security forces | To be determined |  | UNDSS & UNHCR | GoL, all agencies | Review the possibility of allocating an existing radio channel (frequencies) for UN & NGOs, to enable them to communicate for staff safety / operational purposes | To be determined | Additional resources for radios | UNDSS & UNHCR | All agencies
6 | Validate the training & briefing that has gone on, & test the communications 'trees' by implementing a country-wide security drill | To be determined |  | UNDSS | UN Agencies & partners | Determine whether it is possible to share (UN) radios with key (non-UN) counterparts in certain locations to enable remote control response | To be determined | Additional resources for radios | UNDSS & UNHCR | UN Agencies & counterparts (even local authorities)
7 | Assess telecommunication equipment requirements of UN agencies & partners, and place orders for the necessary equipment that is lacking | To be determined |  | UNDSS & UNHCR | UN Agencies & partners
8 | Ensure that the prescribed field security equipment is in place for all locations & staff | To be determined |  | All agencies | All agencies
| Response Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Advise on issues of illegal land occupation by refugees | As necessary |  | UNHCR FSU | UNHCR FSU & Admin
2 | Advise on possible relocation of staff to the safer areas within the country and/or, ultimately, on the evacuation of the international staff | As necessary |  | UNDSS | UNDSS, UNIFIL, UNHCR & other agencies' security focal points
| LOGISTICS |  |  |  |  | LOGISTICS
| Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved | Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Cover the responsibilities of the Logistics Cluster normally led by WFP (i.e. by expanding the TOR of the NFI Sector Working Group | To be determined |  | UNHCR, WFP | All agencies interested in working on common logistics & sharing costs | Amend the TOR of the Area Distribution Working Group, to include logistic issues of common concern | 2013-06-30 |  | UNHCR Area Office | Area Distribution Group members
2 | Inventorize existing stocks of shelter materials, food & NFIs actually physically in country, held by all agencies, to produce combined stock figure & be the basis of a common plan | To be determined |  | All Sector Leads | All agencies | Confirm the stocks of shelter materials, food & NFIs held by all agencies at area level, and map the locations & quantities of these stocks and their availability to respond to a crisis | 2013-06-30 |  | UNHCR Area Office | All agencies
3 | List all 'frame agreements' across all agencies/sectors & ask relevant agencies to check whether they will actually work | To be determined |  | (Proposed) Logistics Working Group | All agencies with 'frame agreements' | Ask all distribution agencies to share their 'frame agreements' - during the distribution coordination meeting | 2013-06-30 |  | UNHCR Area Office | All agencies with 'frame agreements', working through sector working groups
4 | Identify logical hubs across the country for supplies to be stockpiled, & look for common warehousing solutions, in existing facilities or by creating new ones (eg with Rubb Halls) | To be determined |  | (Proposed) Logistics Working Group | All agencies interested in working on common logistics & sharing costs | Map the locations of all significant existing warehouses (including UNRWA, etc) in the area & find locations for new warehouses if possible (eg Rubb Halls) | Ongoing |  | UNHCR Area Office | Area Distribution Group members
5 | Draw upon the scenario planning & mapping work done by UNHCR under the Management, Coordination & Info Management heading, to identify key locations where reserve stockpiles should be established, because they may be cut off in a crisis | To be determined |  | (Proposed) Logistics Working Group | All agencies interested in working on common logistics & sharing costs | Some areas may not be accessible anymore, such as Arsal, Hermel, Masharii Qaa & other potential concentration areas; therefore consider whether to establish contingency stocks (eg of shelter materials) in small local warehouses, engage local partners & make them accountable to respond in a crisis, using these contingency stocks | 2013-06-30 | Local partners, warehouses, funds | UNHCR Area Office | Area Distribution Group members, local authorities, warehouse owners, local NGOs
6 | Analyse the transportation network in Lebanon, for choke points & possible solutions to avoid logistic paralysis in an insecure environment | To be determined |  | (Proposed) Logistics Working Group | All agencies interested in working on common logistics & sharing costs | Establish a monitoring system looking at transportation costs in the area, & keep a consolidated record tracking this (i.e. when the security situation changes) | 2013-06-30 |  | UNHCR Area Office | Area Distribution Group members
7 | Establish protocols for common re-supply from regional humanitarian stockpiles, and drawing upon global suppliers using common procurement agreements | To be determined |  | (Proposed) Logistics Working Group | All agencies interested in working on common logistics & sharing costs | Map out the possible logistics routes in case of road blockage on the main supply route | 2013-06-30 |  | UNHCR Area Office | Area Distribution Group members
| REGISTRATION |  |  |  |  | REGISTRATION
| Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved | Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Develop a database for emergency registration, a border screening methodology, form & database (also in Access?) for systemization of data | In progress |  | UNHCR Registration |  | Share the emergency registration strategy / process with local actors for information purposes | To be determined |  | UNHCR Area Office | GoL (MoSA), UNHCR partners
2 | Prepare a roster of UNHCR staff to cover border monitoring, reception & registration, & prepare existing registration centres to absorb more staff | To be determined |  | UNHCR Registration |  | Train existing Area Registration Centre staff in the emergency screening & registration methodology | To be determined |  | UNHCR Registration | UNHCR Area Office
3 | Negotiate secondment to UNHCR of volunteers, available for deployment on short notice, from the Red Cross, World Vision, Arc en ciel, UNRWA | To be determined |  | UNHCR Registration | Red Cross, World Vision, Arc en ciel, UNRWA | Identify partner staff (incl. from MoSA) for deployment to support emergency screening & registration, & organise training in the methodology / processes | To be determined |  | UNHCR Area Office | GoL (MoSA), UNHCR partners
4 | Develop capacity by training roster staff (UNHCR & partner) in emergency registration | To be determined |  | UNHCR Registration | GoL (MoSA), UNHCR partners | Host & support the training of UNHCR & partner staff rostered for emergency registration | To be determined |  | UNHCR Area Office | GoL (MoSA), UNHCR partners
5 | Request Rubb Halls (up to three) + furniture for the transit centre(s) | To be determined |  | UNHCR Registration | & UNHCR Supply | Identify potential areas for emergency (level 1) registration (eg transit sites, community centres, & sites possible for mobile registration teams) | To be determined |  | UNHCR Area Office | GoL (MoSA), UNHCR partners
6 | Prepare, procure & preposition a contingency stock of registration materials, including family cards, fixing tokens, manifests | To be determined | Funds for materials | UNHCR Registration | & UNHCR Admin | Distribute the contingency stock of registration materials to registration centres at area level | To be determined |  | UNHCR Registration | UNHCR Area Office
7 | Develop mass info (e.g. on the registration process, or visibility material) leaflets & other media for dissemination at borders, transit centre(s) & where needed | To be determined | Funds for materials | UNHCR Protection / Mass Comms |  | Distribute the stock of mass info materials to border crossings, registration & (potential) transit centres at area level | To be determined |  | UNHCR Registration | UNHCR Area Office
8 | Scrutinize mapping of official & unofficial border crossings / make contact with CBOs in those areas | To be determined |  | UNHCR Area Offices | CBOs in areas where groups will cross | Identify & establish contact with CBOs in those areas that can report on groups arriving | To be determined |  | UNHCR Area Office | CBOs in areas where groups will cross
9 | Negotiate with LAF &/or GSO for UNHCR to access border crossings / ensure LAF &/or GSO designates liaison officers to UNHCR | To be determined |  | UNHCR Management | GoL (MoSA, LAF, GSO)
10 | Identify partners to assist in logistics & distribution at transit centre(s) (possibly DRC) | To be determined |  | UNHCR Registration | DRC & other suitable potential partners
11 | Discuss with MSB registration & office work spaces for the camps | To be determined |  | UNHCR Registration | MSB (Sweden, as per global agreement)
12 | Identify partners to provide emergency health care at transit centre(s) (possibly Red Cross) | To be determined |  | Health Sector Lead (UNHCR) | Red Cross & other health actors
13 | Liaise with IOM regarding their preparedness / plan to transfer, accommodate & evacuate TCNs | To be determined |  | IOM | UNHCR
14 | Liaise with UNRWA regarding their preparedness / plan to record, transfer & accommodate PRS | To be determined |  | UNRWA | UNHCR
15 | Identify personal contractor(s) for bus services between transit centre(s) & camps | To be determined |  | UNHCR Admin | & UNHCR Area Offices
16 | Draw up inventory of existing IT equipment that can be deployed to the field and, if necessary, procure 40 laptops for screening & registration | To be determined |  | UNHCR Admin
17 | Identify / allocate vehicles & drivers | To be determined |  | UNHCR Admin | Other partners as necessary
| Response Actions | Deadline | New resources required ? | Responsible | Actors involved | Response Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Revert to emergency registration process (still at individual-level but only basic biodata & specific needs) at all transit sites & registration centres | Within 24 hours | Predefined emergency regisration process | UNHCR |  | Conduct emergency registration: information collected would include basic biodata and specific needs, at designated locations (transit centres) | Within 24 hours | Predefined emergency regisration process | UNHCR
2 | Activate the roster of standby staff & redeploy part of existing registration capacity to predetermined locations suitable for registration (eg transit sites, community centres) if there are significant refugee populations there | Within 24 hours | Roster of staff / list of pre-determined locations | UNHCR | & pre-identified partners (eg ed Cross, World Vision, Arc en ciel, UNRWA) | Mobilise required staffing from national level & redeploy staff from Area Registration Centre to new locations (predetermined), & mobilise partner staffing as available | Within 24 hours | Roster of staff | UNHCR
3 | Mass information mechanism engaged at borders, transit centres & community centres | Within 24 hours | A predefined system & messages | UNHCR | GoL (MoSA), UNHCR partners | Provide mass information regarding registration processes at the border & transit locations | Within 24 hours | A predefined system & messages | UNHCR | GoL (MoSA), UNHCR partners
4 | Depending on size of influx, prepare manifesting or fixing tokens at border points in order to transport refugees to transit sites | Within 48 hours | Transport capacity | UNHCR | GoL (MoSA), UNHCR partners | Utilise basic fixing tokens at border locations in order to transport refugees to transit locations | Within 48 hours | Transport capacity | UNHCR | GoL (MoSA), UNHCR partners
5 | Engage additional local partners from NGOs & the authorities to support reception, registration & identification of the vulnerable | Within 72 hours | Partner staffing | UNHCR | GoL (MoSA), UNHCR partners | Identify vulnerable persons at the entry points & during registration [refer to protection section below] | Within 24 hours |  | UNHCR | GoL (MoSA), UNHCR partners
| PROTECTION |  |  |  |  | PROTECTION
| Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved | Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Develop a strategy, SOP of protection services & the necessary forms for border monitoring & rapid pre-screening for vulnerability (i.e. before registration), & to try to track refugee flows after they have crossed a border | To be determined |  | Protection Sector | Protection Sector members, GoL (MoSA) | Agencies agree to establish a focal point from a single agency (eg DRC, NRC, or UNHCR) to strengthen liaision with officials at Masnaa, Arsal, & other key locations, & additional staff capacity (drawn from all agencies) to monitor official/unofficial crossings | To be determined |  | UNHCR Area Office | Protection Sector members, GoL (MoSA)
2 | Continue to liaise with Lebanese security forces to keep all official border crossing points open & prevent refoulement | Ongoing |  | UNHCR | GoL (MoSA, MoI, LAF, ISF) | Establish a physical presence at Cheba'a' Hasbaya for monitoring, pre-screening, protection, referral & mass communication, & liaise with security forces to keep the crossing open | To be determined |  | UNHCR Area Office | Protection Sector members, GoL
3 | Liaise with GoL (LAF, ISF, MoSA) & UNIFIL to plan & manage a remote response south of the Litani River, in case UNHCR & NGOs have no access | To be determined |  | UNHCR | UNIFIL, GoL (LAF, ISF, MoSA) | Identify, map, make contact with & brief CBOs beyond the Litani River so that they can collect basic bio-data & respond as necessary if UNHCR & NGOs cannnot cross the river | To be determined | Funds for training & 'remote response' | UNHCR Area Office | UNIFIL, GoL (MoSA, LAF, ISF)
4 | Establish a policy, case management process & capacity to handle high risk or sensitive protection cases, including the establishment of 'safe houses' | To be determined |  | Protection Sector | Protection Sector members, GoL (MoSA) | Identify / create 'safe houses' for high risk protection cases / train staff in 'light' case management of such cases | To be determined | Funds for the 'safe houses' / for training | UNHCR Area Office | Protection Sector members, GoL (MoSA)
5 | Create a comprehensive list of contacts with respect to the border monitoring function | To be determined |  | Protection Sector | Protection Sector members, GoL (MoSA) | Identify / prepare contact lists of community focal points for monitoring the areas close to the border / flow points; brief/train the focal points on their activities & our expectations | To be determined | Funds for a small stipend to the FPs / for training | UNHCR Area Office | Protection Sector members, GoL (MoSA)
6 | Discuss with GoL protection issues in a mass influx (treatment, follow-up, detention, etc.) including vulnerable/undocumented TCNs caught in transit or detained | To be determined |  | UNHCR, IOM | Protection Sector members, GoL (MoSA) | Mainstream protection in designing the transit sites (camp/building layouts) / ensure protection is considered in all sectoral meetings (shelter, WASH, etc.) so that vulnerability is reduced not increased by the response | To be determined |  | All Sector Leads | All agencies
7 | Review staffing requirements at national level to provide the field with more support for protection | To be determined |  | UNHCR | Protection Sector members, GoL (MoSA) | Partners confirm number of protection staff per location (hub / district) & idenfity those who could be deployed rapidly to transit sites, community centres, camps, etc. in an emergency | To be determined |  | All agencies | Protection Sector
8 | Create a 'training package' for new UNHCR Protection Staff & appropriate staff from partner agencies | To be determined |  | Protection Sector | Protection Sector members, GoL (MoSA) | Conduct a training session for UNHCR & partner staff in pre-screening & vulnerability identification | To be determined |  | UNHCR Area Office | Protection Sector members, GoL (MoSA)
| Response Actions | Deadline | New resources required ? | Responsible | Actors involved | Response Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Mobilize full-time presence at official / unofficial border points to ensure unhindered & safe entry, the immediate identification of vulnerable persons (including migrants) & the provision of information | Within 24 hours |  | GoL, UNHCR | MoI, MoSA, UNHCR, IOM, select partners | Mobilise monitoring presence at borders / entry points: tasks include identifying vulnerable, disseminating information, referrals to Registration & relevant service providers | Within 24 hours | Staff, mass information material | UNHCR Area Office | MoI, MoSA, UNHCR, select partners
2 | Monitor protection situation / identify protection issues on the ground, including physical safety at transit centres, camps & other locations | Within 24 hours |  | GoL, UNHCR | MoI, MoSA, UNHCR, IOM, select partners | Station multi-sectoral protection focal points from NGOs (child protection, SGBV, PSN) to set up 'protection desks' at transit sites / other locations for monitoring, identification, basic counselling & referral | Within 24 hours | Staff, mass information material | UNHCR Area Office | MoI, MoSA, UNHCR, select partners
3 | Ensure safe transport from border areas to transit sites, camps, other designated areas away from borders | Within 24 hours | Transport capacity | GoL, UNHCR | MoI, MoSA, UNHCR, IOM, select partners | Ensure safe transport from border areas to transit sites, camps, other designated areas away from borders | Within 24 hours | Transport capacity | GoL, UNHCR | MoI, MoSA, UNHCR, select partners
4 | Centralize tracking of refugee movement from entry points within the country, & establish a system to communicate this information rapidly between the areas, to improve their planning & response to major influxes | Within 48 hours |  | UNHCR | UNHCR Area Offices | Utilise border monitoring, pre-screening, & IM capacity to try to trace onward movement, & pass this information to Beirut & the respective area offices | Within 48 hours |  | UNHCR Area Office | MoI, MoSA, UNHCR, select partners
5 | Coordinate with regional partners, embassies & other international partners regarding voluntary returns, possible third-country evacuation, & third-country national repatriation | Within 72 hours |  | GoL, UNHCR, IOM | International partners | IOM will coordinate with embassies the evacuation of TCNs at their request & issue of travel documents for undocumented migrants, plus establish transit centers until their departure | Within 72 hours |  | IOM | Relevant Embassies of TCNs & undocumented migrants
6 | Coordinate relocation of populations in need of relocation, e.g. in areas affected by conflict, or with severe shelter issues - if necessary even establish humanitarian corridors | Within 72 hours | Transport capacity / liaison with military | GoL, UNHCR | MoI, MoSA, UNHCR, select partners
7 | Liaise on a daily basis on with Lebanese security forces in order to address documentation issues, detentions, disseminate / ensure application of guidelines on the quick identification & treatment of persons with special needs (children, women, elderly, sick) | Within 72 hours, then on a daily basis |  | GoL, UNHCR | MoI, MoSA, UNHCR, select partners
| CHILD PROTECTION |  |  |  |  | CHILD PROTECTION
| Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved | Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Identify emergency interim care for unaccompanied minors (UAM) & appropriate sites/locations & partners to provide emergency shelter for children at risk | ongoing |  | UNHCR, UNICEF, GoL (MoSA) | UNRWA, INGOs, select partners | Identify / create emergency interim care for UAM & appropriate sites / locations to provide emergency shelter for children at risk | To be determined | Funds for the emergency shelters | UNICEF, UNHCR Area Office | Child Protection Sector partners, GoL (MoSA)
2 | Define the methodology for Child Protection monitoring, identifying children at risk, tracing, reunification / prepare SOPs, assessment & monitoring forms / disseminate to partners | To be determined |  | UNHCR, UNICEF, GoL (MoSA) | UNRWA, INGOs, select partners | Train staff in the methodology for CP in emergencies & in the use of assessment & monitoring forms | To be determined | Funds for training | UNICEF, UNHCR Area Office | Child Protection Sector partners, GoL (MoSA)
3 | Identify emergency referral pathways of child protection services per 'hub' / disseminate referral pathways to all involved actors & other sectors | To be determined |  | UNHCR, UNICEF, GoL (MoSA) | UNRWA, INGOs, Iselect partners | Train staff & community volunteers in basic PSS / referrals | To be determined | Funds for training | UNICEF, UNHCR Area Office | Child Protection Sector partners, GoL (MoSA)
4 | Prepare & procure contingency stocks of recreation & early childhood development (ECD) kits | To be determined | Funds for procurement of stocks | UNICEF | Child Protection Sector partners, GoL (MoSA) | Establish a contingency stock of recreation & early childhood development (ECD) kits in the area | To be determined | Funds for procurement of stocks | UNICEF, UNHCR Area Office | Child Protection Sector partners, GoL (MoSA)
5 | Develop IEC material with key messages on emergency child protection for awareness raising amongst new arrivals | To be determined |  | UNHCR, UNICEF, GoL (MoSA) | UNRWA, INGOs, select partners | Identify INGOs & local NGOs working with children which can deploy staff to create Child Friendly Spaces (CFS) / update the contact lists of such staff | To be determined | Funds | UNICEF, UNHCR Area Office | Child Protection Sector partners, GoL (MoSA)
| Response Actions | Deadline | New resources required ? | Responsible | Actors involved | Response Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Set up Child protection monitoring at the border entry points to identify UAM / SC / children at risk | Within 48 hours | Trained staff | UNHCR, UNICEF, GoL (MoSA) | UNRWA, INGOs, select partners | Protection monitoring & reporting by trained staff at reception, registration & transit sites, identification of UAM / SC / children at risk | Within 48 hours | Trained staff | UNHCR, UNICEF, MoSA | UNHCR, UNICEF, MoSA
2 | Disseminate IEC materials & conduct awareness raising on child protection concerns (birth registration; parental care; psychosocial support; risk of UXOs; prevention of childhood exploitiation) | Within 48 hours | IEC materials, posters, videos, megaphones | MOSA, UNHCR, UNICEF | MOSA, UNHCR, UNICEF, UNRWA, I/NGOs & civil society | Disseminate IEC materials & conduct awareness raising on child protection concerns | Within 48 hours | Funds | UNICEF, UNHCR Area Office | Child Protection Sector partners, GoL (MoSA)
3 | Conduct psychosocial & recreational activities - in transit sites, & through mobile outreach | Within 72 hours | Recreational & ECD kits | MOSA, UNHCR, UNICEF | MOSA, UNHCR, UNICEF, UNRWA, I/NGOs & civil society | Create Child Friendly Spaces (CFS) in transit sites | Within 72 hours | Funds | UNICEF, UNHCR Area Office | Child Protection Sector partners, GoL (MoSA)
4 | Tracing & family reunification for UAM / SC & referral to alternative care, particularly if in transit sites | Within 72 hours | Trained staff | ICRC, UNHCR, MOSA, UNICEF | ICRC; UNHCR; UNICEF; Save the Children International | Tracing & family reunification for UAM / SC & referral to alternative care, particularly if in transit sites | Within 72 hours | Trained staff | UNICEF | GoL (MoSA), UNICEF, UNHCR, ICRC, Save the Children International
5 | Temporary emergency shelter/child safe houses for UAM/children at risk | Within 72 hours | Child Safe Houses | MOSA, UNHCR, UNICEF | MOSA, UNHCR, UNICEF, UNRWA, I/NGOs & civil society | Implement the emergency interim care arrangements for UAM & appropriate sites/locations, to provide emergency shelter for children at risk | Within 72 hours | Funds for the emergency shelters | UNICEF, UNHCR Area Office | Child Protection Sector partners, GoL (MoSA)
6 | Case management of children at risk (including child recruitment, physical & sexual violence/exploitation, child trafficking) | Within 72 hours |  | MOSA, UNHCR, UNICEF | MOSA, UNHCR, UNICEF, UNRWA, INGOs
| PREVENTION & RESPONSE TO SEXUAL & GENDER BASED VIOLENCE (SGBV) |  |  |  |  | PREVENTION & RESPONSE TO SEXUAL & GENDER BASED VIOLENCE (SGBV)
| Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved | Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Update contact information of SGBV-TF members including GoL counterparts & chairs of field SGBV coordination mechanisms | To be determined |  | SGBV-TF Coordinator | GoL (MoSA), UNICEF, UNFPA, UNHCR, select partners | Update contact information of faith-based organisations, refugee FPs, women's & youth groups, SDCs & UPEL staff for info dissemination | To be determined |  | SGBV field WGs | GoL (MoSA), UNICEF, UNFPA, UNHCR, ICRC, select partners
2 | Order & distribute a stock of PEP Kits to the PHCs & hospitals vetted for inclusion in the referral pathways | To be determined | Funds | UNFPA | SGBV-TF partners | Monitor PHC & hospitals identified to deliver clinical management of SV to ensure personnel & stock remain up to the standard | To be determined | PEP Kits | UNFPA | SGBV field WGs
3 | Continue ongoing training of medical personnel on clinical management of sexual violence | To be determined |  | SGBV-TF Coordinator | UNFPA, UNHCR, IMC, through SGBV & RH-TF | Provide induction on SGBV prevention / response to other sectors (including non-medical staff in PHC, hygiene promotors, frontline workers, etc.) | To be determined | Funds | SGBV field WGs | UNHCR, UNICEF, MoSA
4 | Disseminate minimum standards on the content / delivery of the Dignity Kit & review the sanitary items provided through the WASH Sector | To be determined |  | SGBV-TF Coordinator | GoL (MoSA), UNICEF, UNFPA, UNHCR, ICRC, select partners | Map the stocks of Dignity Kits & sanitary items held at area level, & pre-position more if deemed insufficient | To be determined | Funds | SGBV field WGs | UNHCR, UNICEF, MoSA
5 | Advocate that each case management agency has clear protocols on data security in case its personnel are evacuated | To be determined |  | SGBV-TF Coordinator | SGBV-TF partners | Develop internal protocols to continue managing data & protecting confidentiality, including data security, in case personnel are evacuated | To be determined | PEP Kits | UNFPA | SGBV field WGs
6 | Finalize key messages & IEC/visuals on the prevention of SGBV | To be determined |  | SGBV-TF Coordinator | SGBV-TF partners | Disseminate key messages & IEC to community / train social workers in emergency response | To be determined |  | SGBV field WGs | UNHCR, UNICEF, MoSA
7 | Disseminate to members SOPs, safety audit templates & emergency GBVIMS intake forms | To be determined |  | SGBV-TF Coordinator | GoL (MoSA), UNICEF, UNFPA, UNHCR, ICRC, select partners | Disseminate repertoires of services & referral pathways with contact of lead case management agencies to other agencies / frontline workers | To be determined |  | SGBV field WGs | UNHCR, UNICEF, MoSA
8 | Translate the Protection from Sexual & Exploitation Abuse (PSEA) module into Arabic | To be determined |  | SGBV-TF Coordinator | SGBV-TF partners | Continue to train staff in PSEA | To be determined |  | PSEA Area Focal Points | SGBV field WGs
| Response Actions | Deadline | New resources required ? | Responsible | Actors involved | Response Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Liase with other sector lead agencies to mitigate risks / ensure SGBV prevention & response is integrated into their own response | On Day 1 |  | UNHCR, UNICEF | SGBV-TF partners | Increase mobile intervention to strenthen access to psycho-social / health services including set up of temporary safe spaces, esp. in transit sites | Within 72 hours | Trained staff | UNHCR, UNICEF | SGBV-TF partners
2 | Ensure SGBV is integrated into any emergency protection monitoring & that the right expertise is available to join inter-sectoral assessment | Within 72 hours |  | UNHCR, UNICEF | SGBV-TF partners | Identify more options for temporary shelter arrangements for women & girls at risk / SGBV survivors | Within 72 hours | Trained staff | UNHCR, UNICEF | SGBV-TF partners
| SHELTER |  |  |  |  | SHELTER
| Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved | Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Agree in advance on shelter vulnerability criteria; then create & use a standardised assessment approach | To be determined |  | Shelter, Protection & WASH Sectors | UNHCR, GoL (MoSA), Shelter & WASH Sector partners | Apply the standardised assessment approach & form to assess vulnerability in the area; then respond accordingly | 2013-06-30 |  | UNHCR Area Office | UNHCR, Shelter Sector partners
2 | Shelter options / capacity assessment & mapping: identify, map, and rehabilitate all buildings with potential as possible transit sites or collective shelters, including churches,mosques, schools, abandoned buildings, etc. | To be determined |  | Shelter & WASH Sectors, GoL (MoSA) | UNHCR, GoL (MoSA), Shelter & WASH Sector partners | Divide the area into different localities & agree upon only 1 responsible agency per locality, for consistent coordination with local actors, information sharing with municipalities & communities, for maintaining a contact list of local stakeholders & for mapping all potential shelters | 2013-06-30 |  | UNHCR Area Office | UNHCR, GoL (MoSA), Shelter & WASH Sector partners (eg NRC, DRC, SCI, Medair, GVC, HI, CISP, SHEILD)
3 | Open space assessment': identify, assess & plan the layout of all possible sites/locations were refugees might stay in transit sites or camps, including at road sides, on unoccupied land, agricultural land, etc | To be determined |  | Shelter & WASH Sectors, GoL (MoSA) | UNHCR, GoL (MoSA), Shelter & WASH Sector partners | In addition to any transit sites already identified, identify more sites especially where high influx is anticipated | 2013-06-30 |  | UNHCR Area Office | UNHCR, GoL (MoSA), Shelter & WASH Sector partners, local NGOs, municipalities
4 | Map existing stock levels of building 'sealing-off' kits available with all actors across all areas, & increase the stocks | To be determined |  | UNHCR | UNHCR, Shelter Sector partners | Increase the stock of 'sealing-off' kits in the area, to sufficient for 5,000 HU's &/or for 3 months utilisation of kits at the current rate | 2013-06-30 |  | UNHCR Area Office | UNHCR, Shelter Sector partners (eg NRC, DRC, SCI, Medair, GVC, HI, CISP, SHEILD)
5 | Assess the stock of family tents &/or shelter boxes (T-shelters) & increase it to sufficient for at least 30,000 HH (5,000 in each of the 4 areas + 10,000 as a strategic reserve at national level) | To be determined |  | UNHCR | UNHCR, Shelter Sector partners | Preposition family tents &/or T-shelters sufficient for 5,000 families in each of the 4 areas; coordinate among actors for their storage | 2013-06-30 |  | UNHCR Area Office | UNHCR, Shelter Sector partners
| Response Actions | Deadline | New resources required ? | Responsible | Actors involved | Response Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Utilise agreed vulnerability criteria in order to radically prioritise most vulnerable for provision of shelter | On Day 1 |  | UNHCR | UNHCR, Shelter Sector partners | In summer, coordinate with NFI Sector partners for distribution of blankets for outdoor sleeping; in winter allow people to shelter in mosques, churches, schools etc. | On Day 1 |  | UNHCR Area Office | UNHCR, Shelter Sector partners
2 | Open the new 'transit sites' at predetermined locations & extend existing ones to double their planned size if possible | Within 24 hours |  | UNHCR, GoL (MoSA) | UNHCR, GoL (MoSA), Shelter & WASH Sector partners | Extend any existing 'transit sites' / open new sites where pre-identified & pre-planned | Within 24 hours |  | UNHCR Area Office | UNHCR, GoL (MoSA), Shelter & WASH Sector partners, local NGOs, municipalities
3 | Initiate an immediate rapid assessment of the locations of families in transit | Within 72 hours | Volunteers | UNHCR | UNHCR, Shelter Sector partners | Carry out immediate assessment of location of families in transit sites | Within 72 hours | Volunteers | UNHCR Area Office | UNHCR, Shelter Sector partners
| WASH |  |  |  |  | WASH
| Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved | Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | In cooperation with Shelter Sector, identify options / locations to accommodate a mass influx, including sites for potential collective centres, transit sites & 'camps' | To be determined |  | Shelter & WASH Sectors, GoL (MoSA) | UNHCR, GoL (MoSA), Shelter & WASH Sector partners | In accordance with the division of the area into different localities (as for SHELTER), assign responsibility in that location also for WASH interventions to the same unique agency | 2013-06-30 |  | UNHCR Area Office | UNHCR, GoL (MoSA), Shelter & WASH Sector partners
2 | Review & update lists of current stocks & available capacity for critical rapid response (eg water tankers) | To be determined |  | UNHCR, UNICEF | WASH Sector partners | Review & update lists of current stocks at area level | 2013-06-30 |  | UNHCR, UNICEF | WASH Sector partners
3 | Review staffing requirements & support mechanisms against current capacity | To be determined |  | UNHCR, UNICEF | WASH Sector partners | Review staffing requirements & support mechanisms against current capacity at area level | 2013-06-30 |  | UNHCR, UNICEF | WASH Sector partners
4 | Pre-position critical WASH contingency materials for response at pre-identified key locations including potential transit sites | To be determined | WASH contingency materials | UNHCR, UNICEF | WASH Sector partners | Pre-position critical WASH contingency materials (eg for water storage & purification , garbage containers) at key locations in the area | 2013-06-30 | WASH contingency materials | UNHCR, UNICEF | WASH Sector partners
| Response Actions | Deadline | New resources required ? | Responsible | Actors involved | Response Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Rapid needs assessment particularly of informal tented settlements & potential transit sites that have not already been assessed & planned | Within 24 hours | Predefined assessment tool (form) | UNHCR, UNICEF, GoL | I/NGO partners, Red Cross, Municipalities, water establishments | Rapid needs assessment particularly of informal tented settlements & potential transit sites that have not already been assessed & planned | Within 24 hours | Predefined assessment tool (form) | UNHCR Area Office, UNICEF | I/NGO partners, Red Cross, Municipalities, water establishments
2 | Hygiene promotion / awareness raising | Within 48 hours | IEC materials | UNHCR, UNICEF, GoL | I/NGO partners, Red Cross, Municipalities, water establishments | Hygiene promotion / awareness raising | Within 48 hours | IEC materials | UNHCR Area Office, UNICEF | I/NGO partners, Red Cross, Municipalities, water establishments
3 | Provision of water to all main sites through connection to existing network / water trucking | Within 48 hours | Pipes, fittings, tools / water tankers | UNHCR, UNICEF, GoL | I/NGO partners, Red Cross, Municipalities, water establishments | Provision of water to all main sites through connection to existing network / water trucking | Within 48 hours | Pipes, fittings, tools / water tankers | UNHCR Area Office, UNICEF | I/NGO partners, Red Cross, Municipalities, water establishments
4 | Set up water storage facilities at all main sites | Within 48 hours | Tanks (bladder, T tank) | UNHCR, UNICEF, GoL | I/NGO partners, Red Cross, Municipalities, water establishments | Set up water storage facilities at all main sites | Within 48 hours | Tanks (bladder, T tank) | UNHCR Area Office, UNICEF | I/NGO partners, Red Cross, Municipalities, water establishments
5 | Mass water treatment (chlorination) | Within 48 hours | HTH, bucket, sets of scales | UNHCR, UNICEF, GoL | I/NGO partners, Red Cross, Municipalities, water establishments | Mass water treatment (chlorination) | Within 48 hours | HTH, bucket, sets of scales | UNHCR Area Office, UNICEF | I/NGO partners, Red Cross, Municipalities, water establishments
6 | Distribute aquatabs / water purification filters | Within 48 hours | Aquatabs / filters | UNHCR, UNICEF, GoL | I/NGO partners, Red Cross, Municipalities, water establishments | Distribute aquatabs / water purification filters | Within 48 hours | Aquatabs / filters | UNHCR Area Office, UNICEF | I/NGO partners, Red Cross, Municipalities, water establishments
7 | Test water quality | Within 48 hours | Pool tester / DPD1 / Phenol red | UNHCR, UNICEF, GoL | I/NGO partners, Red Cross, Municipalities, water establishments | Test water quality | Within 48 hours | Pool tester / DPD1 / Phenol red | UNHCR Area Office, UNICEF | I/NGO partners, Red Cross, Municipalities, water establishments
8 | Distribute hygiene kits (including water containers or buckets) & baby kits to those with infants | Within 48 hours | Hygiene kits & baby kits | UNHCR, UNICEF, GoL | I/NGO partners, Red Cross, Municipalities, water establishments | Distribute hygiene kits (including water containers or buckets) & baby kits to those with infants | Within 48 hours | Hygiene kits & baby kits | UNHCR Area Office, UNICEF | I/NGO partners, Red Cross, Municipalities, water establishments
9 | Construct emergency latrines (using pre-fabricated sanitation units) / defecation fields if no alternative | Within 72 hours | Pre-fab units, tools, slabs, tarpaulins, poles, nails | UNHCR, UNICEF, GoL | I/NGO partners, Red Cross, Municipalities, water establishments | Construct emergency latrines (using pre-fabricated sanitation units) / defecation fields if no alternative | Within 72 hours | Pre-fab units, tools, slabs, tarpaulins, poles, nails | UNHCR Area Office, UNICEF | I/NGO partners, Red Cross, Municipalities, water establishments
10 | Set up water distribution tapstands including pipe networks | Within 1 week | Tapstands, pipes, fittings, tools | UNHCR, UNICEF, GoL | I/NGO partners, Red Cross, Municipalities, water establishments | Set up water distribution tapstands including pipe networks | Within 1 week | Tapstands, pipes, fittings, tools | UNHCR Area Office, UNICEF | I/NGO partners, Red Cross, Municipalities, water establishments
11 | Construct emergency showers | Within 1 week | Tarpaulin, poles, nails, tools, gravel | UNHCR, UNICEF, GoL | I/NGO partners, Red Cross, Municipalities, water establishments | Construct emergency showers | Within 1 week | Tarpaulin, poles, nails, tools, gravel | UNHCR Area Office, UNICEF | I/NGO partners, Red Cross, Municipalities, water establishments
12 | Undertake drainage works | Within 1 week | Tools | UNHCR, UNICEF, GoL | I/NGO partners, Red Cross, Municipalities, water establishments | Undertake drainage works | Within 1 week | Tools | UNHCR Area Office, UNICEF | I/NGO partners, Red Cross, Municipalities, water establishments
13 | Install solid waste bins & arrange garbage disposal | Within 1 week | Solid waste bins | UNHCR, UNICEF, GoL | I/NGO partners, Red Cross, Municipalities, water establishments | Install solid waste bins & arrange garbage disposal | Within 1 week | Solid waste bins | UNHCR Area Office, UNICEF | I/NGO partners, Red Cross, Municipalities, water establishments
14 | Distribute latrine / camp cleaning kits | Within 2 weeks | Tools | UNHCR, UNICEF, GoL | I/NGO partners, Red Cross, Municipalities, water establishments | Distribute latrine / camp cleaning kits | Within 2 weeks | Tools | UNHCR Area Office, UNICEF | I/NGO partners, Red Cross, Municipalities, water establishments
| FOOD SECURITY & NUTRITION |  |  |  |  | FOOD SECURITY & NUTRITION
| Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved | Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Maintain WFP's comprehensive market monitoring system, to track price increases/inflation, taking a baseline just before the influx | Already in place |  | WFP | WFP & its IPs | Assess & map Food & Nutrition Sector partner capacity & stocks in the area | To be determined |  | UNHCR Area Office, WFP | Food Security & Nutrition partners
2 | Confirm feasibility of scaling-up production, & make standby agreements for a total of 6,000 parcels/week | Done by 01/07/2013 |  | WFP | Food Security & Nutrition partners, WFP's suppliers | Maintain a fixed level of contingency stocks at 7,500 parcels (50% of the required quantity) at all times | Jul-Dec |  | WFP | Food Security & Nutrition partners
3 | Predefine simple targeting criteria for a mass displacement, based on current Vulnerability Assessment (profiling) in order to target 'on-arrival' food parcels | To be determined |  | WFP | WFP, UNHCR, ACTED & partners in the current profiling exercise | Drawing upon the plans of the Shelter & WASH Sector working groups, plan distribution points at or near to likely sites for collective centres, transit sites & 'camps' | To be determined |  | UNHCR Area Office, WFP | Food Security & Nutrition partners
4 | Prepare for the possibility of using one-off food vouchers for new arrivals, particularly in urban areas, by estimating likely volume & locations | To be determined | Substantial funding would be required | WFP | Food Security & Nutrition partners, WFP's supplier of E-vouchers, shops
5 | Warn donors that a mass influx of population could result in at least short term food price inflation, so the purchasing power of the food vouchers may reduce at the same time as more will be needed for the greater numbers | To be determined | Resources requirement will be substantially increased | WFP | WFP, Food Security & Nutrition partners, & their donors
| Response Actions | Deadline | New resources required ? | Responsible | Actors involved | Response Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Change operational approach by prioritising in-kind food distributions at informal tented settlements, any formal camps, transit sites, collective centres, etc., having already mapped out their likely locations & planned the associated distribution points | On Day 1 |  | WFP | WFP & its IPs | Closely coordinate the Shelter, WASH, Food & NFI response at area level so that the assistance provided is coherent, consistent, & does not create unrealistic expectations in refugees | From Day 1 |  | UNHCR Area Office, UNICEF, WFP | Shelter, WASH, Food Security & Nutrition, & NFI Sector working group partners
2 | Utilise the simplified targeting criteria for mass displacement, to quickly identify other vulnerable &/or needy families, not living in an ITS, camp, transit site or collective centre | Within 48 hours |  | WFP | WFP & its IPs | Distribute food parcels or E-vouchers as appropriate, to refugees not living in 'camp' type situations, & continue assisting the registered, if funds permit | Within 48 hours |  | WFP | WFP & its IPs, & their donors
3 | Monitor for malnutrition - although no reason for concern as yet, set up a system for randomised & statistical pre-assistance (baseline) interviews & PDM HH interviews (including food consumption score, coping strategies & malnutrition indicators) | Within 1 month |  | WFP | WFP & its IPs | Support malnutrition monitoring mechanism, as needed | Within 1 month |  | WFP | WFP & its IPs
| NON-FOOD ITEMS (NFI), including CORE RELIEF ITEMS (CRI) |  |  |  |  | NON-FOOD ITEMS (NFI), including CORE RELIEF ITEMS (CRI)
| Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved | Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Standardize the NFI kit contents & specifications of individual items, provided by all agencies | Ongoing |  | UNHCR | NFI Sector Working Group | Assess & map NFI Sector working group partner capacity & stocks in the area, based on the quantity of standardized kits available | To be determined |  | UNHCR Area Office | NFI Sector working group partners
2 | Predefine simple targeting criteria for a mass displacement, based on current Vulnerability Assessment (profiling) in order to target 'NFI New Arrival' Kits | To be determined |  | NFI Sector Working Group | Agencies involved in the provision of the NFI New Arrival Kit, including UNHCR | Drawing upon the plans of the Shelter, WASH & Food Security Sector working groups, plan distribution points at or near to likely sites for collective centres, transit sites & 'camps' | To be determined |  | UNHCR Area Office, UNICEF, WFP | Shelter, WASH, Food Security & Nutrition, & NFI Sector working group partners
3 | Warn donors that contingency stocks requested under RRP5 (NFIs for 44,000 HH / 220,000 pax) by all agencies will be quickly exhausted & new funding will be needed, as well as a change in attitude to accept the creation of reserve stocks at strategic level | To be determined | Resources requirement will be substantially increased | NFI Sector Working Group | All agencies & their donors | Establish a Contingency Reserve Stock of all NFIs actually within each area, sufficent for 10,000 HH, & seek funds for the creation of more reserve stocks | To be determined | Funds | UNHCR Area Office | NFI Sector working group partners
| Response Actions | Deadline | New resources required ? | Responsible | Actors involved | Response Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Change operational approach by prioritising in-kind NFI distributions at informal tented settlements, any formal camps, transit sites, collective centres, etc., having already mapped out their likely locations & planned the associated distribution points | On Day 1 |  | UNHCR | UNHCR, GoL, NFI Sector working group partners | Closely coordinate the Shelter, WASH, Food & NFI response at area level so that the assistance provided is coherent, consistent, & does not create unrealistic expectations in refugees | From Day 1 |  | UNHCR Area Office, UNICEF, WFP | Shelter, WASH, Food Security & Nutrition, & NFI Sector working group partners
2 | Utilise the simplified targeting criteria for mass displacement, to quickly identify other vulnerable &/or needy families, not living in an ITS, camp, transit site or collective centre | Within 48 hours |  | UNHCR | NFI Sector working group partners | Distribute NFIs as needed, to refugees not living in 'camp' type situations | Within 48 hours |  | UNHCR Area Office | NFI Sector working group partners
| HEALTH |  |  |  |  | HEALTH
| Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved | Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Map out current presence & capacity of partners at national level, set up info sharing / coordination agreements & a matrix of services dividing roles according to comparative advantage | To be determined |  | UNHCR, WHO, GoL (MoPH, MoSA) | Health Sector partners, ICRC | Map out current presence & capacity of partners at area level, set up info sharing / coordination agreements & a matrix of services dividing roles according to comparative advantage | To be determined | Staff training & time | UNHCR Area Office, WHO | Health Sector partners, ICRC
2 | Define key medical items (medicines, supplies & equipment) for the contingency response, & inventorize the stocks held at national level | To be determined |  | UNHCR, WHO, GoL (MoPH, MoSA) | Health Sector partners | Define key medical items (medicines, supplies & equipment) for the contingency response, & inventorize the stocks items held at area level | To be determined |  | UNHCR Area Office, WHO | Health Sector partners
3 | Map out existing Primary Health Care (PHC) & Secondary Health Care (SHC) facilities at country level | To be determined |  | UNHCR, WHO, GoL (MoPH, MoSA) | Health Sector partners | Map out existing PHC & SHC facilities at area level | To be determined | Staff training & time | UNHCR Area Office, WHO | Health Sector partners
4 | In consultation with GoL (MoPH) assess the risk of a major epidemic (Scenario 3), & ensure that the response to it is properly planned by all sectors | To be determined |  | UNHCR, WHO, GoL (MoPH) | Health Sector partners | Ensure that the response to a major epidemic outbreak, exacerbated by the refugee emergency & complicated by the refugee presence, is properly planned by all area offices | To be determined |  | UNHCR Area Office, WHO | Health Sector partners
| Response Actions | Deadline | New resources required ? | Responsible | Actors involved | Response Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Establish teams at entry points (legal & illegal) with security coverage at critical locations, to conduct triage (eg identifying & stabilising the injured or seriously ill) epidemic control / health monitoring / rapid assessment | Within 24 hours | ER medical personnel, equipment, medicine, facilities, transport | UNHCR, WHO, GoL (MoPH, MoSA) | Health Sector partners, ICRC, LRC, MdM, MSF, Humedica | Establish teams at entry points (legal & illegal) with security coverage at critical locations, to conduct triage (eg identifying & stabilising the injured or seriously ill) epidemic control / health monitoring / rapid assessment | Within 24 hours | ER medical personnel, equipment & medicine | UNHCR Area Office, WHO | Health Sector partners, ICRC, LRC, MdM, MSF
2 | Referral system for stabilised cases, on to the network of existing PHC & SHC, & extend their opening hours | Within 24 hours | Transport | UNHCR, LRC | Health Sector partners, ICRC, MdM, MSF | Referral system to the network of existing PHC & SHC, & extend their opening hours | Within 24 hours | Transport | UNHCR Area Office, LRC | Health Sector partners, ICRC, MdM, MSF
3 | Monitor & control health of population, particularly epidemic monitoring & control | Within 48 hours | Trained personnel, reporting, vaccines, medicines | UNHCR, WHO, UNICEF, GoL (MoPH) | Health Sector partners | Monitor & control health of population, particularly epidemic monitoring & control | Within 48 hours | Trained personnel, reporting, vaccines, medicines | UNHCR, WHO, UNICEF, GoL (MoPH) | Health Sector partners
4 | Mobile clinics/outposts to deliver emergency response & PHC at new sites or personnel, equipment & medicines to increase capacity at existing facilities | Within 48 hours | ER medical personnel, equipment, medicine, transport | UNHCR, WHO, GoL (MoPH) | Health Sector partners, ICRC, MdM, MSF, UNICEF, UNFPA | Mobile clinics/outposts to deliver emergency response & PHC at new sites or personnel, equipment & medicines to increase capacity at existing facilities | Within 48 hours | ER medical personnel, equipment, medicine, transport | UNHCR Area Office, WHO | Health Sector partners, ICRC, MdM, MSF, UNICEF, UNFPA, Amel, Humedica
5 | Establish staffed, equipped & properly resourced field hospitals | Within 72 hours | Field hospitals, space, personnel & resources | MSF, IMC, GoL (MoPH) | Health Sector partners, ICRC, IMC, MdM, MSF, UNICEF | Establish staffed, equipped & properly resourced field hospitals | 3 days | Field deployable hospital kit, Medical personnel, space | MSF, IMC | ICRC; MSF; IMC, UNCHR, WHO, UNICEF, MOPH
6 | Health education & outreach to the population | Within 1 month | Trained personnel | UNHCR (health & mass comms specialist) | Health partners active in PHC provision | Health education & outreach to the population | Within 1 month | Trained personnel | UNHCR Area Office, WHO, UNICEF, MoPH | Health partners active in PHC provision
| EDUCATION |  |  |  |  | EDUCATION
| Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved | Preparedness Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Drawing upon Shelter's plan of likely locations, assess & map tented settlements with regard to access to education, number of children of school age, a proper studying environment & the availability of space for tented schools [under Scenario 1a - mass but gradual refugee influx, & where physically possible under Scenario 2 - mass IDPs] | To be determined | Tents procured & prepositioned, permission from GoL / local authority | GoL (MEHE), UNICEF, UNHCR | Education Sector partners | Support the national Education Sector WG plan to set up temporary schools in tents at likely sites for collective centres, transit sites & 'camps' through site assessment, planning & prepositioning stocks in the area | To be determined | Tents procured & prepositioned, permission from GoL / local authority | GoL (MEHE), UNICEF, UNHCR Area Office | Education Sector partners
2 | If the mass influx is very rapid & very large, & particularly if it occurs in the winter, then as a last resort schools may have to be used for shelter. In this case the Education Sector must make its own contingency plan to get all refugee Syrian children & all displaced Lebanese children back to school within 3-6 months, if necessary by stretching existing school capacity (larger classes, double shifts, etc.), also covering basic monitoring of the children during the period when schooling is suspended | To be determined | To be determined based on Education Sector Contingency Plan | GoL (MEHE), UNICEF, UNHCR | Education Sector partners | In order to be prepared for a mass but gradual refugee influx, and for a more rapid mass influx, when schooling might have to be suspended temporarily, map & divide the area into school-clusters & designate a focal point (i.e. 1 IP) per school-cluster to faciliate response & info flow | To be determined | To be determined based on Education Sector Contingency Plan | GoL (MEHE), UNICEF, UNHCR Area Office | Education Sector partners
3 | Raise awareness, provide vaccines, hygiene kits, medication, shampoo to all schools & tented settlements | To be determined | Health personnel, vaccines, training | GoL (MEHE, MoPH), UNICEF, UNHCR | Education & Heatlh Sector partners | Support the awareness raising & practical measures to combat lice, scabies & other infectious conditions | To be determined | Health personnel, vaccines, training | GoL (MEHE, MoPH), UNICEF, UNHCR Area Office | Education & Heatlh Sector partners
4 | Conduct a Joint Education Capacity & Needs Assessment, looking at all public & private schools across the country | To be determined | Personnel, logistic support | GoL (MEHE), UNICEF, UNESCO, UNHCR | Education Sector partners | Support the Joint Education Capacity & Needs Assessment by mapping the school situation, locations & capacity, across the area | To be determined | Personnel, logistic support | GoL (MEHE), UNICEF, UNESCO, UNHCR Area Office | Education Sector partners
5 | Plan how to set up child-friendly spaces in collective centres, transit sites, ITS & other forms of 'camps', where some educational activities can continue | To be determined | Funds for capacity building, facilities & supplies | GoL (MEHE), UNICEF, UNHCR | Education Sector partners | Map locations, centres, partners who are capable (& build the capacity of other partners) to do remedial classes & ALPS for newcomers & children outside schools | To be determined | Funds for capacity building, facilities & supplies | GoL (MEHE), UNICEF, UNHCR Area Office | Education Sector partners
6 | Map availability of incentive teachers (include question in ITS & other similar assessments) & provide them with training, facilities & supplies | To be determined | Funds for training, facilities & supplies | GoL (MEHE), UNICEF, UNHCR | Education Sector partners | Support mapping of availability of incentive teachers & providing them with appropriate training, facilities & supplies | To be determined | Funds for training, facilities & supplies | GoL (MEHE), UNICEF, UNHCR Area Office | Education Sector partners, Balamand University, IQRAA
7 | Preposition 'Schools-in-a-Box', Recreational Kits & school tents/prefabs at key locations across the country | To be determined | Supplies & tents procured & prepositioned | GoL (MEHE), UNICEF, UNHCR | Education Sector partners | Map suitable warehouses in order to preposition 'Schools-in-a-Box', recreational kits and school tents/prefabs, & perform basic rehabilitation (1 month) | To be determined | Warehouses, funds, logistic support | GoL (MEHE), UNICEF, UNHCR | Education Sector partners
8 | Procure additional education supplies (books, stationery, bags, uniforms) sufficient for 1 month's mass influx (e.g. ~150,000 school age children) | To be determined |  | GoL (MEHE), UNICEF, UNHCR | Education Sector partners | Pre-position education supplies in each area | To be determined | Warehouses, funds | GoL (MEHE), UNICEF, UNHCR Area Office | Education Sector partners
9 | Confirm with MEHE & communicate widely the curriculum defined for Syrian refugee children in Lebanon | To be determined |  | UNICEF, UNHCR | GoL (MEHE)
10 | Obtain authorisation from GoL (MEHE) to allow educational activities to take place in any form of tented settlement | To be determined |  | UNICEF, UNHCR | GoL (MEHE)
11 | Prepare existing schools to accommodate a mass influx by provision of teacher training, enhanced facilities, school supplies, & rehabilitation if necessary & possible | To be determined | Funds for training, facilities, supplies & rehabilitation | GoL (MEHE), UNICEF, UNHCR | UNICEF, UNHCR
12 | Reinforce MEHE through deployment of an Emergency Education Team (including specialists & IM) | Ongoing |  | UNICEF, UNHCR | GoL (MEHE)
| Response Actions | Deadline | New resources required ? | Responsible | Actors involved | Response Actions | Deadline | New resources required ? | Responsible | Actors involved
1 | Include Education in any rapid inter-sectoral assessment | Whenever it occurs |  | UNICEF, UNHCR | Education Sector partners, GoL (MEHE) | Include Education in any rapid inter-sectoral assessment | Whenever it occurs |  | UNICEF, UNHCR Area Office | Education Sector partners, GoL (MEHE)
2 | To guide the response, verify that data on the education situation is still collected, consolidated, analysed & disseminated, & perform M&E on a regular basis | Within 1 week |  | GoL (MEHE), UNICEF, UNHCR | Education Sector partners | To guide the response, verify that data on the education situation is still collected, consolidated, analysed & disseminated, & perform M&E on a regular basis | Within 1 week |  | GoL (MEHE), UNICEF, UNHCR | Education Sector partners
3 | Initiate Two-Shift schooling country-wide including in private schools, ensuring that fees, equipment & running costs are covered | Within 2 weeks | Funds for additional teachers, supplies | GoL (MEHE) | Education Sector partners | Initiate Two-Shift schooling country-wide including in private schools | Within 2 weeks | Funds for additional teachers, supplies | GoL (MEHE) | Education Sector partners
4 | Set up child-friendly spaces in collective centres, transit sites, ITS & other forms of 'camps', where some educational activities can continue | Within 1 month | Funds for capacity building, facilities & supplies | GoL (MEHE), UNICEF, UNHCR | Education Sector partners | Initiate remedial classes & ALPS for newcomers & children outside schools | Within 1 month | Funds for capacity building, facilities & supplies | GoL (MEHE), UNICEF, UNHCR Area Office | Education Sector partners
5 | In a mass but gradual refugee influx, establish tented schools for the refugees in collective centres, transit sites & 'camps', also inside existing school facilities to expand capacity | Within 1 month | Tents, supplies, permission from GoL / local authority | GoL (MEHE), UNICEF, UNHCR | Education Sector partners | Support the establishment of temporary schools in tents at collective centres, transit sites & 'camps' | Within 1 month | Tents, supplies, permission from GoL / local authority | GoL (MEHE), UNICEF, UNHCR Area Office | Education Sector partners
6 | In a more rapid & overwhelming mass influx, & only if ncessary as a last resort, use schools for shelter but initiate the Education Sector's contingency plan to get all refugee Syrian children & Lebanese children back to school within 3-6 months | Within 1 month | To be determined based on Education Sector Contingency Plan | GoL (MEHE), UNICEF, UNHCR | Education Sector partners | Support implementation of the Education Sector's contingency plan to get all refugee Syrian children & Lebanese children back to school within 3-6 months | Within 3-6 months | To be determined based on Education Sector Contingency Plan | GoL (MEHE), UNICEF, UNHCR Area Office | Education Sector partners
7 | Intensify community outreach to ensure enrolment | Within 2 months | Funds for outreach | GoL (MEHE, MoSA), UNICEF, UNHCR | Education Sector partners
8 | Advertise for, select & recruit additional teachers as necessary | Within 2 months | Funds for teachers | GoL (MEHE), UNICEF, UNHCR | Education Sector partners

## National & Area Task List only
STRATEGY at NATIONAL LEVEL |  |  |  | And at AREA LEVEL
| Management, Coordination, Info Management & Fundraising |  |  | Bekaa, North, South, Beirut & Mt Lebanon
| Preparedness Actions (National) | Deadline | Responsible | Preparedness Actions (Area)
1 | Determine & agree any special additional coordination mechanisms to manage response to a mass influx, particularly with key actors in GoL (MoI, MoD, LAF, ISF) | To be determined | GoL (MoSA) & UNHCR | Agree coordination modalities with local actors, authorities and NGOs, political parties (& UNIFIL), for 'remote control response' in certain dangerous locations
2 | Map possible displacement scenarios, liaise with GoL to be prepared in case of restricted humanitarian access | To be determined | UNHCR | Hold simulation exercise for an influx into the respective area with a scenario involving a combination of difficult factors, & ensure GoL involvement
3 | Agree on early warning signals that will trigger deployment of resources from outside Lebanon to agencies operating here, & from the national to area level | To be determined | UNHCR | Consult UNIFIL & verify it will continue to provide assistance in support of the hosting / local community, as well as emergency medical care to Syrian refugees
4 | Develop a strategy for agencies to mobilize additional resources quickly (eg a revision of the RRP) | To be determined | UNHCR to call IA meeting | Pre-prepare more ERF applications (= OCHA administered life-saving fund)
5 | Obtain from all agencies on a regular basis a self-assessment of their current level of preparedness (i.e. how many HH they can support, any physical reserve stocks &/or financial resources above and beyond this) | To be determined | UNHCR (Beirut) to design template | Support the agencies’ self-assessment, making it clear whether stocks are national level or area level, & not to duplicate this info
6 | Continue to discuss the issue of 'Transit Sites' with GoL, to ensure all actors understand the pros & cons of establishing them to cope with a mass influx | Ongoing | UNHCR | Continue to identify additional locations within the area, suitable for potential Transit Sites
7 | Map possible displacement scenarios, liaise with GoL so as to be prepared in case of limitations of humanitarian access | To be determined | UNHCR & GoL (MoSA) | Establish inter-area agreements on mutual support and particularly for data sharing
8 | Strengthen the current border monitoring system / introduce it ASAP with GoL support & LAF agreement | To be determined | UNHCR | Agree on permanent presence & a public information function at the border to facilitate access to the refugees
9 | Continue to enhance coordination with the Red Cross (ICRC, LRC & other societies) on contingency planning | Ongoing | UNHCR | Liaise with Lebanese Red Cross, and other national organizations in every district in the area
10 | Review & clarify level of authority of Senior Field Coordinators & their staff in area offices - specifically for managing the contingency response to the scenarios | To be determined | All actors | Strengthen relationships & improve data collection at municipality level - continue building trust
11 | Review requirements for information management in a contingency response, particularly reporting from and to the field, & continue to develop SOPs & templates | Ongoing | UNHCR | Review IM, agree reporting protocols / standardized assessment templates & other forms to improve info flow
12 | Complete the 3W mapping, and produce maps of key facilities in each area, including locations of SDCs & Lebanese Red Cross | To be determined | UNHCR | Strengthen info sharing protocols between agencies/service providers, & outreach to local authorities, refugees & host communities
13 | Create a core group to oversee 'operationalization' of the CP, and follow-up with Sector Leads & Senior Field Officers to ensure they complete all assigned taskings | 2013-07-31 | UNHCR, GoL (MoSA) | Establish an Area Crisis Management Team with key actors (e.g. MoSA Regional Coordinator), to follow up on CP preparedness actions & take executive decisions
14 | Add contingency planning as a standing item to each sectoral & inter-agency working group meeting agenda | Immediately | Sector Leads | Add contingency planning as a standing item to each sectoral & inter-agency group meeting agenda
15 | Pre-agree vulnerability & targeting criteria for sectors (Protection, Health, Shelter & WASH, Food & NFIs) | Ongoing | Sector Leads | Endorse group level assessment forms reflecting pre-agreement of vulnerability for relevant sectors
16 | Determine the core tasks to be fulfilled in a crisis & prepare rosters of key staff to perform them | To be determined | All actors | Determine the core tasks to be fulfilled in a crisis & prepare rosters of key staff to perform them
| Response Actions (National) | Deadline | Responsible | Response Actions (Area)
1 | GoL & UNHCR activate CP response after verification of numbers & inform UNSCOL, UNIFIL, OCHA & partners | On Day 1 | GoL (MoSA) & UNHCR | Implement the strategy to obtain information directly from the border, 24/7
2 | GoL to provide population movement data on a daily basis (entries & exits) | Daily, starting ASAP | GoL | Liaise with relevant authorities in areas of concern, to ensure humanitarian access (problem is staff safety)
3 | Adjust and re-deploy staffing for initial 24 hrs response by relevant actors / prepare & share lists of staff | 24 hrs | All actors | Redeploy staff from centre, another area or within it to respond adequately, particularly at transit sites
4 | Seek urgent authority from the Council of Ministers to establish 'transit sites' at predetermined locations | Within 48 hrs | GoL (MoSA) | Reconfirm potential of all predetermined locations for 'transit sites', & activate plans for their establishment
5 | Review existing national / field level coordination structure & adapt as necessary to the actual situation | Within 1 week | UNHCR | Decide whether activities can be reduced in one sector in order to increase in other sectors
6 | Ensure regular consultation with ICRC, the Red Cross Movement & any other relevant actors not formally in the coordination structure | Weekly | UNHCR | Regular consultation with ICRC, Red Cross Movement & other relevant actors, especially local CBOs
7 | Coordinate any inter-agency or cross-sectoral rapid assessment & present a 'gap analysis' | Within 1 month | GoL, UNHCR
8 | Sector working groups review priorities & capacities in the light of the early response to the new emergency, & report any alarming shortcomings | Within 1 month | Sector Leads
9 | Liaise with relevant members of the UNCT to assess impact on other population groups (IDP, PRS, Host, etc) | Within 1 month | UNHCR, IOM
10 | Liaise with embassies regarding TCNs & assist with issue of documentation / evacuation through transit centres | Within 1 month | IOM
| EXTERNAL RELATIONS & PUBLIC INFORMATION |  |  | Bekaa, North, South, Beirut & Mt Lebanon
| Preparedness Actions (National) | Deadline | Responsible | Preparedness Actions (Area)
1 | Revitalise the working group concerned with PI policy, to produce common messaging & template Q&As | To be determined | All agencies | Prepare area-specific PI lines / Q&As for quick response, in accordance with agencies' PI policies & the common messaging agreed at national level
2 | Develop mass communication capacity, strategy, tools & messages, designed for use in the current emergency but also in case of any heightened crisis | Ongoing | UNHCR | Tailor messages to area, & communicate systematically with the refugees (at transit sites, community centres & upon registration) on the services they should expect
3 | Pre-identify a Comms / Reporting Officer for rapid deployment to any area facing a new emergency | To be determined | UNHCR | Prepare media response by clarifiying who may speak to the press, pre-identification of spokespeople & training
| Response Actions (National) | Deadline | Responsible | Response Actions (Area)
1 | Deploy the identified Comms / Reporting Officers to each area | Within 24 hours | All agencies | Call forward Comms / Reporting Officers from national / Beirut level, to support the area
2 | PI staff issue daily updates, with information feed from field & sectors through the IMU | Daily, starting ASAP | UNHCR
3 | Issue a joint press statement / conference with GoL following consultation with agency PI units | Within 48 hours | GoL, UNHCR
4 | Initiate joint GoL-UN donor meeting & repeat periodically | Within 1 week | GoL, UNHCR
| SECURITY OF OPERATIONS (including the physical means of communication) |  |  | Bekaa, North, South, Beirut & Mt Lebanon
| Preparedness Actions (National) | Deadline | Responsible | Preparedness Actions (Area)
1 | Liaise with Lebanese security forces (ISF, LAF) to assess the security situation for refugees, staff & host communities | Ongoing | UNDSS | Contact local authorities (including security forces) in advance, to ensure they understand IHL & that they are responsible for the security of humanitarian personnel
2 | In coordination with the UNDSS & following SMT decisions to establish an internal security plan & SOPs for staff movements & contingency response | Ongoing | UNHCR | Collect a comprehensive list of satellite telephone numbers in order to set up a satellite 'communication tree' covering each agency/location
3 | Ensure that the warden system is updated & wardens are properly briefed on the changing environment | Ongoing | UNHCR | Establish clear coordination between UNHCR, UNRWA, UNIFIL & UNDSS (eg exchange Liaison Officers), & a back-up comms system for support
4 | Ensure that all staff & partners are briefed on the latest security developments | Ongoing | UNHCR | Agree on a communications & coordination system for rapid passage of security information, to increase the safety of UN & NGO staff in the area
5 | Seek clarification from GoL on the process to follow for NGOs to use radios for operations & safety, provided they meet the requirements of the LAF & ISF | To be determined | UNDSS & UNHCR | Review the possibility of allocating an existing UN radio channel to NGOs, to enable them to communicate for staff safety & operational purposes
6 | Validate the training & briefing that has gone on, & test the communications 'trees' by implementing a country-wide security drill | To be determined | UNDSS | Determine whether it is possible to share (UN) radios with key (non-UN) counterparts in certain locations to enable remote control response
7 | Assess telecomms equipment requirement of UN agencies & partners, & procure necessary equipment | To be determined | UNDSS & UNHCR
8 | Ensure that the prescribed field security equipment is in place for all locations & staff | To be determined | All agencies
| Response Actions (National) | Deadline | Responsible
1 | Advise on issues of illegal land occupation by refugees | As necessary | UNHCR FSU
2 | Advise on possible relocation of staff to the safer areas within the country &/or, ultimately, on evacuation | As necessary | UNDSS
| LOGISTICS |  |  | Bekaa, North, South, Beirut & Mt Lebanon
| Preparedness Actions (National) | Deadline | Responsible | Preparedness Actions (Area)
1 | Cover the responsibilities of the Logistics Cluster normally led by WFP (i.e. by expanding the TOR of the NFI Sector Working Group | To be determined | UNHCR, WFP | Amend the TOR of the Area Distribution Working Group, to include logistic issues of common concern
2 | Inventorize existing stocks of shelter materials, food & NFIs held by all agencies in country, to produce combined stock figure & be the basis of a common plan | To be determined | All Sector Leads | Confirm stocks of shelter materials, food & NFIs held by all agencies at area level, & map locations / quantities of these stocks / their availability to respond to a crisis
3 | List 'frame agreements' of all agencies/sectors & ask relevant agencies to check that they will actually work | To be determined | (Proposed) Logistics WG | Ask all agencies to share their 'frame agreements' - during the distribution coordination meeting
4 | Identify hubs across the country for supplies to be stockpiled, & look for common warehousing, in existing facilities or by creating new ones (eg with Rubb Halls) | To be determined | (Proposed) Logistics WG | Map the locations of all significant existing warehouses (including UNRWA, etc) in the area & find locations for new warehouses if possible (eg Rubb Halls)
5 | Draw upon the scenario planning & mapping work done by UNHCR to identify key locations where reserve stockpiles are needed, because they may be cut-off | To be determined | (Proposed) Logistics WG | Engage local partners for response & consider establishing stocks in local warehouses & in areas that may be inaccessible (e.g. Arsal, Hermel, Masharii Qaa)
6 | Analyse the transportation network in Lebanon, for choke points & possible solutions to avoid logistic paralysis in an insecure environment | To be determined | (Proposed) Logistics WG | Establish a monitoring system looking at transportation costs in the area, & keep a consolidated record tracking this (i.e. when the security situation changes)
7 | Establish protocols for common re-supply from regional humanitarian stockpiles, and drawing upon global suppliers using common procurement agreements | To be determined | (Proposed) Logistics WG
| REGISTRATION |  |  | Bekaa, North, South, Beirut & Mt Lebanon
| Preparedness Actions (National) | Deadline | Responsible | Preparedness Actions (Area)
1 | Develop a database for emergency registration, a border screening methodology, form & database (also in Access?) for systemization of data | In progress | UNHCR Registration | Share the emergency registration strategy / process with local actors for information purposes
2 | Prepare a roster of UNHCR staff to cover border monitoring, reception & registration, & prepare existing registration centres to absorb more staff | To be determined | UNHCR Registration | Train existing Area Registration Centre staff in the emergency screening & registration methodology
3 | Negotiate secondment to UNHCR of volunteers, available for deployment on short notice, from the Red Cross, World Vision, Arc en ciel, UNRWA | To be determined | UNHCR Registration | Identify partner staff (incl. from MoSA) for deployment to support emergency screening & registration, & organise training in the methodology / processes
4 | Develop capacity by training roster staff (UNHCR & partner) in emergency registration | To be determined | UNHCR Registration | Host & support the training of UNHCR & partner staff rostered for emergency registration
5 | Request Rubb Halls (up to three) + furniture for the transit centre(s) | To be determined | UNHCR Registration | Identify potential areas for emergency registration (eg transit sites, community centres, & mobile locations)
6 | Prepare, procure & preposition a stock of registration materials (family cards, fixing tokens, manifests) | To be determined | UNHCR Registration | Distribute the contingency stock of registration materials to registration centres at area level
7 | Develop mass info (e.g. on registration, or visibility material) leaflets & other media for dissemination at borders, transit centre(s) & where needed | To be determined | UNHCR Protection / Mass Comms | Distribute the stock of mass info materials to border crossings, registration & (potential) transit centres at area level
8 | Scrutinize mapping of official & unofficial border crossings / make contact with CBOs in those areas | To be determined | UNHCR Area Offices | Identify & establish contact with CBOs in those areas that can report on groups arriving
9 | Negotiate with LAF &/or GSO for UNHCR to access border crossings / ensure LAF &/or GSO designates liaison officers to UNHCR | To be determined | UNHCR Management
10 | Identify partners to assist in logistics & distribution at transit centre(s) (possibly DRC) | To be determined | UNHCR Registration
11 | Discuss with MSB registration & office work spaces for the camps | To be determined | UNHCR Registration
12 | Identify partners to provide emergency health care at transit centre(s) (possibly Red Cross) | To be determined | Health Sector Lead (UNHCR)
13 | Liaise with IOM regarding their preparedness / plan to transfer, accommodate & evacuate TCNs | To be determined | IOM
14 | Liaise with UNRWA regarding their preparedness / plan to record, transfer & accommodate PRS | To be determined | UNRWA
15 | Identify personal contractor(s) for bus services between transit centre(s) & camps | To be determined | UNHCR Admin
16 | Draw up inventory of IT equipment available for screening & registration - if nec., procure 40 laptops | To be determined | UNHCR Admin
17 | Identify / allocate vehicles & drivers | To be determined | UNHCR Admin
| Response Actions (National) | Deadline | Responsible | Response Actions (Area)
1 | Switch to emergency registration process at all transit sites & registration centres | Within 24 hours | UNHCR Registration | Carry out emergency registration, collecting basic bio-data & specific needs, at designated locations
2 | Activate roster of standby registration staff & redeploy some of the existing capacity to predetermined points | Within 24 hours | UNHCR Registration | Mobilise & redeploy required emergency registration staff to new locations, & mobilise partner staffing
3 | Mass information mechanism engaged at borders, transit centres & community centres | Within 24 hours | UNHCR Registration | Provide mass information regarding registration processes at the border & transit locations
4 | Depending on size of influx, prepare manifesting or fixing tokens at border points for refugee transportation | Within 48 hours | UNHCR Registration | Utilise basic fixing tokens at border locations in order to transport refugees to transit locations
5 | Engage additional local partners to support reception, registration & identification of the vulnerable | Within 72 hours | UNHCR Registration | Identify vulnerable persons at the entry points & during registration [refer to protection section below]
| PROTECTION |  |  | Bekaa, North, South, Beirut & Mt Lebanon
| Preparedness Actions (National) | Deadline | Responsible | Preparedness Actions (Area)
1 | Develop the system for border monitoring & rapid pre-screening for vulnerability (i.e. before registration), & to try to track refugee flows after they have entered | To be determined | Protection Sector | Agencies agree to establish a focal point from a single agency for liaision at borders & other key locations, & additional staff (from all agencies) to monitor
2 | Continue to liaise with Lebanese security forces to keep all official crossing points open & prevent refoulement | Ongoing | UNHCR | Establish a physical presence at Cheba'a' Hasbaya for monitoring, pre-screening, protection, referral & mass communication, & advocate to keep it open
3 | Liaise with GoL (LAF, ISF, MoSA) & UNIFIL to plan & manage a remote response south of the Litani River, in case UNHCR & NGOs have no access | To be determined | UNHCR | Identify, map & brief CBOs beyond the Litani River so that they can collect basic bio-data & respond as necessary if UNHCR & NGOs cannnot cross the river
4 | Confirm the policy, process & capacity to handle high risk or sensitive cases, including use of 'safe houses' | To be determined | Protection Sector | Identify / create 'safe houses' for high risk protection cases / train staff in 'light' case management
5 | Create a comprehensive list of contacts with respect to the border monitoring function | To be determined | Protection Sector | Identify / prepare a list of & train community focal points to monitor areas close to the border / flow points
6 | Discuss with GoL protection issues in a mass influx (treatment, follow-up, detention, etc.) including vulnerable/undocumented TCNs who may be detained | To be determined | UNHCR, IOM | Mainstream protection in transit sites (layout, buildings) & ensure it is considered in all sectoral meetings
7 | Review staffing requirements at national level to provide the field with more support for protection | To be determined | UNHCR | Partners confirm number of protection staff per location & identify who to deploy rapidly to transit sites, etc
8 | Create a 'training package' for new UNHCR Protection Staff & appropriate staff from partner agencies | To be determined | Protection Sector | Conduct a training session for UNHCR & partner staff in pre-screening & vulnerability identification
| Response Actions (National) | Deadline | Responsible | Response Actions (Area)
1 | Mobilize full-time presence at borders to ensure unhindered & safe entry, immediate identification of vulnerable persons & provision of information | Within 24 hours | GoL, UNHCR | Mobilise monitoring presence at borders / entry points to identify vulnerable, disseminate information, refer to Registration & relevant service providers
2 | Monitor protection situation / identify protection issues on ground, including physical safety at transit sites, etc | Within 24 hours | GoL, UNHCR | Station protection focal points from NGOs to set up 'protection desks' at transit sites / other locations for monitoring, identification, basic counselling & referral
3 | Ensure safe transport from border areas to transit sites, camps, other designated areas away from borders | Within 24 hours | GoL, UNHCR, IOM | Ensure safe transport from border areas to transit sites, camps, other designated areas away from borders
4 | Centralize tracking of refugee movement from entry points within the country, & communicate this rapidly | Within 48 hours | UNHCR | Utilise border monitoring, pre-screening & IM capacity to try to trace & inform about onward movement
5 | Coordinate with relevant partners regarding voluntary returns, possible third-country evacuation & repatriation | Within 72 hours | GoL, UNHCR, IOM | IOM will coordinate with embassies TCN evacuation & issue of travel documents for undocumented migrants
6 | Coordinate relocation of populations in need of relocation - if necessary establish humanitarian corridors | Within 72 hours | GoL, UNHCR
7 | Liaise with Lebanese security forces on documentation, detentions, application of guidelines on the quick identification & treatment of persons with special needs | Within 72 hours, then on a daily basis | GoL, UNHCR
| CHILD PROTECTION |  |  | Bekaa, North, South, Beirut & Mt Lebanon
| Preparedness Actions (National) | Deadline | Responsible | Preparedness Actions (Area)
1 | Identify emergency interim care for unaccompanied minors (UAM) & appropriate sites/locations & partners to provide emergency shelter for children at risk | Ongoing | UNHCR, UNICEF, GoL (MoSA) | Identify / create emergency interim care for UAM & appropriate sites / locations to provide emergency shelter for children at risk
2 | Prepare & disseminate to partners SOPs, assessment & monitoring forms for Child Protection monitoring, identifying children at risk, tracing, reunification | To be determined | UNHCR, UNICEF, GoL (MoSA) | Train staff & partners in the methodology for CP in emergencies & use of assessment & monitoring forms
3 | Identify & disseminate to all actors emergency referral pathways of child protection services per 'hub' | To be determined | UNHCR, UNICEF, GoL (MoSA) | Train staff & community volunteers in basic PSS / referrals
4 | Prepare & procure contingency stocks of recreation & early childhood development (ECD) kits | To be determined | UNICEF | Establish a contingency stock of recreation & early childhood development (ECD) kits in the area
5 | Develop IEC material with key messages on emergency child protection to raise awareness | To be determined | UNHCR, UNICEF, GoL (MoSA) | Identify appropriate CP actors & create lists of staff who can be deployed to create Child Friendly Spaces (CFS)
| Response Actions (National) | Deadline | Responsible | Response Actions (Area)
1 | Set up child protection monitoring at the border entry points to identify UAM / SC / children at risk | Within 48 hours | UNHCR, UNICEF, GoL (MoSA) | Protection monitoring & identification of UAM / SC / children at risk at reception, registration & transit sites
2 | Disseminate IEC materials & conduct awareness raising on child protection concerns | Within 48 hours | MOSA, UNHCR, UNICEF | CP concerns: birth registration, parental care, psychosocial support; UXO risk, childhood exploitation
3 | Conduct psychosocial & recreational activities - in transit sites, & through mobile outreach | Within 72 hours | MOSA, UNHCR, UNICEF | Create Child Friendly Spaces (CFS) in transit sites
4 | Tracing & family reunification for UAM / SC & referral to alternative care, particularly if in transit sites | Within 72 hours | ICRC, UNHCR, MOSA, UNICEF | Tracing & family reunification for UAM / SC & referral to alternative care, particularly if in transit sites
5 | Implement the emergency interim care arrangements for UAM & provide emergency shelter for children at risk | Within 72 hours | MOSA, UNHCR, UNICEF | Temporary emergency shelter/child safe houses for UAM/children at risk
6 | Case management of children at risk (child recruitment, physical & sexual violence/exploitation, trafficking) | Within 72 hours | MOSA, UNHCR, UNICEF
| PREVENTION & RESPONSE TO SEXUAL & GENDER BASED VIOLENCE (SGBV) |  |  | Bekaa, North, South, Beirut & Mt Lebanon
| Preparedness Actions (National) | Deadline | Responsible | Preparedness Actions (Area)
1 | Update contact information of SGBV-TF members including GoL counterparts & chairs of field SGBV coordination mechanisms | To be determined | SGBV-TF Coordinator | Update contact information of faith-based organisations, refugee FPs, women's & youth groups, SDCs & UPEL staff for info dissemination
2 | Order & distribute a stock of PEP Kits to the PHCs & hospitals vetted for inclusion in the referral pathways | To be determined | UNFPA | Monitor PHC & hospitals identified to deliver clinical management of SV to ensure up to the standard
3 | Continue ongoing training of medical personnel on clinical management of sexual violence | To be determined | SGBV-TF Coordinator | Provide induction on SGBV prevention / response to other sector staff (including non-medical)
4 | Disseminate minimum standards for the Dignity Kit & review the sanitary items provided through WASH Sector | To be determined | SGBV-TF Coordinator | Map the stocks of Dignity Kits & sanitary items held at area level, & pre-position more if deemed insufficient
5 | Advocate that each case management agency has clear protocols on data security in case its personnel are evacuated | To be determined | SGBV-TF Coordinator | Develop internal protocols to continue managing data & protecting confidentiality, including data security, in case personnel are evacuated
6 | Finalize key messages & IEC/visuals on the prevention of SGBV | To be determined | SGBV-TF Coordinator | Disseminate key messages & IEC to community / train social workers in emergency response
7 | Disseminate to members SOPs, safety audit templates & emergency GBVIMS intake forms | To be determined | SGBV-TF Coordinator | Disseminate repertoires of services & referral pathways with contact details to other agencies / frontline workers
8 | Translate the PSEA module into Arabic | To be determined | SGBV-TF Coordinator | Continue to train staff in PSEA
| Response Actions (National) | Deadline | Responsible | Response Actions (Area)
1 | Liase with other sector lead agencies to mitigate risks / ensure SGBV prevention & response is integrated into their own response | On Day 1 | UNHCR, UNICEF | Increase mobile intervention to strenthen access to psycho-social / health services including set up of temporary safe spaces, esp. in transit sites
1 | Ensure SGBV is integrated into any emergency protection monitoring & any inter-sectoral assessment | Within 72 hours | UNHCR, UNICEF | Identify more options for temporary shelter arrangements for women & girls at risk / SGBV survivors
| SHELTER |  |  | Bekaa, North, South, Beirut & Mt Lebanon
| Preparedness Actions (National) | Deadline | Responsible | Preparedness Actions (Area)
1 | Agree in advance on shelter vulnerability criteria; then create & use a standardised assessment approach | To be determined | Shelter, Protection & WASH Sectors | Apply the standardised assessment approach & form to assess vulnerability in the area; respond accordingly
2 | Shelter capacity assessment & mapping: identify, map & rehabilitate all potential transit sites, collective shelters | To be determined | Shelter & WASH Sectors, GoL (MoSA) | Make 1 agency responsible per locality for coordination, info sharing with municipalities & communities, etc.
3 | Open space assessment': identify, assess & plan the layout of all possible transit sites / other locations along road sides, on unoccupied land, agricultural land, etc | To be determined | Shelter & WASH Sectors, GoL (MoSA) | Identify more transit sites (in addition to any already identified) especially where high influx is anticipated
4 | Map existing stocks of building 'sealing-off' kits available with all actors across all areas, & increase the stocks | To be determined | UNHCR | Increase the stock of 'sealing-off' kits in the area, to 5,000 HU's &/or 3 months stock (at current rate)
5 | Assess the stock of tents &/or shelter boxes & increase to sufficient for at least 20,000 HH (5,000 in each of the 4 areas + 10,000 as a strategic reserve at national level) | To be determined | UNHCR | Preposition tents &/or T-shelters sufficient for 5,000 families in each of the 4 areas; coordinate their storage
| Response Actions (National) | Deadline | Responsible | Response Actions (Area)
1 | Utilise agreed vulnerability criteria in order to radically prioritise most vulnerable for provision of shelter | On Day 1 | UNHCR | In summer, coordinate with NFI partners for distribution of blankets; in winter open mosques, churches, schools
2 | Open new 'transit sites' & extend existing ones to double their planned size if possible | Within 24 hours | UNHCR, GoL (MoSA) | Extend any existing 'transit sites' / open new sites where pre-identified & planned
3 | Initiate an immediate rapid assessment of the locations of families on the move elsewhere | Within 72 hours | UNHCR | Carry out immediate assessment of location of families on the move elsewhere
| WASH |  |  | Bekaa, North, South, Beirut & Mt Lebanon
| Preparedness Actions (National) | Deadline | Responsible | Preparedness Actions (Area)
1 | In cooperation with Shelter Sector, identify options / locations to accommodate a mass influx, including sites for potential collective centres, transit sites & 'camps' | To be determined | Shelter & WASH Sectors, GoL (MoSA) | In accordance with the division into different localities (as per Shelter), assign responsibility in that location also for WASH interventions to the same unique agency
2 | Review & update lists of current stocks & available capacity for critical rapid response (eg water tankers) | To be determined | UNHCR, UNICEF | Review & update lists of current stocks at area level
3 | Review staffing requirements & support mechanisms against current capacity | To be determined | UNHCR, UNICEF | Review staffing requirements & support mechanisms against current capacity at area level
4 | Pre-position critical WASH materials for response at pre-identified key locations including potential transit sites | To be determined | UNHCR, UNICEF | Pre-position WASH materials for water storage & purification, garbage containers, at key locations
| Response Actions (National) | Deadline | Responsible | Response Actions (Area)
1 | Rapid needs assessment particularly of ITS & potential transit sites not already been assessed & planned | Within 24 hours | UNHCR, UNICEF, GoL | Rapid needs assessment particularly of ITS & potential transit sites not already been assessed & planned
2 | Hygiene promotion / awareness raising | Within 48 hours | UNHCR, UNICEF, GoL | Hygiene promotion / awareness raising
3 | Provision of water to all main sites through connection to existing network / water trucking | Within 48 hours | UNHCR, UNICEF, GoL | Provision of water to all main sites through connection to existing network / water trucking
4 | Set up water storage facilities at all main sites | Within 48 hours | UNHCR, UNICEF, GoL | Set up water storage facilities at all main sites
5 | Mass water treatment (chlorination) | Within 48 hours | UNHCR, UNICEF, GoL | Mass water treatment (chlorination)
6 | Distribute aquatabs / water purification filters | Within 48 hours | UNHCR, UNICEF, GoL | Distribute aquatabs / water purification filters
7 | Test water quality | Within 48 hours | UNHCR, UNICEF, GoL | Test water quality
8 | Distribute hygiene kits (including water containers or buckets) & baby kits to those with infants | Within 48 hours | UNHCR, UNICEF, GoL | Distribute hygiene kits (including water containers or buckets) & baby kits to those with infants
9 | Construct emergency latrines (using pre-fabricated sanitation units) / defecation fields if no alternative | Within 72 hours | UNHCR, UNICEF, GoL | Construct emergency latrines (using pre-fabricated sanitation units) / defecation fields if no alternative
10 | Set up water distribution tapstands including pipe networks | Within 1 week | UNHCR, UNICEF, GoL | Set up water distribution tapstands including pipe networks
11 | Construct emergency showers | Within 1 week | UNHCR, UNICEF, GoL | Construct emergency showers
12 | Undertake drainage works | Within 1 week | UNHCR, UNICEF, GoL | Undertake drainage works
13 | Install solid waste bins & arrange garbage disposal | Within 1 week | UNHCR, UNICEF, GoL | Install solid waste bins & arrange garbage disposal
14 | Distribute latrine / camp cleaning kits | Within 2 weeks | UNHCR, UNICEF, GoL | Distribute latrine / camp cleaning kits
| FOOD SECURITY & NUTRITION |  |  | Bekaa, North, South, Beirut & Mt Lebanon
| Preparedness Actions (National) | Deadline | Responsible | Preparedness Actions (Area)
1 | Maintain market monitoring system to track price increases/inflation, taking a baseline before the influx | Already in place | WFP | Assess & map Food & Nutrition Sector partner capacity & stocks in the area
2 | Confirm feasibility of scaling-up production, & make standby agreements for a total of 6,000 parcels/week | Done by 01/07/2013 | WFP | Maintain a fixed level of contingency stocks at 7,500 parcels (50% of the required quantity) at all times
3 | Predefine simple targeting criteria for a mass displacement, based on current Vulnerability Assessment, in order to target 'on-arrival' food parcels | To be determined | WFP | Drawing upon the plans of the Shelter & WASH Sector working groups, plan distribution points at or near to likely sites for collective centres, transit sites & 'camps'
4 | Estimate likely volume & locations, particularly in urban areas, for use of one-off food vouchers for new arrivals | To be determined | WFP
5 | Warn donors that a mass influx could result in short term food price inflation, so the vouchers' purchasing power may reduce at the same time as more will be needed | To be determined | WFP
| Response Actions (National) | Deadline | Responsible | Response Actions (Area)
1 | Prioritise in-kind food distributions at ITS, transit sites, collective centres, etc., having already mapped out the likely locations & planned associated distribution points | On Day 1 | WFP | Closely coordinate Shelter, WASH, Food & NFI response at area level so that the assistance is coherent, consistent, & does not create unrealistic expectations
2 | Utilise the simplified targeting criteria to quickly identify the other vulnerable &/or needy families, who are not living in an ITS, transit sites or collective centres | Within 48 hours | WFP | Distribute food parcels or E-vouchers as appropriate, to refugees not living in 'camp' type situations, & continue assisting the registered, if funds permit
3 | Set up a system to monitor for malnutrition | Within 1 month | WFP | Support malnutrition monitoring mechanism, as needed
| NON-FOOD ITEMS (NFI), including CORE RELIEF ITEMS (CRI) |  |  | Bekaa, North, South, Beirut & Mt Lebanon
| Preparedness Actions (National) | Deadline | Responsible | Preparedness Actions (Area)
1 | Standardize the NFI kit contents & specifications of individual items, provided by all agencies | Ongoing | NFI Sector Working Group | Assess & map NFI Sector partner capacity & stocks in the area, based on the quantity of standard kits available
2 | Predefine simple targeting criteria for a mass displacement, based on current Vulnerability Assessment, in order to target 'NFI New Arrival' Kits | To be determined | NFI Sector Working Group | Drawing upon the plans of the Shelter & WASH Sector working groups, plan distribution points at or near to likely sites for collective centres, transit sites & 'camps'
3 | Warn donors that contingency stocks requested under RRP5 (for 44,000 HH) by all agencies will be quickly exhausted & make them agree to strategic reserves | To be determined | NFI Sector Working Group | Establish a reserve stock of all NFIs sufficent for 10,000 HH actually within each area, & seek funds for more
| Response Actions (National) | Deadline | Responsible | Response Actions (Area)
1 | Prioritise in-kind NFI distributions at ITS, transit sites, collective centres, etc., having already mapped out the likely locations & planned associated distribution points | On Day 1 | UNHCR | Closely coordinate Shelter, WASH, Food & NFI response at area level so that the assistance is coherent, consistent, & does not create unrealistic expectations
2 | Utilise the simplified targeting criteria to quickly identify the other vulnerable &/or needy families, who are not living in an ITS, transit sites or collective centres | Within 48 hours | UNHCR | Distribute NFI kits or E-vouchers as appropriate, to refugees not living in 'camp' type situations, & continue assisting the registered, if funds permit
| HEALTH |  |  | Bekaa, North, South, Beirut & Mt Lebanon
| Preparedness Actions (National) | Deadline | Responsible | Preparedness Actions (Area)
1 | Map current capacity of partners at national level, set up info / coordination agreements & a matrix of services dividing roles according to comparative advantage | To be determined | UNHCR, WHO, GoL (MoPH, MoSA) | Map current capacity of partners at area level, set up info / coordination agreements & a matrix of services dividing roles according to comparative advantage
2 | Define key medical items for the contingency response, & inventorize the stocks held at national level | To be determined | UNHCR, WHO, GoL (MoPH) | Define key medical items (medicines, supplies & equipment), & inventorize the stocks held at area level
3 | Map out existing Primary Health Care (PHC) & Secondary Health Care (SHC) facilities at country level | To be determined | UNHCR, WHO, GoL (MoPH) | Map out existing PHC & SHC facilities at area level
4 | In consultation with MoPH assess the risk of Scenario 3, & ensure that the response is properly planned | To be determined | UNHCR, WHO, GoL (MoPH) | Ensure the response to a major epidemic, complicated by the refugees, is properly planned by all area offices
| Response Actions (National) | Deadline | Responsible | Response Actions (Area)
1 | Establish teams at entry points to conduct triage / epidemic control / health monitoring / rapid assessment | Within 24 hours | UNHCR, WHO, GoL (MoPH, MoSA) | Establish teams at entry points (legal & illegal) with security coverage at critical locations
2 | Referral system for stabilised cases, on to the network of existing PHC & SHC, & extend their opening hours | Within 24 hours | UNHCR, LRC | Referral system to the network of existing PHC & SHC, & extend their opening hours
3 | Monitor & control health of population, particularly epidemic monitoring & control | Within 48 hours | UNHCR, WHO, UNICEF, MoPH | Monitor & control health of population, particularly epidemic monitoring & control
4 | Mobile clinics/outposts to deliver emergency response & PHC at new sites or personnel, equipment & medicines at existing facilities to increase capacity | Within 48 hours | UNHCR, WHO, GoL (MoPH) | Mobile clinics/outposts to deliver emergency response & PHC at new sites or personnel, equipment & medicines to increase capacity at existing facilities
5 | Establish staffed, equipped & properly resourced field hospitals | Within 72 hours | MSF, IMC, GoL (MoPH) | Establish staffed, equipped & properly resourced field hospitals
6 | Health education & outreach to the population | Within 1 month | UNHCR | Health education & outreach to the population
| EDUCATION |  |  | Bekaa, North, South, Beirut & Mt Lebanon
| Preparedness Actions (National) | Deadline | Responsible | Preparedness Actions (Area)
1 | Assess & map tented settlements for access to education, number of school age children, proper studying environment & space for school tents | To be determined | GoL (MEHE), UNICEF, UNHCR | Set up temporary schools in tents at likely sites for collective centres, transit sites & 'camps' through site assessment, planning & prepositioning stocks in the area
2 | If the mass influx is very large or overwhelming, especially if in winter, as a last resort use schools for shelter | To be determined | GoL (MEHE), UNICEF, UNHCR | Map & divide the area into school-clusters & designate a focal point (i.e. 1 IP) per school-cluster in case schools might have to be suspended to use them for shelter
3 | Raise awareness, provide vaccines, hygiene kits, medication, shampoo to all schools | To be determined | MEHE, MoPH, UNICEF, UNHCR | Support the awareness raising & practical measures to combat lice, scabies & other infectious conditions
4 | Conduct a Joint Education Capacity & Needs Assessment, looking at all public & private schools across the country | To be determined | MEHE, UNICEF, UNESCO, UNHCR | Support Joint Education Capacity & Needs Assessment - map school situation, locations & capacity, across area
5 | Plan how to set up child-friendly spaces in collective centres, transit sites, ITS & other forms of 'camps', where some educational activities can continue | To be determined | GoL (MEHE), UNICEF, UNHCR | Map locations, centres, partners who are capable (& build the capacity of other partners) to do remedial classes & ALPS for newcomers & children outside schools
6 | Map availability of incentive teachers & provide them with training, facilities & supplies | To be determined | GoL (MEHE), UNICEF, UNHCR | Support mapping of availability of incentive teachers & provide appropriate training, facilities & supplies
7 | Preposition 'Schools-in-a-Box', Recreational Kits & school tents/prefabs at key locations across the country | To be determined | GoL (MEHE), UNICEF, UNHCR | Map suitable warehouses ito preposition 'Schools-in-a-Box', recreational kits and school tents/prefabs
8 | Procure additional education supplies sufficient for 1 month's mass influx (e.g. ~150,000 school age children) | To be determined | GoL (MEHE), UNICEF, UNHCR | Pre-position education supplies in each area
9 | Confirm with MEHE & communicate the curriculum defined for Syrian refugee children in Lebanon | To be determined | UNICEF, UNHCR
10 | Obtain authorisation from GoL (MEHE) for educational activities to take place in any form of tented settlement | To be determined | UNICEF, UNHCR
11 | Prepare for a mass influx by providing teacher training, enhanced facilities, school supplies, & rehabilitation | To be determined | GoL (MEHE), UNICEF, UNHCR
12 | Reinforce MEHE through deployment of an Emergency Education Team | Ongoing | GoL (MEHE), UNICEF, UNHCR
| Response Actions (National) | Deadline | Responsible | Response Actions (Area)
1 | Include Education in any rapid inter-sectoral assessment | ASAP | UNICEF, UNHCR | Include Education in any rapid inter-sectoral assessment
2 | Ensure that education data is collected, consolidated, analysed & disseminated, & perform M&E regularly | Within 1 week | GoL (MEHE), UNICEF, UNHCR | Ensure that education data is collected, consolidated, analysed & disseminated, & perform M&E regularly
3 | Initiate Two-Shift schooling country-wide, ensuring that fees, equipment & running costs are covered | Within 2 weeks | GoL (MEHE) | Initiate Two-Shift schooling country-wide including in private schools
4 | Set up child-friendly spaces in collective centres, transit sites, & ITS, so that some educational activities continue | Within 1 month | GoL (MEHE), UNICEF, UNHCR | Initiate remedial classes & ALPS for newcomers & children outside schools
5 | In a mass but gradual refugee influx, establish tented schools in collective centres & transit sites, & enlarge existing school facilities to expand capacity | Within 1 month | GoL (MEHE), UNICEF, UNHCR | Support the establishment of temporary schools in tents at collective centres & transit sites, & also inside existing school facilities to expand capacity
6 | If the influx is more sudden/overwhelming, use schools for shelter but initiate Education's plan to get all refugee & Lebanese children back to school within 3-6 months | Within 1 month | GoL (MEHE), UNICEF, UNHCR | Support implementation of Education's contingency plan to get all refugee Syrian children & all Lebanese children back to school within 3-6 months
7 | Intensify community outreach to ensure enrolment | Within 2 months | GoL (MEHE), UNICEF, UNHCR
8 | Advertise for, select & recruit additional teachers as necessary | Within 2 months | GoL (MEHE), UNICEF, UNHCR

## I. Contingency Stocks
SUMMARY TABLE OF ALL AREAS + NATIONAL RESERVE STOCKS
Serial | Item | ACF | AVSI | Caritas | CISP | DRC | GVC | HI | ICRC | INTERSOS | IOCC | IOM | IR | IRC | Medair | Mercy Corps | MSF | SCI | Solidarités | Tdh-L | UNHCR | UNICEF | UNRWA | WFP | World Vision | Totals
1 | Tent (Family) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5140 | 0 | 0 | 0 | 0 | 5140
2 | Tent (Lightweight) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 0 | 0 | 511
3 | Tent (Heavyweight) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 0 | 0 | 0 | 0 | 119
4 | Blanket (High Thermal) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38792 | 0 | 0 | 0 | 0 | 38792
5 | Blanket (Medium Thermal) | 0 | 0 | 3000 | 0 | 800 | 0 | 2500 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7800 | 0 | 0 | 0 | 77999 | 200 | 0 | 0 | 4000 | 98049
6 | Quilt | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49447 | 0 | 0 | 0 | 0 | 51447
7 | Bed Sheets | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
8 | Kitchen Set | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892 | 0 | 0 | 0 | 24101 | 0 | 0 | 0 | 0 | 27243
9 | Bucket + Lid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19878 | 1000 | 0 | 0 | 0 | 20878
10 | Sleeping Mat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44000 | 0 | 0 | 0 | 0 | 44000
11 | Mattress | 0 | 0 | 3000 | 0 | 1000 | 0 | 2000 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49516 | 0 | 0 | 0 | 0 | 57266
12 | Water Container (10 L collapsible) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21203 | 2000 | 0 | 0 | 0 | 23203
13 | Hygiene Kit | 300 | 0 | 10000 | 0 | 600 | 0 | 500 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10191 | 1946 | 0 | 0 | 0 | 25287
14 | Sanitary Napkins (packets) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Baby Kit (Small) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Baby Kit (Medium) | 75 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325
17 | Baby Kit (Large) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Dignity Kit | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300
19 | Plastic Tarpaulins | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8557 | 0 | 0 | 0 | 0 | 8557
20 | Plastic Sheeting (rolls) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274 | 0 | 0 | 0 | 0 | 274
21 | Cooking Stove & ancillaries | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 7
22 | Heating Stove & ancillaries | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Gas Cylinder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 150
24 | Jerry-can (for fuel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1255
25 | Clothing (items) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Food Parcel (for newcomer family) | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 4250
27 | Building 'Sealing-Off' Kits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 250
28 | Emergency Latrines | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125
29 | Water Purification (NaDCC) 33mg tabs/BOX-10,000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 59
30 | Water Purification (NaDCC) 33mg tabs/PAC-50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 90000
31 | Water Filter, candle (10-80 litre/day) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1714 | 0 | 0 | 0 | 1714
32 | Water Tank, rigid (10 m3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 100
33 | Water Trucking (m3 per month) | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000
34 | Prosthetics/mobility for handicapped | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120
35 | Rubb Halls (for logistic support) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 20
36 | Other warehouses available for use in the area | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NATIONAL RESERVE STOCKS
Serial | Item | ACF | AVSI | Caritas | CISP | DRC | GVC | HI | ICRC | INTERSOS | IOCC | IOM | IR | IRC | Medair | Mercy Corps | MSF | SCI | Solidarités | Tdh-L | UNHCR | UNICEF | UNRWA | WFP | World Vision | Totals
1 | Tent (Family) | [19 empty] | 4620 |  |  |  |  | 4620
2 | Tent (Lightweight) | [24 empty] | 0
3 | Tent (Heavyweight) | [24 empty] | 0
4 | Blanket (High Thermal) | [19 empty] | 15335 |  |  |  |  | 15335
5 | Blanket (Medium Thermal) | [19 empty] | 31340 |  |  |  |  | 31340
6 | Quilt | [19 empty] | 46973 |  |  |  |  | 46973
7 | Bed Sheet | [24 empty] | 0
8 | Kitchen Set | [19 empty] | 9800 |  |  |  |  | 9800
9 | Bucket + Lid | [19 empty] | 15847 |  |  |  |  | 15847
10 | Sleeping Mat | [19 empty] | 37500 |  |  |  |  | 37500
11 | Mattress | [19 empty] | 23993 |  |  |  |  | 23993
12 | Water Container (10 L collapsible) | [19 empty] | 18500 |  |  |  |  | 18500
13 | Hygiene Kit | [19 empty] | 191 |  |  |  |  | 191
14 | Sanitary Napkins (packets) | [24 empty] | 0
15 | Baby Kit (Small) | [24 empty] | 0
16 | Baby Kit (Medium) | [24 empty] | 0
17 | Baby Kit (Large) | [24 empty] | 0
18 | Dignity Kit | [24 empty] | 0
19 | Plastic Tarpaulins | [19 empty] | 650 |  |  |  |  | 650
20 | Plastic Sheeting (rolls) | [19 empty] | 274 |  |  |  |  | 274
21 | Cooking Stove & ancillaries | [24 empty] | 0
22 | Heating Stove & ancillaries | [24 empty] | 0
23 | Gas Cylinder | [24 empty] | 0
24 | Jerry-can (for fuel) | [24 empty] | 0
25 | Clothing (items) | [24 empty] | 0
26 | Food Parcel (for newcomer family) | [24 empty] | 0
27 | Building 'Sealing-Off' Kits | [24 empty] | 0
28 | Emergency Latrines | [24 empty] | 0
29 | Water Purification (NaDCC) 33mg tabs/BOX-10,000 | [24 empty] | 0
30 | Water Purification (NaDCC) 33mg tabs/PAC-50 | [24 empty] | 0
31 | Water Filter, candle (10-80 litre/day) | [24 empty] | 0
32 | Water Tank, rigid (10 m3) | [24 empty] | 0
33 | Water Trucking (m3 per month) | [24 empty] | 0
34 | Prosthetics/mobility for handicapped | [24 empty] | 0
35 | Rubb Halls (for logistic support) | [19 empty] | 19 |  |  |  |  | 19
36 | Other warehouses available for use in the area | [24 empty] | 0
BEKKA
Serial | Item | ACF | AVSI | Caritas | CISP | DRC | GVC | HI | ICRC | INTERSOS | IOCC | IOM | IR | IRC | Medair | Mercy Corps | MSF | SCI | Solidarités | Tdh-L | UNHCR | UNICEF | UNRWA | WFP | World Vision | Totals
1 | Tent (Family) | [19 empty] | 320 |  |  |  |  | 320
2 | Tent (Lightweight) | [19 empty] | 440 |  |  |  |  | 440
3 | Tent (Heavyweight) | [19 empty] | 119 |  |  |  |  | 119
4 | Blanket (High Thermal) | [19 empty] | 1110 |  |  |  |  | 1110
5 | Blanket (Medium Thermal) |  |  | 3000 |  | 800 |  | 2500 | 1750 | [7 empty] | 7800 |  |  |  | 2644 | 200 |  |  | 4000 | 22694
6 | Quilt |  |  | 2000 | [16 empty] | 1974 |  |  |  |  | 3974
7 | Bed Sheet |  |  | 2000 | [21 empty] | 2000
8 | Kitchen Set | [6 empty] | 500 | 1750 | [7 empty] | 892 |  |  |  | 2875 |  |  |  |  | 6017
9 | Bucket + Lid | [19 empty] | 2015 | 1000 |  |  |  | 3015
10 | Sleeping Mat | [19 empty] | 4000 |  |  |  |  | 4000
11 | Mattress |  |  | 3000 |  | 1000 |  | 2000 | 1750 | [11 empty] | 2898 |  |  |  |  | 10648
12 | Water Container (10 L collapsible/rigid) | [19 empty] | 2266 | 2000 |  |  |  | 4266
13 | Hygiene Kit | 300 |  | 10000 |  | 600 |  | 500 | 1750 | [12 empty] | 1946 |  |  |  | 15096
14 | Sanitary Napkins (packets) | [24 empty] | 0
15 | Baby Kit (Small) | [24 empty] | 0
16 | Baby Kit (Medium) | 75 | [5 empty] | 250 | [17 empty] | 325
17 | Baby Kit (Large) | [24 empty] | 0
18 | Dignity Kit | 300 | [23 empty] | 300
19 | Plastic Tarpaulins | [19 empty] | 5554 |  |  |  |  | 5554
20 | Plastic Sheeting (rolls) | [24 empty] | 0
21 | Cooking Stove & ancillaries | [19 empty] | 7 |  |  |  |  | 7
22 | Heating Stove & ancillaries | [24 empty] | 0
23 | Gas Cylinder | [24 empty] | 0
24 | Jerry-can (for fuel) | [15 empty] | 1255 | [8 empty] | 1255
25 | Clothing (items) | [24 empty] | 0
26 | Food Parcel (for newcomer family) | [6 empty] | 500 | 1750 | [14 empty] | 2000 |  | 4250
27 | Building 'Sealing-Off' Kits | [19 empty] | 250 |  |  |  |  | 250
28 | Emergency Latrines | 125 | [23 empty] | 125
29 | Water Purification (NaDCC) 33mg tabs/BOX-10,000 | [20 empty] | 59 |  |  |  | 59
30 | Water Purification (NaDCC) 33mg tabs/PAC-50 | [20 empty] | 90000 |  |  |  | 90000
31 | Water Filter, candle (10-80 litre/day) | [20 empty] | 1714 |  |  |  | 1714
32 | Water Tank, rigid (10 m3) | [20 empty] | 100 |  |  |  | 100
33 | Water Trucking (m3 per month) | 9000 | [23 empty] | 9000
34 | Prosthetics/mobility for handicapped | [6 empty] | 120 | [17 empty] | 120
35 | Rubb Halls (for logistic support) | [19 empty] | 1 |  |  |  |  | 1
36 | Other warehouses available for use in the area | [24 empty] | 0
NORTH
Serial | Item | ACF | AVSI | Caritas | CISP | DRC | GVC | HI | ICRC | INTERSOS | IOCC | IOM | IR | IRC | Medair | Mercy Corps | MSF | SCI | Solidarités | Tdh-L | UNHCR | UNICEF | UNRWA | WFP | World Vision | Totals
1 | Tent (Family) | [19 empty] | 200 |  |  |  |  | 200
2 | Tent (Lightweight) | [19 empty] | 71 |  |  |  |  | 71
3 | Tent (Heavyweight) | [24 empty] | 0
4 | Blanket (High Thermal) | [19 empty] | 897 |  |  |  |  | 897
5 | Blanket (Medium Thermal) | [19 empty] | 4015 |  |  |  |  | 4015
6 | Quilt | [19 empty] | 500 |  |  |  |  | 500
7 | Bed Sheet | [24 empty] | 0
8 | Kitchen Set | [19 empty] | 1426 |  |  |  |  | 1426
9 | Bucket + Lid | [19 empty] | 2016 |  |  |  |  | 2016
10 | Sleeping Mat | [19 empty] | 2500 |  |  |  |  | 2500
11 | Mattress | [19 empty] | 673 |  |  |  |  | 673
12 | Water Container (10 L collapsible) | [19 empty] | 437 |  |  |  |  | 437
13 | Hygiene Kit | [24 empty] | 0
14 | Sanitary Napkins (packets) | [24 empty] | 0
15 | Baby Kit (Small) | [24 empty] | 0
16 | Baby Kit (Medium) | [24 empty] | 0
17 | Baby Kit (Large) | [24 empty] | 0
18 | Dignity Kit | [24 empty] | 0
19 | Plastic Tarpaulins | [19 empty] | 2353 |  |  |  |  | 2353
20 | Plastic Sheeting (rolls) | [24 empty] | 0
21 | Cooking Stove & ancillaries | [24 empty] | 0
22 | Heating Stove & ancillaries | [24 empty] | 0
23 | Gas Cylinder | [19 empty] | 150 |  |  |  |  | 150
24 | Jerry-can (for fuel) | [24 empty] | 0
25 | Clothing (items) | [24 empty] | 0
26 | Food Parcel (for newcomer family) | [24 empty] | 0
27 | Building 'Sealing-Off' Kits | [24 empty] | 0
28 | Emergency Latrines | [24 empty] | 0
29 | Water Purification (NaDCC) 33mg tabs/BOX-10,000 | [24 empty] | 0
30 | Water Purification (NaDCC) 33mg tabs/PAC-50 | [24 empty] | 0
31 | Water Filter, candle (10-80 litre/day) | [24 empty] | 0
32 | Water Tank, rigid (10 m3) | [24 empty] | 0
33 | Water Trucking (m3 per month) | [24 empty] | 0
34 | Prosthetics/mobility for handicapped | [24 empty] | 0
35 | Rubb Halls (for logistic support) | [24 empty] | 0
36 | Other warehouses available for use in the area | [24 empty] | 0
SOUTH
Serial | Item | ACF | AVSI | Caritas | CISP | DRC | GVC | HI | ICRC | INTERSOS | IOCC | IOM | IR | IRC | Medair | Mercy Corps | MSF | SCI | Solidarités | Tdh-L | UNHCR | UNICEF | UNRWA | WFP | World Vision | Totals
1 | Tent (Family) | [24 empty] | 0
2 | Tent (Lightweight) | [24 empty] | 0
3 | Tent (Heavyweight) | [24 empty] | 0
4 | Blanket (High Thermal) | [24 empty] | 0
5 | Blanket (Medium Thermal) | [24 empty] | 0
6 | Quilt | [24 empty] | 0
7 | Bed Sheet | [24 empty] | 0
8 | Kitchen Set | [24 empty] | 0
9 | Bucket + Lid | [24 empty] | 0
10 | Sleeping Mat | [24 empty] | 0
11 | Mattress | [24 empty] | 0
12 | Water Container (10 L collapsible) | [24 empty] | 0
13 | Hygiene Kit | [24 empty] | 0
14 | Sanitary Napkins (packets) | [24 empty] | 0
15 | Baby Kit (Small) | [24 empty] | 0
16 | Baby Kit (Medium) | [24 empty] | 0
17 | Baby Kit (Large) | [24 empty] | 0
18 | Dignity Kit | [24 empty] | 0
19 | Plastic Tarpaulins | [24 empty] | 0
20 | Plastic Sheeting (rolls) | [24 empty] | 0
21 | Cooking Stove & ancillaries | [24 empty] | 0
22 | Heating Stove & ancillaries | [24 empty] | 0
23 | Gas Cylinder | [24 empty] | 0
24 | Jerry-can (for fuel) | [24 empty] | 0
25 | Clothing (items) | [24 empty] | 0
26 | Food Parcel (for newcomer family) | [24 empty] | 0
27 | Building 'Sealing-Off' Kits | [24 empty] | 0
28 | Emergency Latrines | [24 empty] | 0
29 | Water Purification (NaDCC) 33mg tabs/BOX-10,000 | [24 empty] | 0
30 | Water Purification (NaDCC) 33mg tabs/PAC-50 | [24 empty] | 0
31 | Water Filter, candle (10-80 litre/day) | [24 empty] | 0
32 | Water Tank, rigid (10 m3) | [24 empty] | 0
33 | Water Trucking (m3 per month) | [24 empty] | 0
34 | Prosthetics/mobility for handicapped | [24 empty] | 0
35 | Rubb Halls (for logistic support) | [24 empty] | 0
36 | Other warehouses available for use in the area | [24 empty] | 0
BEIRUT & MT LEBANON
Serial | Item | ACF | AVSI | Caritas | CISP | DRC | GVC | HI | ICRC | INTERSOS | IOCC | IOM | IR | IRC | Medair | Mercy Corps | MSF | SCI | Solidarités | Tdh-L | UNHCR | UNICEF | UNRWA | WFP | World Vision | Totals
1 | Tent (Family) | [24 empty] | 0
2 | Tent (Lightweight) | [24 empty] | 0
3 | Tent (Heavyweight) | [24 empty] | 0
4 | Blanket (High Thermal) | [19 empty] | 21450 |  |  |  |  | 21450
5 | Blanket (Medium Thermal) | [19 empty] | 40000 |  |  |  |  | 40000
6 | Quilt | [24 empty] | 0
7 | Bed Sheet | [24 empty] | 0
8 | Kitchen Set | [19 empty] | 10000 |  |  |  |  | 10000
9 | Bucket + Lid | [24 empty] | 0
10 | Sleeping Mat | [24 empty] | 0
11 | Mattress | [19 empty] | 21952 |  |  |  |  | 21952
12 | Water Container (10 L collapsible) | [24 empty] | 0
13 | Hygiene Kit | [19 empty] | 10000 |  |  |  |  | 10000
14 | Sanitary Napkins (packets) | [24 empty] | 0
15 | Baby Kit (Small) | [24 empty] | 0
16 | Baby Kit (Medium) | [24 empty] | 0
17 | Baby Kit (Large) | [24 empty] | 0
18 | Dignity Kit | [24 empty] | 0
19 | Plastic Tarpaulins | [24 empty] | 0
20 | Plastic Sheeting (rolls) | [24 empty] | 0
21 | Cooking Stove & ancillaries | [24 empty] | 0
22 | Heating Stove & ancillaries | [24 empty] | 0
23 | Gas Cylinder | [24 empty] | 0
24 | Jerry-can (for fuel) | [24 empty] | 0
25 | Clothing (items) | [24 empty] | 0
26 | Food Parcel (for newcomer family) | [24 empty] | 0
27 | Building 'Sealing-Off' Kits | [24 empty] | 0
28 | Emergency Latrines | [24 empty] | 0
29 | Water Purification (NaDCC) 33mg tabs/BOX-10,000 | [24 empty] | 0
30 | Water Purification (NaDCC) 33mg tabs/PAC-50 | [24 empty] | 0
31 | Water Filter, candle (10-80 litre/day) | [24 empty] | 0
32 | Water Tank, rigid (10 m3) | [24 empty] | 0
33 | Water Trucking (m3 per month) | [24 empty] | 0
34 | Prosthetics/mobility for handicapped | [24 empty] | 0
35 | Rubb Halls (for logistic support) | [24 empty] | 0
36 | Other warehouses available for use in the area | [24 empty] | 0