Livelihoods and Social Stability Working Group Meeting - Minutes

| MEETING |  |  |  |
| --- | --- | --- | --- |
| Name | Livelihoods and Social Stability WG meeting | Meeting date | Tuesday 10th of May |
| Meeting location | UNDP office Chtaura | Meeting time | 10:00 |
| Chair person | Rania Hammoud/ UNDP | Meeting duration | 1 hr., 30 mins |
| Minutes prepared by | UNDP |  |  |
| Participants | DRC, IOM, UNHCR, SCI, ALEF, UNDP, WFP, LOST, MC, MOSA, UNRWA and AMEL |  |  |
| Agenda of the meeting | - Update from the central level - UNHCR presentation on the Solidarity Initiative - Update from partners on the ongoing and planed projects - AOB |  |  |

Summary of Discussion Points

| 1. | - Central level update Steering committees are still being set up in each sector, pending Government confirmation of Ministries participating. ACF and AlMajmoua will represent NGOs in Livelihoods, SFCG in Social Stability. The last national working group focused on value chains where partners who implemented programmes shared lessons learnt – this included examples from Bekaa, notably from Mercy Corps work on recycling and solid waste management and Save the Children work in value chain development. The sector will organize a mini-workshop to consolidate and exchange on experiences and lessons learnt in providing market-based skills trainings. Overall, there are 22 partners providing over 160 trainings across the country, covering more than 50 types of trainings (including food processing, AC/computer/mobile maintenance, electricity, embroidery, handicrafts, nursery…). In Bekaa/Baalbek, 9 partners (AVSI, UNDP, SPARK, ACA, SCI, B&Z, Al Majmoua, MC, LOST) are involved in the organization of market-based skills trainings. LOST and MC will need to provide input to the sector field coordinator in order to feed the ongoing skills trainings analysis conducted by the sector. Overall, 26% of all MBST are available in Bekaa/Baalbek, covering all the main types of trainings listed (including embroidery, agriculture, handicrafts, nursing, mechanics, electricity…). |
| --- | --- |
| 2. | - UNHCR presentation on the Solidarity Initiative Opportunities from grassroots groups to submit application for one month initiatives to enhance protection and social stability. 500 to 2,000$ per initiatives. This can cover a wide range of issues as long as it fits the above criteria. The deadline is 25 May. 50 people need to be reached by each protect. UNCHR will directly monitor the Bekaa (Central, West, Rashaya) projects and IRC will follow the Baalbeck-Hermel area. For example, community events could focus on road safety, social events... the underlying rational is that community are in the best position to identify and resolve issues. You do not have to be affiliated to an NGO, individuals can apply directly. 8 projects will be initially funded in Bekaa and 6 in Baalbeck-Hermel. One NGO can submit several proposals but individuals will be prioritized to emphasize the grassroots and bottom-up approach. There were initiatives last year related to peaceful coexistence but that’s the first time this modality is used. To be eventually continued afterwards based on results of this phase. Proposals can be submitted either in English or Arabic. |
| 3 | - Update from partners on the ongoing and planed projects DRC: 6 municipalities Hermel/Baalbeck/Brital expanding to Saaide this month. 3 MSAs, including one vacant. Central and West: Bar Elias, Marj, Majdel Anjar. Livelihoods/public work as well in each area. Update on social stability/CSPs: 6 CSPs completed in North Bekaa and 4 ongoing in Central Bekaa. Municipal elections have slowed down the work. Marj Garbage truck and Mini Football to be finalized within 3 months. Madjel Anjar – building a multi-purpose hall, garbage truck, drainage canal to be completed within 3 months. Hermel the municipality was provided with a Bobcat: Baalbeck municipality was provided with a Bobcat as well. Rehabilitation of Ras Ain public garden. In Brital, maintenance and equipment of cultural centre and installation of sewage line. Livelihoods: Labour intensive neighbourhood approach in Waivel camp – gardening, painting on the walls. In Baalbeck, the public work was in the ruins neighbourhood, co-funded with the municipality. River cleaning in Hermel and gardening. Cleaning the drainage and garden in Marj, in addition of street painting. In Majdel Anjar also cleaning of streets and installing bus stations. In Bar Elias, garbage bins painting and cleaning street, painting training centre. Referrals from protection team and from the municipality – vulnerability assessment conducted afterwards. Beneficiaries from both communities but almost exclusively men. Approximately 10 people for each project. In Baalbeck, there were more Lebanese but in rural areas more Syrians. One of the challenges is the dropout rate, especially for Lebanese – some of the Lebanese are actually not vulnerable enough when referred to municipality. Teams are almost always mixed. Skilled workers are remunerated 25$/day against 20 $/day for non-skilled workers. Each mission lasts on average between 10 to 12 days. Livelihoods: BPRM project – multi sector including protection, livelihoods and shelter. Livelihoods in partnership with Makhzoumi Foundation in Baalbeck – assessment to be launched by the end of the month- skills training on beauty, computer, mobile fixing, targeting male and female, 125 Lebanese, 125 Syrians. Makhzoumi has done the market assessment in their areas. LOST: Stability: Forum ZFD project on inter-community dialogue. We trained community activists who then train working group members on non-violent communications, dispute resolution. In Ain, there is an office for the project. In Hermel – rehabilitation of a spring area. In Bednayl provided a Crain for the Municipality. In Baalbek provision of medical equipment to the Lebanese Red Cross. The project will be expanded thanks to the outreach of community activities Chfat, Harent Hreik. 2 more years. New project with Embassy of Netherlands – Baalbeck Ain Chmistar Hermel Deir El Ahmar – Lebanese only to identify needs/ projects that could resolve issues between villages. 2 years. Peacebuilding strategy for Baalbeck area – aim at buildling the capacity of local NGOs and municipalities through providing training – Started in April for 8 months. Livelihoods: food security for vulnerable Lebanese families – providing 60 women with sheep in 4 areas. This has been ongoing for a while but will continue for 2 years. Women are often selling the milk or substituting purchase. This will be referred to FSS and FAO since it falls more in food security. IOM: Livelihoods Finished implementation for labour intensive projects and will work in new municipalities. 200 beneficiaries but municipalities not identified yet, pending election results SCI: Livelihoods – youth project starting in May funded by Japan. Very similar project to last year, focused on increasing employability Qab Elias, Marj, Madjel Anjar. Life skills and conflict sensitivity as well. Humanitarian training and community initiaties. Phase 2 of project with DFID – CSPs in North and West Bekaa. TBC Home based skills development, working on two new value chains. 150 in home based – 500 in cash for work. WFP: Starting a livelihoods project on agriculture livelihoods in partnership with Mercy Corps to improve food security and livelihoods. 1170 beneficiaries spread across 3 main components, first targeting 450 beneficiaries – targeting food insecure HH. Training on management of food resources and awareness. The second targets small farmers and goat farmers – in-kind packages and support, building on MC experience. Marketing support to producers and cooperatives to enhance the quality of their products. Refugees will work on packaging. Third component to target 300 beneficiaries: 80% Syrian - 20% Lebanese through labour intensive modalities to rehabilitate agricultural infrastructure with a view to increase food security and income productivity. Strong focus on developing sustainable agriculture (notably through permaculture). Targeting clusters with high food insecurity but will try to diversify and include North Bekaa and Rachaya. Coordination with MoA does not have a register for farmers but has one for herders and with MOSA through NPTP. The project will start this month and end in December 2016. Life: Livelihoods: Douris, Haoch Barada... training for women at home on handicraft – their products are later sent abroad. Starting new project near Baalbeck with Islamic Relief to do a training on water treatment, photography, hairdressing, computer classes and English classes, for all communities. 5 classes of 10 to 15 people for 6 months. People will receive certificates and can be provided with opportunities abroad (Africa). Life also works in education, health... ALEF – Social stability: Alef works in Marj area with a group of Lebanese and Syrians who will identify common issues for advocacy purposes – 12 Syrians and 7 Lebanese. To coordinate with DRC and interested partners. AMEL – no project so far but start in Arsal and Al Ain. They will start a LH project focusing on providing vocational training for Syrian and Lebanese youth between 15 and 30. UNDP – MRR phase 3 are being completed Livelihoods: community kitchen in Bar elias, Public market Ghazze and Sadnayel. Social stability project include infrastructures throughout the Bekaa. Peacebuilding project is supporting through small grants for the social-cultural committees to take initiatives (creation of a school of music in Bar Elias, painting in Majdel Anjar…). |
| 4 | - AOB Field coordinator highlighted the importance for partners to provide brief updates on their activities and projects in the LH and SoST sectors prior to the monthly IA meeting. LOST Shared invitation for an event organized on 17 May. Next LH&SOST WG meeting will be held in Bekaa on 14 June 2016. |