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Minutes of Health & Nutrition Working Group Meeting/ South
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	List of participants


	Organization
	Name
	Position
	Telephone
	E-mail

	IA-UNHCR
	Hala Abou Farhat
	Health Coordinator
	03-183067
	aboufarh@unhcr.org


	WHO
	Edwina Zoghbi
	Public Health Officer
	03-815727
	zoghbie@who.int


	AMEL
	Lama Youssef
	Field Coordinator
	70/797712
	south@amel.org

	IOM
	Rana Amer
	Health Team Leader South
	76/777139
	ramer@iom.int

	ICRC
	Aoife Kenny
	Health Delegate
	71/802892
	akenny@icrc.org 

	ICRC
	Faten Al Ali
	Health Officer
	71/802875
	falali@icrc.org

	PU-AMI
	Rasha Al-Askar
	
	03-530438
	Lib.pm-health.sai@pu-ami.org


	UNICEF-Beirut
	Carina McCabe
	Health & Nutrition, Beirut


	76-774421
	cmccabe@unicef.org


	UNICEF-Tyre
	Rouham Yamout
	Health & Nutrition, Tyre

	81-696985
	ryamout@unicef.org


	IMC
	Fatima Aoun
	
	76-172618
	faoun@internationalmedicalcorps.org



Agenda of the Meeting
· LCRP 2016 Health Sector Overview: Process & Results Framework
· Preparing for reporting: Indicators and Disaggregation

· MMU Mapping
· AOB
Summary of discussions and action points

	No.
	Issue
	Focal Point
	Deadline

	1.
	LCRP 2016 Health Sector Overview (refer to ppt)
· The 2016 Lebanon Crisis Response Plan (LCRP) was launched on the 17th of December 2015 after 4 months of extensive meetings and consultations with Health sector stakeholders to determine priorities for the sector in 2016 as well as funding requirements
· Health Sector funding requirement is 290 Million USD of 2.48 billion required by all sectors.
· Health outcomes are more or less the same compared to LCRP 2015 outcomes. One outcome relative to transparency and accountability of health partners has been added.
Comment:
· UNICEF: UNICEF also expressed interest under Output “Vaccination Campaigns” but does not show as a partner under this output.
       Action Point: Hala to look into that.

	Hala Abou Farhat
	

	2. 
	Preparing for reporting: Indicators and Disaggregation (refer to word doc)
· Organizations are to familiarize themselves with 2016 AI indicators as well as disaggregation in preparation for January reporting
· Non-LCRP partners are also encourage to report on AI to have a clearer idea of health landscape

                       Action Point: Organizations reporting on AI are to make sure that data collected at field 

                       level captures population cohort (DisSyr, LEB, PRL or PRS), sex (male, female), age group (0-4, 

                       5-17, 18-59 and >60).

	Hala Abou Farhat

	

	3.
	MMU Mapping

· Organizations providing health services through MMUs are to enter or update their MMUs-related information on AI. This exercise is to be finalized by end of January.
· Contact Hala or Maroun to be provided access to “Public-Health Services” under which MMU data is mapped

	Hala Abou Farhat

and
Maroun Sader (IM)
	

	4.
	Reminders:
· To receive Health Sector related communication kindly sign-up to the Inter-Agency (IA) mainling/contact list by following this link http://unhcr.us7.listmanage.com/subscribe?u=8173eed01e68ce76256aba23b&id=210887bf3a
· Individuals who wish to unsubscribe for the IA mailing/contact list are to follow this link http://unhcr.us7.listmanage.com/unsubscribe?u=8173eed01e68ce76256aba23b&id=210887bf3a.
	
	

	5.
	AOB
· UNICEF is in the preparation phase for the polio vaccination campaigns
· Amel Association have a new project funded by AFD for 1 year and a half. It will have a MMU component in Marjeyoun and Tyre. Starting January 16th there will be an assessment for 2 potential PHC centers in Halta and Fardis to be operational as of June 2016.
· Scabies+ Lice Outbreak in the Pepsi/Akbieh shelter with 1,000 refugees: Blue Mission/Islamic Relief targeted the lice issue, and completed the necessary intervention. The response to Scabies is still being planned in detail as it entails a large and multi-sectorial response, with ICRC/LRC following up on the medical intervention. 


	
	


Next Meeting will be held on Thursday 4 February, 2016 at 12.30 in UNHCR, Tyre Office
For any queries, please contact:  
Reem Mdeihly
E-mail: mdeihly@unhcr.org 

Mobile: 76/ 421 638
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