## Sheet1
WASH WG Projects and activities for 2016
Agency/Partner | no. | Activity | % funded | Location | Sub-activities | Jan | Feb | March | April | May | June | July | Aug | Sep | Oct | Nov | Dec | 2017 | 2018 | 2019
UNICEF | 1 | Government and WASH sector partners plan and optimally utilize WASH resources and services for equitable access |  |  | Support the development of comprehensive WASH Master Plan aligned to national priority (JRP), integrating the impact of Syrian Crisis Impact. Technical support to MWI such as GIS mapping, strategic planning and enhancement of their monitoring capacity.
Support sector coordination efforts, e.g. WASH Task Force as the Secretariat and part of the WASH Core Team, provide capacity development and technical support to assessments and surveys, support MOE in WASH in Schools.
Provide support to household through means such as water storage capacity enhancement and leak repairs.
Improve and extension of water systems to increase water quantity and reduce water losses
Provide water, sanitation and hygiene package/services to the schools in host communities
Improvement and extension of Sewerage network in host communities
Enhancement of monitoring capacity for all WASH intervention with partners at camps and host communities
Evaluation for the Water, Sanitation and Hygiene programme in camps and host communities from 2012-2014
| 2 | Children, parents and community members are aware of and practice hygiene and water conservation |  |  | Support hygiene promotion and communication for development activities, and provide HP kits in camps
Support hygiene promotion and communication for development activities, and provide HP kits in host communities
Provide hygiene promotion at targeted schools in camps and host communities including provision of student HP Kits
Carry out KAP, and surveys to assess behavior changes in hygiene practices in camps, host communities and schools
|  | Urgent needs of vulnerable people especially children are met through quality and lifesaving WASH services |  | Zaatari ,Azraq,KAP &CC | Provide refugees in camps with safe access to sufficient water for drinking through trucking and at the ITS
|  |  |  | Zaatari | Establish a water supply network for the camps to ensure proper and cost effective access to safe water as per the required standards to refugees
Provide safe access to proper sanitation through waste water disposal through dislodging, including the ITS
|  |  |  | Zaatari | Complete of the wastewater treatment facilities at the camps and the re-use portion
| 3 |  |  |  | Establish a sewage network for the camps to ensure proper and cost effective access to safe waste water disposal as per the required standards to refugees and to safe environment.
Support the solid waste disposal system and support local authorities to enhance their capacity to handle solid waste at the camps
Support the community maintenance and operations activities at the camps and the maintenance and operations to the Water resources and Sanitation facilities
Provide water, sanitation and hygiene package/services to the schools at the camps
Emergency preparedness and contingency planning to respond quickly and effectively to unexpected events
OXFAM |  | Rehabilitattion of Wash facilities at the HH level | 100% Comic Relief | Balqa & Zarqa | Rehabilitattion of 500 Wash facilities at the HH level.
|  | Rehabilitation of Borehole | 100% Oxfam Appeal | Mafraq | Rehabilitation of Borehole / Replacment of well
|  | Rehabilitation of Borehole | 100%Irish Aid | Balqa | Rehabilitation of Borehole / Manitinanace
|  | Hygiene Vouchers |  | Balqa and Zarqa | Distribution of Hygiene, Baby and Comfort vouchers
|  | Child to child Kit |  |  | Hygiene promotion Child to Child Kits
|  | 1. Reduction in leaks and malfunctions in domestic water networks in Russayfa city (Naqab area) | 100% DFATD | Russayfa/Zarqa | 1.1 Technical and Feasibility study conducted for potential network rehabilitation
1.2 Domestic water network rehabilitated / repaired in the target communities
|  | 2. Increased ability of water utility personnel to anticipate, prevent and respond to water system breakdown and malfunctions | 100% DFATD | Miyahuna/ Zarqa, WAJ/Balqa | 2.1 Assessment of water utility capacity carried out to detect and monitor leaks
2.2 Water technicians trained on operational and maintenance in water system operations
|  | 3. Increased participation of Zarqa and Balqa communities, especially women, in efficient water management | 100% DFATD | Russayfa/ Zarqa and Allan/ Balqa
World Vision | 1 | Stormwater drainage network design in Zatari | 100% (WV Korea) | Zatari Camp | Data Collection, Mapping of camp, Mapping of existing stormwater system and related utilities, Feasibility Study with schematic designs including optional design approach with cost estimate of each option
Preliminary design
Detailed design, preparation of tender documentation
| 2 | Implemention of storm water drainage works | 100% (OCHA) | Zatari Camp | Rehabilitation of part of the storm water drainage netwerk in Zatari
| 3 | Wash Cash Project | 100% (DFATD) | Amman, Irbid and Mafraq | Rehabilitation of water and sanitaion facilities in schools (34)
Capacity building on hygiene practices at school communities and care givers (34 schools).
Cash transfer to selected beneficiaries and installation of water tanks at HH-level (612) and water dispensers in schools (64).
ACF | 1 | Support for WASH services in Azraq camp | 100% (Funded by UNICEF) | Azraq camp | Undertake Social Mobilisation activities | Continous activity
[5 empty] | Undertake operation and maintenance (O&M) of the WASH facilities | Continous activity
Construct additional tapstands
Provide kits, training and oversight to WASH committees
Upgrade WASH blocks in Village 5 by installing ceramic seat
Culverts maintenance
Installation of WASH facilities at the public area to cater for refugee influx
Installation of grey water network as apilot project
| 2 | Connecting Vulnerable Households to public water supply system (**Subject to funding approval) | 0% (To be funded by UNICEF) | Irbid Governorate | Houshold connections to public network
Dissemination of water conservation measures to newly connected households
Capacity building of Yarmouk water company staff on capacity building
| 3 | Providing Lebanese and Jordanian communities hosting Syrian refugees with improved WASH infrastructure and facilities at community, institution, and household level. (**Subject to funding approval) | 0% To be funded by EU_Madad | Irbid Governorate | Improving water and sanitation infrastructure
Institutional strengthening of water authorities / establishments
Improve WASH facilities in public institutions.
Rehabilitations and upgrades are conducted to improve WASH standards in targeted households
NRC | 1 | Construction of 7 WASH blocks in Jordan public schools | 100% | Irbid governorate | Construction of WASH blocks, Water re-use system, maintenance support
| 2 | Construction of 6 WASH blocks in Jordan public schools | 0 | Northern Jordan | Construction of WASH blocks, Water re-use system, maintenance support
| 3 | Hygiene awareness activities in 3 schools | 100% | Irbid governorate
Mercy Corps | 1 | Rehabilitation and strengthening of water networks | 100% | Mafraq | Construction activities, pipes installation and testing
| 2 | Rehabilitation and strengthening of water networks | 100% | Irbid | Rehabilitation of water network
| 3 | Rehabilitation and strengthening of water networks | 100% | Jarash | Rehabilitation of water network
| 4 | Installation of wastewater networks | 100% | Balqa | construction works and installation of wastewater pipelines
JEN | 1 | Construct WWN in D3 and D4 | 100% | D3, D4 | Install 2, 4 and 8 m3 tanks at appropriate locations
Install piping from 2,4 and 8m3 tanks toward HHs
Install HH connections to the pipes/tanks
Install private toilets for the most vulnerable HHs
|  |  |  | D3, D4 , D5 | Support safety messaging and actions around construction
|  |  |  | D3, D4, D5 | Support HHs with tools and knowledge shareing to maintin the WWN
| 2 | Upgrade of HH toilets for vulnerable families | 100% | D3, D4, D5 | Round 2 of private toilet upgrades
Round 3 of private toilet upgrades
| 3 | Disinfection of public use water tanks | 100% | D3, D4, D5 | Public Water tank disinfections
Organization Water tank disinfections
| 4 | Disinfection of private water tanks | 100% | D3, D4, D5 | Disinfect private water tanks
| 5 | Decomissions public WASH blocks | 100% | D3, D4, D5 | Cancel WASH committees
Remove WASH block sturcture
| 6 | Convert WASH block space in to public use space | 100% | all districts | Convert 1 former WASH block/distict into usable space for the community.
| 7 | Hygiene Promotion Activities | 100% | D3, D4, D5 | Train CHPs to provided messages around the community
CHPs offer HP sessions in community
JEN staff offers sessions in the community
JEN staff offers limited childrens activities regarding HP message
| 8 | Support construction of water network | 100% | D3, D4, D5 | Provide Safety messaging regarding water network safety
| 9 | Solid Waste Management - Stree Cleaning | 100% | D3, D4, D5 | Manage street cleaning in D3, D4 and D5.
| 10 | Annual WASH KAP Survey | 100% | all districts | Support conduct of annual WASH KAP survey development,
support data collection
support analysis and reporting
LWF | 1 | Rehabilitation of 60 WASH block | 100% | Irbid Governorate | MoPIC approval
Assessments & schools selection
Stakeholders approvals
Tendering
Implementation and monitoring
Handing Over
| 2 | Construction of 15 WASH block | 100% | Irbid Governorate | MoPIC approval
Assessments & schools selection
Stakeholders approvals
Designing & tendering
implementation and monitoring
Handing Over
| 3 | Hygiene awareness sessions | 100% | Irbid Governorate | Training material preperation
[5 empty] | Staff training | [12 empty] | Refreshment training
ACTED | 1 | Water Supply | 100% | Za'atari, KAP and CC, Azraq | Water trucking:
|  |  | 100% | Za'atari, KAP and CC, Azraq | Water quality control and testing:
|  |  |  | Azraq | Operation and maintenance of water network:
| 2 | Solid Waste management and camp cleaning |  | Za'atari, KAP and CC | Solid waste management:
|  |  |  | Za'atari, KAP and CC | Cash for Work Schemes
| 3 | Social Mobilisation | 100% | Za'atari | Support for the implementation of the water distribution and monitoring mechanism:
Building the capacity of WASH committees:
Social mobilisation messaging:
| 4 | Repair and Maintenance: | 100% | Za'atari, KAP and CC | Continuation of support to capacity building of WASH committees for Tier 1 repairs, Tier 2 repairs in ACTED districts and Tier 3 at camp level and general maintenance of facilities in KAP and CC:
|  |  |  | Za'atari | Backfilling of medium and small holes:
Maintenance of waste bins:
Repair, replacement, and disinfection of water tanks.
| 5 | Water Supply Network | 100% | Za'atari | Water network topographical survey and engineering design:
Water network construction:
Community Engagement:
| 6 | Wastewater Network | 100% | Za'atari | Construction of a fully functional interim wastewater network.
| 7 | Desludging of camp facilities: | 100% | Azraq | Desludging of wastewater holding tanks:
| 8 | Solid waste management and camp cleaning: | 100% | Azraq | Garbage removal:
|  |  | 100% | Azraq | Camp cleaning:
|  |  | 100% | Azraq | Solid waste superstructure at informal markets:
| 9 | School cleaning | 100% | Azraq | Repair and maintenance of school WASH facilities:
School cleaning
| 10 | Social Mobilisation | 100% | Host Communities | Diverse activities in schools
| 11 | Water management | 100% | Host Communities/ VOC | Distribute and repair water tanks
Water filters
| 12 | Solid Waste management | 100% | Host Communities/ VOC | Installation of pit latrines
| 13 | Hygiene promotion | 100% | Host Communities/ VOC | Sessions on hygiene + distribution of hygiene kits
| 14 | 11 targeted communities in Jordan and 25 communities in Lebanon benefit from improved water and sanitation infrastructure, including repairing, rehabilitating, upgrading and extending water supply and sanitation networks. | 100% | Irbid | Identification of water and sanitation infrastructure assets for rehabilitation
Rehabilitation of identified community infrastructural assets
| 15 | Quality and sustainability of water and waste-water management improved in target communities through institutional strengthening of water authorities / establishments in Jordan and Lebanon. | 100% | Irbid | Capacity assessments and design of capacity building plan:
Development of O&M plan and capacity building
Additional Capacity building
| 16 | WASH facilities in 30 public institutions in Jordan and 32 institutions in Lebanon such as schools (including informal schools), prisons, CBOs, health centres, and child friendly spaces are improved to meet minimum standards in terms of quantity, quality, safety, and hygiene, as well as equal access to girls, boys, men, and women, including persons with special needs. | 100% | Irbid | Identification of proposed sites.
Site needs assessments and development of a technical site plan
Implementation of works by contractors with Consortia oversight
| 17 | Committee formed in Jordan and Lebanon to ensure ongoing repair and maintenance of works as well as community outreach (such as Healthy Clubs) in 30 institutions in Jordan and 32 institutions in Lebanon. | 100% | Irbid | Establishment of WASH committees:
Training of wash committees and development of an O&M plan
Hygiene promotion and community mobilisation through committees
| 18 | WASH minimum standards are met in 1200 targeted households in Jordan to ensure hygienic and dignified living environments for vulnerable Jordanians and Syrian refugees. | 100% | Irbid | Identification of households
Rehabilitation of identified WASH infrastructure
Basic training on maintenance and repair to targeted households
| 19 | Shelter related legal assistance is provided to 1200 households in Jordan. | 100% | Irbid | Legal aid to refugee households
Referrals to shelter actor
| 20 | Hygiene promotion and information events held for 1200 households in Jordan and 59,000 households in Lebanon | 100% | Irbid | Knowledge, Aptitude and Practice (KAP) surveys
Hygiene promotion activities in communities
National media campaign in Lebanon:
Establishment of women’s plumbers clubs:
ICMC | 1 | Distribution of House Cleaning Kits and Hygiene Promotion Materials | 70% | Mafraq, Irbid, Zarqa, Jerash, Ajloun, Balqa, Madaba | Design and production of hygiene promotion materials according to FGD feedback
Revision of HCK content according to PDM and FGD feedback
Beneficiary selection through outreach and assessment
Distributions
Post-distribution monitoring
| 2 | Distribution of Baby Hygiene Kits and Hygiene Promotion Materials | 70% | Mafraq, Irbid, Zarqa, Jerash, Ajloun, Balqa, Madaba | Design and production of hygiene promotion materials according to FGD feedback
Revision of BHK content according to PDM and FGD feedback
Beneficiary selection through outreach and assessment
Distributions
Post-distribution monitoring
| 3 | Distribution of Personal Hygiene Kits and Hygiene Promotion Materials | 70% | Mafraq | Design and production of hygiene promotion materials according to FGD feedback
Revision of PHK content according to PDM and FGD feedback
Beneficiary selection through outreach and assessment
Distributions
Post-distribution monitoring
2016
Note on D127: Philippine: Conditional upon start date. Estimated beginning of June.
Note on C141: Philippine: ACTED is respnsible for 400 households out of the total 1200 HH.