## Sheet1
Tasks / Activities
Week 1 | Oct 4th (W) | LCRP 2018 Planning: 1st Health Sector Core Group Meeting
| Oct 5th (Th) | Field Consultation / South (Confirmed)
| Oct 6th (F) | LCRP 2018 Multi-Stakeholder Workshop
Week 2 | Oct 9th (M)
| Oct 10th (T) | 1) RBM Workshop 2) Draft Situation Analysis submitted to Inter-Sector
| Oct 11th (W) | LCRP 2018 Planning: 2nd Health Sector Core Group Meeting (Confirmed 12:00-2:00 pm)
| Oct 12th (Th) | Field Consultation / North (Confirmed)
| Oct 13th (F) | Field Consultation / Bekaa (TBC)
Week 3 | Oct 16th (M) | Field Consultation / BML (TBC)
| Oct 17th (T) | Draft Health Sector Plan submitted to Inter-Sector
Oct 18th (W)
| Oct 19th-20th (Th-F) | Inter-Sector Workshop
Week 4 | Oct 23rd (M) | Inter-sector feedback to sector response plans
| Oct 27th (F) | 1) Sectors submit revised sector response plan to Health Sector Steering Committee 2) Deadline for expression of Interest
Week 5 | Oct 30th (M) | Health Sector Steering Committee Meeting (TBC)
| Oct 31st (T) | Draft Health Chapter Finalized
Week 7 | Nov 17th (F) | Deadline for submission of partner financial appeals