## Guide
Blue bold | Required activities
Orange text | From 2014 workplan (items that were completed, or already included this year not shown)
Workshop ranking | For groups that suggested an order for activities
Overlap-Duplicates | some activities are quite similar, flagging for consideration in one/other/or both
Priorities
1,2,3 | rank in order
1a, 1b, 1c | if activities are linked to one another, give letter order

## CPiE workshop inputs
Child Protection in Emergencies Working group - National Workplan 2018
Area | Task | Responsible (actors) | When |  |  | Status
|  |  | Q2 | Q3 | Q4
Coordination | Support and Assist MoSA in the leadership of the CPiEWG work | Nat/Field CP Coordinators |  |  |  | on-going
| Ensure coordination with other working groups /task forces/technical sub-working groups | National / Field CPiEWGs |  |  |  | on-going
| Coordinate service mapping- field-level gap and overlap analysis | National / Field CPiEWGs |  |  |  | on-going
| Review / strengthen data collection tools | National / Field CPiEWGs |  |  |  | on-going
Strategy and Planning | Conduct yearly planning workshop and complete 2018 National Workplan | National / Field CPiEWGs
Complete LCRP Mid-Year Review
Complete LCRP planning for 2019
Facilitate cross-sector linkages
Strengthen CP contingency plan
CP Minimum Standards | Seek endorsement of Standards with relevant Ministries / GoL | Nat CP Coordinator
| Launching of contextualized Standards at National and field levels | National / Field CPiEWGs
Case Management | Support CPIMS roll out and implementation | CMTF members
Support convergence of National SOPs and practical guidance note
Strengthen coordination and collaborative with MoSA on CM
Support implementation of recommendations from interim shelter and alt. care mission
Develop comms tools for communities on CM
Finalise guidelines on use of cash in CM
Collaborate in BTS campaign
Develop and roll out M&E tool for CM
PSS | Focused PSS Toolbox Translation and roll out | PSS Committee Members
SDQ update
Rolling out of community based Toolkit
PSS guidelines updated
Community based CP- compile resources/ share aseessment on social change
Ensuring PSS implemented activities are inclusive
Strengthen collaboration with MHPSS
Caregivers and Engaging males - review practices and lessons learnt
CP / GBV | Finalise CP/GBV coordination guidance note and diseminate | CP/GBV platform
| Survey and checklist developed on PSEA and CP for CP partners and sub partners | CPWG - Nat and field
| Support development of CM tool kit for Lebanon | CPWG - Nat and field
| Develop survey to assess effectiveness of CP Sector trainings (SOPs, SDQ, FPSS etc) | CPWG - Nat and field
Advocacy | Determine and implement key advcocacy actions J4C, Violent Discipline, Child labor | CPWG- Nat and field
Conduct thematic meetings on each topic with other relevant sectors
Develop key advocacy messages on each topic

## Sheet2
Strategy & Planning
Policy & Guidance
Assessments
Monitoring & Reporting
Mapping & Analysis
Emergency Preparedness
Advocacy & Resource Mobilisation
Cross-Cutting
Training & Capacity Building