| TITLE OF THE COORDINATION MEETING : Bekaa Health Coordination Meeting |  |  |  |
| --- | --- | --- | --- |
| Date | 26 April 2018 | Time | 11:00-12:40 |
| Location | UNHCR Zahle premises | Duration | 1h and 40 min |
| Chair | Mona Kiwan-UNHCR |  |  |
| Attendance |  |  |  |

| Name | Organization | Email address | Phone Number |
| --- | --- | --- | --- |
| Nathalie Mazloum | MOSA | natalymazloum90@outlook.com | 70707833 |
| Hala Abou Farhat | IA/UNHCR | aboufarhat@unhcr.org | 3183067 |
| Stephanie Laba | UNICEF | slaba@unicef.org | 76 77 44 27 |
| Edwina Zoghbie | WHO | zoghbie@who.int | 03 815727 |
| Jessy Gedeon | IOM | jgedeon@iom.int | 76 777431 |
| Hussein Zreik | Relief International | hussein.zreik@ri.org | 81759893 |
| Marshall Tuck | ICRC | mtuck@icrc.org | 70 259122 |
| Maria Stacke | FPS | maria.stacke@gmail.com | 70423988 |
| Roland Hassel | Humedica | r.hassel@humedica.org | 76 065 117 |
| Dr Bassem Al Qalleeh | URDA-MCA (Al Rahma Hospital) | basem.alqalleeh@urda.org.lb | 76426878 |
| Omar Ajamy | IMC | oajamy@InternationalMedicalCorps.org | 76 838004 |
| Mona Sabra | IMC | msabra@InternationalMedicalCorps.org | 81 767733 |
| Jana Sarout | IOCC | Jsarout@iocc.org | 70196340 |
| Merhe Fliti | Amel | meriifliti@hotmail.com | 71813880 |
| Elias ABI AAD | MSF B | msfocb-barelias-coord@brussels.msf.org | 03 105 269 |
| Laurence | MSF-fr | msff-zahle-eam@paris.msf.og |  |
| Sachin Desai | MSF-fr | msff-bekaa-med@paris.msf.org | 78930312 |
| Ola El Khatib | MSF-fr | msff-Bekaa-socialworker@paris.msf.org | 71447760 |
| Sahar Bahadi | WAHA | medco.liban@waha-international.org | 81616875 |
| Christine Broby | Heart For Lebanon | christine.broby@heartforlebanon.org | 76 814256 |
| Khalil Zarzour | MTI | kzarzour@medicalteams.org | 71359876 |
| Samira Youssef | MTI | CHP7@medicalteams.org | 71330295 |
| Dr Ibrahim Saleh | Medair | health-manager-zah@medair.org | 76890143 |
| Olfat Mohammad | ACF | molfat@lb.acfspain.org | 76 656628 |
| Nagham Faour | ACF | nfaour@lb.acfspain.org | 76462342 |
| Rola Al Abdallah | ACF | rabdallah@lb.acfspain.org | 71121566 |
| Noel Awad | Insan | nawad@insanlb.org | 76044609 |
| Nisrin Dibian | Insan | ndibian@insanlb.org | 03897405 |
| Mona Kiwan | UNHCR | mkiwan@unhcr.org | 79160198 |
| Rajaa Halabi | UNHCR | halabi@unhcr.org | 76421565 |

| 1.0 | INTRODUCTION/ PURPOSE OF MEETING | ACTION | DUE DATE |
| --- | --- | --- | --- |
| 1.1 | Monthly health and Nutrition working group meeting |  |  |
| 2.0 | Registration Updates (as of 23 April 2018) | ACTION | DUE DATE |
| 2.1 | -Bekaa total individuals registered : 361,224 HH: 79,235 -Zahle: 160 706, Baalbeck: 118 776, West Bekaa: 62 318, Rachaya:8 505, Hermel: 6 376 **HFL reported that among the barriers for not getting recorded with UNHCR is the HH illegal status who have misconception and fear for showing up. | NGO to promote the need to call the reception centre to get appointment to be recorded |  |
| 3.0 | Epidemiology update Lebanese and Syrian Refugees/ Great Bekaa) |  |  |
| 3.1 | Report measles available on MoPH-ESU website |  |  |
| 4.0 | AIA & Measles incidence and response update | ACTION | DUE DATE |
| 4.1 | -Presentation including numbers as of April 18, 2018 in addition to the Ministry of Public Health - Epidemiological Surveillance Descriptive Findings Report will be shared with the minutes of meeting - Facebook link of the Measles video shared by the Ministry of Public Health on the Primary Healthcare Lebanon page. https://www.facebook.com/PHCLebanon/videos/1610426572326812/ -UNICEF will share UNHCR Key messages in Arabic to be posted through social medias sites (including refugee website) -Measles Brochures developed by MoPH/WHO will be shared ready Next week |  |  |
| 5.0 | IOM Global Fund project IOM presentation: Middle East Response To Tuberculosis, HIV/AIDS and Malaria (shared with the minutes) | ACTION | DUE DATE |
| 5.1 | -IOM will be sharing the updated contact list for TB referral -IOM supporting the HIV counselling & testing |  |  |
| 6.0 | Community Health Workers/ Health Outreach volunteers Bekaa workshop- Recommendations follow up | ACTION | DUE DATE |
| 6.1 | A sub working group will be created: *Chaired by MTI (Samira Youssef) *Co-chaired by IMC (Mona Sabra) Meeting between UNHCR/MTI/IMC to discuss the Sub Working group TOR -Health OV Mapping: data still needed from URDA-SAMS and MSF-ch |  |  |
| 7.0 | BHWG co-chair | ACTION | DUE DATE |
| 7.1 | Co-chair: RI replied following the meeting that they accept to co-chair the BHWG |  |  |
| 8.0 | Dialysis Funding updates | ACTION | DUE DATE |
| 8.1 | No updates |  |  |
| 9.0 | Partners/ Programs updates and challenges | ACTION | DUE DATE |
| 9.1 | Humedica: -50% change in the IS coverage/ assessing new sites -Assessing health center for potential support (IOM suggested Taalabaya health center ) | Any Suggestions to add IS to be kindly shared with Roland | April/May 2018 |
| 9.2 | MSF fr: running 4 PQ beds and 18 Ped bed at Zahle Gov Hospital |  |  |
| 9.3 | IMC: signed the agreement with MOSA-SDC Baalbeck and will resume the support as of May first 2018 |  |  |
| 10.0 | Contingency Plan/stocks | ACTION | DUE DATE |
| 10.1 | -UNHCR will share the updated inter-agency Health Contingency plan with the minutes -Activity Info will be reviewed for Contingency Stock update |  |  |
| 11.0 | Referral care updates | ACTION | DUE DATE |
| 11.1 | MSF-B field hospital: -Will be inaugurated by end of July 2018 (if no change to the plan) -MSF-B admission and exclusion criteria in addition to the Referral form will be attached to the minutes. -Further explanations about opening date, criteria, and referrals will be shared with all partners in the near future. |  |  |
| 11.2 | Nextcare Hospital Network: *Rayak, Manara, and Chtaura hospitals will be cut from the network by the end of April 2018 *Kherbet Kanafar Gov Hospital added to the network as of April First 2018 *Taanayel General Hospital will be added to the network as of May First 2018 |  |  |
| 12.0 | AOB | ACTION | DUE DATE |
| 12.1 | Vital Data Observatory (VDO): Dashboard 2017 MoPH developed an online system for reporting deliveries and maternal and neonatal health outcomes |  |  |
| 12.2 | MdM proposed an initiative and along with IA Health coordinator (Hala Abou Farhat) are discussing an approach to harmonize the support of PHCs/ Building the capacity of the PHCs among all Partners | More information will be disseminated soon |  |
| 12.3 | AUB Invitation: Humanitarian Aid Agencies and Non-Governmental Organizations (NGOs) engagement meeting on mapping the health needs of Syrian Refugees residing in Lebanon- May Second 2018 |  |  |