| PUBLIC HEALTH SECTOR – UNHCR WEEKLY TEAM MEETING 9th July 2018 Time: 8:30 AM Monday Venue: UNHCR office Attendance: Dr. Julius, Dr. Ronald, Ibrahim, Emmanuel, Ahmed Chaired by: Dr. Julius |  |
| --- | --- |
| Sub-sector updates | Actions & way forward |
| RH & HIV – Ronald - Had a meeting with JPIAGO to discuss RH issues, discussed Fistula - RH performance shared with high neonatal rates in some locations | - Cervical cancer screening & Treatment data - Emmanuel - Need to track HPV vaccination implementation in settlements –Emmanuel - Need to get data on Fistula from settlements- Emma - IGAD reporting by 20th of the month – July - Will meet Marie stopes and RHU - Pepfar - Need to organise circumcision camps to increase coverage |
| Pharmacy & Medical logistics – Ahmed - A balance of the LLIN to be redistributed - 2019 quantification received - 60% NDA clearance received - Redistribution from AIRD will be done this week - Planning a mission from 9th to 25th in SW & MD | - Ahmed to provide summary indicators for Pharmacy to be included on the monthly indicators - Julius - Follow up on Ebola items - Review partners orders before they purchase medicines |
| Health Information – Emmanuel - Follow up on PEPFAR reporting | - Organise monthly meetings to discuss Monthly reports – Friday before 15th - Follow up on Uganda EMR report from MoH - Follow up on Master facility list - VHT reporting tool piloting |
| Public health - Ibrahim - Meeting AMREF - Ministry introduced rotavirus vaccines - Quantifications for 2019 - LLINs distribution on going in all settlements - VHT pilot not kicked off well - Mid-year review coming up | - Follow up with IM on fact sheet and website design to include over view – Emmanuel |
| Julius - Had a management meeting last week and staff reduction was discussed and organogram will not change - Coordination meeting tomorrow at MoH - KW meeting in the week - Cholera vaccine started and will be extended due to low coverage | - Gaps data should be ready before Wednesday – Emmanuel - Every survey will have refugee component in Uganda - Cholera vaccination will be intensified |

Compiled by: Emmanuel Omwony