|  |  |
| --- | --- |
| **PUBLIC HEALTH SECTOR – UNHCR**  **WEEKLY TEAM MEETING**  **2nd July 2018**  **Time:** 8:30 AM Monday  **Venue:** UNHCR office  **Attendance:** Dr. Julius, Dr. Ronald, Ibrahim, Emmanuel, Ahmed & Isaac  **Chaired by:** Dr. Julius | |
| **Sub-sector updates** | **Actions & way forward** |
| **PH – Ibrahim**   * Meeting at UNICEF to fill the gaps in Ebola response * Red cross will take up Kanungu and Kisoro, support WASH partners in transit centers and receptions * UNICEF would support partner trainings on Ebola * Unicef to support waste management facilities * MoH proposes to use EBOLA vaccine in Uganda but only for study purposes. * WHO supplied Ebola RDTs to UVRI and will also be supplied to other settlements * NO VHF tested positive in Mubende following the scare of Ebola outbreak * Need to develop SOPs for disinfecting registration equipment at the boarder points * Partners are procuring medicines which UNHCR also has some * Discussed the VHT voucher scheme * Multi-antigen campaigns to kick off | * Uganda red cross planned to train, community awareness and boarder screening |
| **RH & HIV – Ronald**   * HTS meeting was held with IPs (AHA & MTI). Assisted partner notification but challenges were lack of trainings for the identifiers and lack of tools * Had a mission to West Nile with IGAD to revere performance * Much of the IGAD funds have not been used since they were received late * UNFPA set up regional points to do FP,,, | * Should use trained cadres for APN * MoH will share the tools for APN * Kyaka to organise VMMC camps |
| **Pharmacy & Medical logistics – Ahmed**   * Low stocks of tracer medicines across settlements * Finalised technical review for local procurement * Monthly stock status report available * Need to revise essential medicines list * Shared a memo on redistribution of medicines * Medical equipment are non-functional in settlements | * Need to have an inventory management of medical equipment * Should share monthly stock status report by Wednesday 15th together with the HIS reports |
| **Health Information – Emmanuel**   * HIS mission in West Nile (Bidibidi and Palorinya) and lack of tools & poor documentation were major issues. Rolled out VHT reporting tools and followed up with referral database * Had a protection meeting at IAU and there were many non-medical cases residing at the medical hostel. Delays in processing funds was a challenge as well. * Submitted Pepfar reports for Q3 * 6 measles cases in Kyangwali and need follow up   This week:   * Compile and submit HIS reports and have a discussion on Tuesday Afternoon * Compile and share VHT reports from Bidibidi and Palorinya were the pilot is taking place * Will share the referral database as well * Fact sheet completed by Friday | * Update twine with outbreaks * Share surveillance data * Update the gaps matrix |
| **Public health - Isaac**   * Attended review or IMAM guidelines * FSNA preparation on going * Results for mass nutrition screening has been released for Kyangwali * Commodity reports for RUTF received is needed | * Follow up on JAM * Conduct FSANA in October and share results table by November 2018 * Share results of the Mass nutrition screening in Kyangwali |
| **Julius**   * ANN Burton is coming to the country, advocacy and address challenges. Will visit locations of rift valley fever. * Conference on Wednesday and Thursday at Serena * Training on mental health * Had a mission on Ebola preparedness in SW * An audit on coordination, monitoring and import * Regional public health meeting will be held in Uganda and possibly all will attend | * Prepare mission reports, weekly, monthly reports and minutes of coordination meetings for the audit team and file them – Emmanuel * Ibrahim to attend the mental health training |

**Compiled by**: Emmanuel Omwony