## 2018 Workplan
Health Sector 2019 Workplan
Action Identified | Key Activities/Outcomes | Status | Timeline | Responsible
Health Services Mapping / Coverage & Information Dissemination | Ensure the Health Sector 5Ws is updated on a regular basis and shared with partners | Ongoing | Last Updated: February 2019 | Stephanie Laba (UNHCR-IA)
| Ensure the PHC Masterlist is updated on a regular basis and shared with partners | Ongoing | Last Updated: April 2019 | Stephanie Laba (UNHCR-IA)
| Ensure the Mobile Medical Units (MMUs) mapping is updated on a regular basis and shared with partners | Ongoing | Last Updated: February 2019 | Stephanie Laba (UNHCR-IA)
| Ensure the Health Gateways Dynamic Map are updated on a regular basis | Ongoing | To be finalized: May 2019 | Stephanie Laba (UNHCR-IA) Maroun Sader (UNHCR-IA)
| Prepare a list of partners supporting access to hospital care/SHC to be shared with partners | Pending | To be finalized: May 2019 | Stephanie Laba (UNHCR-IA)
| Prepare a presentation targeting non-health partners on Access to Health Services and referral pathways | Pending | To be finalized: June 2019 | Stephanie Laba (UNHCR-IA)
| Ensure the updated Health Leaflets and list of UNHCR/NEXtCARE hospitals are shared on a regular basis with partners and frontliners | Ongoing | Last Updated: April 2019 | Stephanie Laba (UNHCR-IA)
Engaging with communities | Support UNHCR Communication with Communities Unit is producing updated Health Leaflets on a regular basis and shared with partners | Ongoing | Last Updated: April 2019 | Stephanie Laba (UNHCR-IA) Maroun Sader (UNHCR IA) Marie Akiki (UNHCR-PHU) Jerome Seregni (UNHCR-CwCs)
Increase information and tool sharing among members of the HWG | To update the dropbox folder to include all IEC tools/materials developed by Health Partners | Ongoing | To be finalized: May 2019 | Stephanie Laba (UNHCR-IA)
| To ensure the Inter-Agency Information Sharing Data Portal, Health Sector Working Group Page is up-to-date | Ongoing | Portal updated for Q1 | Stephanie Laba (UNHCR-IA) Maroun Sader (UNHCR-IA)
Coordination of Health Programmes / Projects & Medical Missions | To coordinate with OCHA on the Health sector priorities for the LHF allocations | Completed | Last Updated: April 2019 | Stephanie Laba (UNHCR-IA)
| To support partners in identifying gaps and priorities and in developing proposals for the LHF funds | Pending | To be finalized: May 2019 | Stephanie Laba (UNHCR-IA)
| To participate in the steering and technical committee for the revision of the Health proposals to the LHF allocations | Pending | To be finalized: June 2019 | Stephanie Laba (UNHCR-IA)
| To prepare a list of medical missions planned by partners in 2019 | Pending | To be finalized: May 2019 | Stephanie Laba (UNHCR-IA)
| To gather feedback on medical missions conducted in 2019 | Pending | To be finalized: June 2019 | Stephanie Laba (UNHCR-IA)
| To conduct a coordination meeting for Ophthalmological missions in 2019 | Pending | To be finalized: April 2019 | Stephanie Laba (UNHCR-IA)
Strengthening Referrals from PHC facilities to SGBV services (including CMR) | Follow-up with the SGBV TF on the development of a draft circular to be shared with MoPH | Pending | To be finalized: May 2019 | Stephanie Laba (UNHCR-IA) Elsa Bousket &/or Lara Chelala (UNHCR-IA)
| follow up with the SGBV TF on the development of posters & leaflets | Completed | Completed: January 2019 | Stephanie Laba (UNHCR-IA)
| Follow-up with MoPH and partners re. endorsement of tools and dissemination of the information to facilities | Ongoing | To be finalized: June 2019 | Stephanie Laba (UNHCR-IA)
Increasing accountability in terms of Health Referrals | Develop an automatized mechanism/tool for Health Referrals | Pending | To be finalized: June 2019 | Stephanie Laba (UNHCR-IA) Raffi Kouzoudjian (UNHCR-IA)
| Pilot the automatized mechanism/tool for Health Referrals | Pending | To be finalized: July 2019 | UNHCR PHU Field UNHCR PHU BO
| Incorporate feedback from field colleagues and launch the automatized mechanism/tool for Health Referrals | Pending | To be finalized: August 2019 | Stephanie Laba (UNHCR-IA) Raffi Kouzoudjian (UNHCR-IA)
Data Analysis | Prepare a gap mapping for PHC support | Pending | To be finalized: May 2019 | Stephanie Laba (UNHCR-IA)
| Liaise with MHPSS TF to identify gaps in access to MH services | Pending | To be finalized: May 2019 | Stephanie Laba (UNHCR-IA)
| Update the funding gaps document on a regular basis | Pending | To be finalized: May 2019 | Stephanie Laba (UNHCR-IA) Health Sector Core Group
| Draft TORs and guidelines for research projects proposals | Completed | Last Updated: April 2019 | Stephanie Laba (UNHCR-IA) Asaad Kadhum (UNHCR-PHU)
| Share the TORs and guidelines for research projects proposals with UNHCR, WHO & MoPH for revision and clearance | Pending | To be finalized: May 2019 | Stephanie Laba (UNHCR-IA) Asaad Kadhum (UNHCR-PHU)
| Discuss and form a Health Sector Strategic Advisory Group for research proposals | Pending | To be finalized: June 2019 | Stephanie Laba (UNHCR-IA) Asaad Kadhum (UNHCR-PHU) Health Sector Core Group
| Keep track of list of studies/assessments planned for 2019 as well as information gaps | Ongoing | Last Updated: March 2019 | Stephanie Laba (UNHCR-IA)
| Develop a template for detailed financial reporting of Health Sector Partners and disseminate | Pending | To discuss in Core Group | Stephanie Laba (UNHCR-IA) Health Sector Core Group
Advocacy | Update the advocacy messages on a regular basis | Ongoing | Last updated: January 2019 | Stephanie Laba (UNHCR-IA) Health Sector Core Group
| Update the LCRP Health research questions | Completed | Last Updated: March 2019 | Stephanie Laba (UNHCR-IA)
Institutional support | Ensure that detailed information on Institutional Support is captured on a regular basis through quarterly reporting of partners | Pending | To be finalized: June 2019 | Stephanie Laba (UNHCR-IA))
Dialysis Support | Maintain an updated list of patients in need of dialysis | Ongoing | Last Updated: March 2019 | Stephanie Laba (UNHCR-IA)
| Develop advocacy tools aimed at supporting fundraising for dialysis | Pending | To be finalized: June 2019 | Stephanie Laba (UNHCR-IA)