| COUNTRY OPERATION: | UGANDA | LOCATION (specify sites): |  | All refugee settlements |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Type of situation | (refugee/IDP/mixed situation): Refugee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OBJECTIVE | The Operation will increase meaningful access to household shelter construction materials and non-food items (NFIs) for refugees and host communities in order to mitigate the risk of SGBV. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RISK STATEMENT | If there is a continued lack of meaningful access to construction materials, then there will be inadequate shelter durability and privacy. Furthermore, PoCs will travel farther distances to locate wooden poles for framing and grass for roofing resulting in an increased exposure to SGBV as well as refugee/host conflicts as natural resources become scarcer. If POCs lack meaningful access to non-food items upon arrival in Uganda, this hinders their ability to collect/store water, sleep in comfort, prepare and eat meals, store belongings etc., further delaying the stabilisation process. It can also increase the likelihood of resorting to negative coping mechanisms to acquire such NFIs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall accountability (if accountability changes below, please indicate) | OPM and UNHCR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lead/Coordination (if lead/coordination is different in the different program steps, please indicate) | Shelter, Settlements and NFI Working Group (SSNFI WG), Environment & Energy WG and Field teams |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - ASSESSMENT & ANALYSIS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DESCRIPTION OF PRIORITY ACTIONS | Responsibility | Support required by whom | Partners/ Key actors |  | Target population |  | Timeline | Tentative Budget required |  | Constraints |  | Opportunities |  |  |  |  |  |
| Priority action 1: Prepare desk review to identify participation of at-risk groups in existing assessments. Review reports including AGD Participatory Assessment, PSN Assessment, PDM reports, annual reports on NFI and emergency shelter kit distributions to identify risks, needs, challenges and recommendations. | Community-Based Protection (CBP), SSNFI Sector | MFT and SSNFI WGs (central and settlement-level) to review and endorse recommendations. SMT endorsement | OPM, CRS (sector co-lead) |  |  | -Refugees -Household (HH) level -At-risk groups including PSNs | Q2 2019 | $20,000 |  | Accessibility of documents – actors reluctant to share reports with sensitive data etc. Lack of staff and dedicated time available |  | Existing reports that require compilation + analysis. Technical experts are in the field. CBP staff available. MFT Participatory Assessments. |  |  |  |  |  |
| Priority action 2: Analyse SGBV risks with the delivery mechanisms of providing emergency shelter and NFI kits to new refugee arrivals. | SSNFI Sector, SGBV, CBP | MFT and SSNFI WGs (central and settlement-level) Protection, Field SMT | Protection partners, OPM, CRS, SSNFI WG members |  | -Refugees - HH level -At-risk groups including PSNs |  | Q2 2019 | n/a |  | Complexity Lack of dedicated resources to conduct analysis. |  | Technical experts are in the field. SGBV Technical experts are in the field. |  |  |  |  |  |
| Priority action 3: Consult with women, men, girls, boys, transgender and intersex people to assess the ‘user’ satisfaction and level of success of humanitarian-built semi-permanent PSN shelters. Ensure to address issues around the shelter’s ability to cater to specific needs (e.g. ramps, handle bars), safety, privacy and cultural appropriateness. Assess the designs’ level of safety in terms of SGBV risks (sustainability, quality, market supply and lifecycle of construction materials that are being provided, review of minimum BOQs for shelter design including locks, privacy layout, size etc.) | SSNFI Sector | OPM/Ministry of Lands, Housing + Urban Development (MLHUD) MFT and shelter working groups (central and settlement-level), Protection, E+E, Field, Information Mgmt Unit, REACH | SSNFI WG members, Community extension workers |  | - PSN refugee HHs who received a semi-permanent shelter in last 3 years |  | Q2 2019 | n/a |  | Lack of committed resources and no additional budget – have to improvise collectively across WG actors for participation |  | Process initiated with help of REACH to design HH survey. Technical experts are in the field. SGBV Technical experts are in the field. |  |  |  |  |  |
| - PLANNING & DESIGN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DESCRIPTION OF PRIORITY ACTIONS | Responsibility | Support required by whom | Partners/ Key actors |  | Target population |  | Timeline | Tentative Budget required |  | Constraints |  | Opportunities |  |  |  |  |  |
| Priority action 1: In consultation with beneficiaries, review Emergency Shelter and NFI Kit Standards for new arrivals to ensure sufficient and sustainable construction materials are provided (poles and plastic sheeting). FGDs are conducted with women, transgender and intersex people, girls and boys, including those with disabilities and the elderly, in line with the AGD approach | SSNFI Sector, Programme | MFT – Protection, WASH, E&E, Field to revise and SMT to endorse | SSNFI WG members, Hygiene promoters (community extension workers) |  | -Refugees - HH level -At-risk groups including PSNs |  | Q2 2019 | TBD |  | Lack of resources and budget |  | Ongoing review for 2019 |  |  |  |  |  |
| Priority action 2: Revise and adopt range of standard semi-permanent shelter designs (in a catalogue) to include sustainable options based on results of ‘user’ satisfaction assessment (Priority #3 above) and the recommendations of the Inter Agency SGBV assessment. | SSNFI Sector | OPM/GOU/MLHUD/District Engineers, CRRF Steering Group MFT – Protection, WASH, E&E, Shelter, Field to revise & SMT endorse | CRS & SSNFI WG members |  | -Refugees - HH level -At-risk groups including PSNs |  | Q2 2019 | n/a |  | Government endorsement, Consistent adherence to standards from central to field level |  |  | Process initiated |  |  |  |  |
| - IMPLEMENTATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DESCRIPTION OF PRIORITY ACTIONS | Responsibility | Support required by whom | Partners/ Key actors |  | Target population |  | Timeline | Tentative Budget required |  | Constraints |  | Opportunities |  |  |  |  |  |
| Priority action 1: Implement programming to enable sustainable construction including skilling for mud and ISSB bricks and supply chains for grass/poles for possible income generation with priority or at-risk groups. | SSNFI Sector, Livelihoods | DLGs, Shelter/Livelihoods/ E+E WGs, CBP | OPM, Refugees & Hosts OPs/IPs |  | -Refugees & Hosts -At-risk groups including PSNs |  | Q2 2019 | n/a |  | Land availability Need for gradual approach |  | ENABEL Skilling Program HYT ISSB projects |  |  |  |  |  |
| Priority action 2: Ensure inclusion of women, men, transgender and intersex people, girls and boys throughout the emergency shelter and NFI kit distribution process, consider opportunities for CBI (cash for work and/or vouchers) | Field staff, SGBV and CBP | OPM, Programme, Tech unit, Supply, CBI, HoSOs etc. | OPM SSNFI WG |  | -Refugees - HH level -At-risk groups including PSNs |  | Q2 2019 | n/a |  | Late PPAs, Implementation |  | Existing community structures Ongoing CBI development |  |  |  |  |  |
| Priority action 3: Develop key shelter messaging to feed into multi-sectoral SGBV prevention messaging for communications in existing community dialogues, PAs, protection desks, feedback and referral system to link community members to technical support and materials. Create a one-pager that includes referral information and step by step pictorial instructions on how to assemble emergency shelter kit items into a finished shelter. | Community-based protection/ Shelter Expert | MFT OPM Field shelter colleagues Community-based protection | CTEN Comms IPs OPM |  | -Refugees - HH level -At-risk groups including PSNs |  | Q2 2019 | n/a |  | Need for clarity and translation OPM approval |  | CBOs for communication Technical Unit has emergency shelter kit diagrams/ drawings |  |  |  |  |  |
| Priority action 4: Ensure PSNs have adequate support to construct their shelters to proper standards e.g. CfW | SSNFI WG | OPM, CBP, SSNFI WG Field, SMT | SSNFI WG members |  | -Refugees - HH level -At-risk groups |  | Q2 2019 | TBD |  | Resources available workforce, skills in the community |  | Unskilled youth labour, Construction material |  |  |  |  |  |
| - MONITORING & EVALUATION (indicators and M&E plan) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DESCRIPTION OF PRIORITY ACTIONS IN RELATION TO MONITORING AND EVALUTION (data collection, reporting) | Responsibility | Support required by whom | Partners/ Key actors |  | Output |  | Indicators |  | Baseline |  | Target | Timeline |  |  |  |  |  |
| M&E Assessment and Analysis: Priority Action #1 - SGBV-related questions included in the assessments | SSNFI Sector/ Shelter MFT | CBP, SGBV | UNHCR, Shelter + Protection partners |  | Desk review completed |  | % shelter/NFI assessments that include SGBV related questions |  | 100% |  | 100% | Q1 |  |  | Q2 | Q3 | Q4 x |
| M&E Assessment and Analysis: Priority Action #2 | SSNFI Sector/ Shelter MFT | CBP, SGBV | UNHCR, OPM, Protection + Shelter Partners |  | Minutes of consultations |  | # settlements where consultations took place with affected populations on SGBV risk factors in NFI & emergency shelter kit distributions |  | 0 |  | 1 per settlement per year |  |  |  |  |  | x |
| M&E Planning and Design: Priority Actions #1 + 2 - Participation prior to the design of shelter and NFI kits and semi-permanent designs | SSNFI Sector | CBP and refugees | UNHCR, OPM, Shelter Partners |  | Minutes of consultations + Technical Appraisal of current standards |  | #consultations with affected at-risk persons prior to the finalising of shelter design |  | 3 |  | 1 per settlement per year |  |  |  |  |  | x |
| M&E Implementation: Priority Actions #1, 2 + 4 - Ensure RRP indicators for Shelter & NFI are disaggregated by gender, head of HH, age and at-risk groups #newly arrived refugee households receiving CRIs # of stabilised refugee HHs receiving MEB for basic needs # of refugee HHs receiving NFI cash assistance #newly arrived refugee HH provided with emergency shelter support # of individuals (refugees & hosts) trained and engaged in sustainable construction # of refugee households with specific needs assisted with semi-permanent shelters | SSNFI Sector/ Programme | IM Field | Shelter Partners |  | RRP Quarterly Reports |  | Disaggregated RRP indicators for Shelter and NFI # Shelter & NFI RRP indicators that are disaggregated to at-risk groups |  |  |  |  | x |  | x |  | x | x |
| M&E Implementation: Priority Actions #3 - Link community members to technical support and materials | Community-Based Protection | Shelter sector Communications | Protection Partners |  | Key messages developed and disseminated |  | #community outreach activities that include key shelter information for referrals & tech support |  | 0 |  | 2 x year per settlement |  |  | x |  |  | x |

Meaningful access means that the materials must be available in sufficient quantity and quality, provided on the basis of needs and without discrimination, be physically and financially accessible (e.g. within safe and easy reach of the community), and known of by the community, whilst being culturally relevant and socially acceptable taking into account gender and age needs and requirements