Livelihoods and Resilience Sector Working Group

Coordination Meeting – 20 August 2019 at Food for the Hungry

Agenda

- Welcome remarks from Food for the Hungry Country Director

- Co-chair update (40 minutes)

  - Standards update

    - LRS strategy

  - Updates from coordination forums (e.g. Inter-sector and Inter-agency)

  - Updates from other related sector WG

  - Other topics of coordination

    - Ebola Business Continuity Plan

    - Jobs and Livelihoods Response Plan

- RRP Progress presentation (30 minutes)

  - ActivityInfo

  - Mapping of partners and funding

- Discussion on gaps and coordination (20 minutes)

  - How do the gaps in activity mapping and reporting relate?

  - What can we do as a sector to achieve targets?

- Review of LRS Strategy (20 minutes)

- Partner announcements/AOB (5 minutes)

1. Welcome remarking from Food for the Hungry Country Director

2. Co-chair update

  - Standards update

- TOR: Completed.

- Sector strategy: Draft to be discussed later in meeting per agenda.

- Sector coordination at field level: No update.

- Reporting: Results of Q1 and Q2 presented later in agenda.

  - A reminder that all actors engaged in the refugee response/livelihoods are required to report. The next reporting period is in early October.

- Contact list: Reminder to please share any staffing changes, especially with any changes that have occurred over the summer.

- Coordination meetings: No change.

- Sector fact sheets: Dashboard shared with all partners that will be published shortly by UNHCR capturing progress. The mid-year report is anticipated by the end of August.

- Sector indicator dataset collection: No change.

- Joint needs assessments: No change.

- Uganda refugee portal: The portal is updated on a regular basis with all WG documents.

  - Updates from coordination forums (e.g. Inter-sector and Inter-agency)

Inter-sector coordination

  - Main relevant discussion point was around ActivityInfo and the need to streamline reporting and to avoid overlaps. This point particularly relates to LRS, which connects with several other sectors. Co-chairs will be meeting with other sector leads in the coming weeks on this issue and update the sector accordingly.

Inter-agency coordination

  - OPM:

    - Kyaka II expected to soon reach capacity and refugees will be settled in Nakivale and Oruchinga Settlements in Isingiro District. Kyagwali continues to receive refugees crossing at Lake Albert. Conflict based on politics over Obongi Sub-county have arisen. There are ongoing discussions about opening a settlement in Lama sub-county of Moyo District. There is also ongoing discussion of opening Zone 8 in Palabek Settlement (Lamwo District).

    - The updated Refugee Policy has a deadline of October 2019. It has been submitted to cabinet and awaiting approval to be submitted to Parliament.

  - UNHCR:

    - Approximately 64,000 refugees have arrived in 2019 (January – July), representing about 40% of the anticipated new arrivals in the RRP.

    - There have been 2,671 cases of EVD in the DRC (as of 30 July 2019) with a 67% fatality rate. WHO declared the outbreak as a Public Health Emergency of International Concern on 17 July. Uganda has had four cases, but also 27 cases of cholera (15 in Kisoro and 12 in Kyaka).

    - There was fighting near Juba on 23 July, highlighting that the peace process is still ongoing and the situation remains unpredictable in South Sudan. Omugo zone is no longer receiving new arrivals.

    - The Burundi refugee situation not considered an emergency, though “serious Human Rights abuses have continued since May 2018.”

  - CRRF: noted that development partners have allocated through off-budget and bilateral support approximately USD 762 mil over the next three years to refugee hosting districts.

  - Updates from other related sector WG

Energy and Environment WG

- The Water and Environment Response Plan is advancing. Partners are encouraged to engage through the Energy and Environment Sector Working Group.

Food security sector WG

- No update.

Cash-based interventions TWG

- The rate for cash-for-work (CFW) is undergoing a review in relationship to the mid-term review of NUSAF 3. Once communicated, the rate will be shared with all partners to harmonize with the national standards.

  - Other topics of coordination

    - Ebola Virus Disease

- There have been four cases in Kasese District. The Government took the lead to design a Government-led response plan with an initial budget of USD 19 million that covered a three-month response plan (completed) and a six-month preparedness (current state). The UN Preparedness Plan supports the government-led plan with a proposed budget of USD 13 million.

- The LRS has reformed the task force to finalize the EVD Business Continuity Plan. NGO member were identified based on comparative advantages to review and assist in finalizing the plan by the September working group meeting.

    - Jobs and Livelihoods Response Plan

- Ongoing development of the plan. The chairs held a meeting with Mr. Godfrey Kaima, Under-secretary for Refugees and Disasters/CRRF Director, on 19 August. MGLSD is the lead with full ownership of the plan. A follow up meeting with MGLSD and development partners to be held on 21 August.

- A new draft has been developed and requested that it be shared with the chairs to look for opportunities of collaboration. Chairs shared concern about the need to ensure adequate attention to social protection issues and addressing the needs of refugees to achieve socio-economic integration/self-reliance.

- RRP Progress presentation

- Mapping: Only 50% of partners have reported planned and achieved activities (see slides 3-6).

  - Close trend in activities planned and achieved. There is an over-focus on Objective 1 (Emergency livelihoods) at the risk that the sector will not achieve 2019 targets, let alone 2020 targets.

  - Email shared with country directors whose organizations have not shared information on the mapping exercise.

Action: See attached list of partner reporting standing for the Mapping and ActivityInfo exercises. All partners having reported in ActivityInfo but not the mapping are kindly requested to do so no later than 30 August.

- Reporting: There are many discrepancies between achievements (e.g. delivery of inputs versus training), geographic and refugee targeting (e.g. over-targeting in specific settlements for South Sudanese, yet limited to no targeting of Congolese or Burundian populations).

  - The indicators are raising concerns about respect of best practices and programmatic standards to achieve self-reliance. For example, there are a number of actors in vocational training, yet it is not clear that market scans are being completed as the basis for informing program decisions.

- To avoid duplication and ensure sustainability and viability, partners are reminded to report their activities (planned and achieved) and to base programmatic decisions on evidence.

Action: LRS IM focal point to clean data and verify with LRS partners discrepancies in reported numbers (e.g. over 5,000 market assessments reported in one settlement).

- Discussion on gaps and coordination

Topic: How do the gaps in activity mapping and reporting relate?

- There is a common trend of focusing on the South Sudanese population under Objective 1 (Emergency livelihoods assistance), with limited to no support to facilitate the socio-economic integration (Objective 2) or an enabling environment (Objective 3). This trend presents a risk that the LRS targets of the RRP will not be achieved, which is a risk for the achievement of the RRP, notably RRP Strategic Objective 3.

Topic: What can we do as a sector to achieve targets?

- Funding issues

  - Donor areas to not necessarily align to needs creating a disconnect between need and funding.

  - LRS partners encouraged to report in Mapping that the LRS co-chairs may assist in advocacy with donors to prioritize the gaps in the LRS strategy, as well as geographically and by refugee population.

- Reporting issues

  - Partners felt there is an issue of under-reporting, especially noting the discrepancies in the mapping and ActivityInfo.

  - Requested that a refresher training on reporting focused on the results framework and ActivityInfo might be part of the September working group meeting.

Action: LRS co-chairs to include a refresher on the results framework and ActivityInfo in the September meeting.

Action: LRS co-chairs to include monitoring discussion in Working Group agenda in the month following reporting to facilitate discussion around coordination/achievement of targets.

- Review of LRS Strategy

- The development of the LRS strategy to serve as a transition strategy and consolidate the various LRS strategy documents into one document was presented.

- Noted areas that are important to highlight are the strategy around information sharing and collaboration between actors.

Action: LRS co-chairs will organize a representative sub-committee in the week of 26 August to review the strategy and develop a final draft for review ahead of the September meeting when the final version will be presented for adoption by the Working Group.

- Partner announcements/AOB

- LRS co-chairs: The Response Innovation Lab (hosted by Save the Children) is preparing an application to USAID for a nutrition innovation project (with private sector linkages). In the event that they are successful, they will liaise with the sector with a view to identifying a partner to work with on an innovative concept.

Next Meeting: Tuesday, 17 September 2019 2:30 - 4:30 PM at Danish Refugee Council (DRC)