## 2020 YTF plan
Youth Task Force Work Plan 2020
For all YTF activities, age, gender and disability should be taken into consideration
Indicator 1. | Number of professional humantarian workers attending the Compact workshop | [5 empty] | Baseline 2: 20 | Target 2: 40 (cumulative)
Indicator 2. | YTF fact sheets are issued | [5 empty] | Baseline 3: No | Target 3: Yes
Indicator 3. | A youth engagment structure is established for YTF | [5 empty] | Baseline 3: No | Target 3: Yes
Objective | Activity | Sub-Activity | Q1 | Q2 | Q3 | Q4 | Responsible agency | Comments
Objective 1. Coordinate and promote information and resource sharing among key youth actors | Update ToR for YTF | Chairs to Share ToRs with YTF members for revision by November 2020. The ToRs will be finalized by December 2020 |  |  |  | x | YTF Co-Chairs | Share ToR with new YTF members
| Conduct elections for co-chairs of YTF | Chairs to share the call in March 2020 and the election to take place in April 2020 |  | x |  |  | Out going co-chairs | Election will take place in April 2020
| Knowledge Management | Coordinate with UNHCR on updating YTF information on Portal (Minutes, Fact sheets, and Newsletter) | x | x | x | x | YTF Co-Chairs UNHCR Coordination unit Amman
|  | Update Education/CP/GBV /protection and Youth services map and contribute to 4 Ws of the Camp as needed |  | x |  | x | YTF Co- chairs all YTF members, and all relevant working groups and subworking groups.
|  | Update Services Advisor for all youth programming in Zaatari in collaboration with UNHCR Coordination Unit and take 4Ws mapping from that. |  | x |  | x |  | All YTF members, UNHCR Coordination Unit
|  | Prepare and share an outline of trainings that can be provided by various agencies in Zaatari and share ad hoc trainings. |  | x | x | x | x | YTF Chairs and YTF members
|  | Coordinate with CMWG for dissemination of any messages needed. |  | x | x | x | x | IRD, UNHCR, NRC, UNFPA
|  | Conduct Quarterly meetings with Education and Protection WG's to update on the workplan progress |  | x | x | x | x | YTF Co- Chairs and chairs of Protection and Education WG's
| Monthly Meetings | Conduct YTF meetings on monthly basis | x | x | x | x | Co- Chairs
| Consultation on programme planning and assessments | Consultation on programme planning and assessments within YTF and youth stakeholders as well as with PWG, EWG, ADTF and other sectors as relevant. Organisations should present their intentions when designing new projects to make sure that gaps are taken into consideration and addressed. Approvals to be provided by ESWG and PSWG/CMWG for any projects involving community mobilisation. | x | x | x | x | Co- Chairs, with relevant actors as agreed | All YTF members
| Promote referrals between services | Encourage YTF members to implement referrals to and from youth related services between one another to benefit youth and build on their knowledge and skills. | x | x | x | x | YTF Chairs and UNHCR | This will be supported through the Services Advisor mapping.
Objective 2: Improve responsiveness to youth needs in youth programming by developing youth strategies at the camp level, and develop capacity of youth, youth volunteers and field staff working with youth. | Compact Capacity Building | Conduct workshops on the Global Compact for young people in Humanitarian Action for members in all coordination stuctures in the camp including all WG's and TF's |  | x |  |  | YTF Chairs
|  | Film Production around Zaatari Camp youth work inline with the COMPACT | x | x |  |  | UNFPA
| 16 Days of Activisim joint YTF event |  |  |  |  | x | All YTF members in coordination with Protection and SGBV WG's.
| Support coordination structures in improving their programming and messaging targeting youth (PLEASE ADD SUB ACTIVITIES YOU THINK ARE RELEVENT) | Conduct joint meeting with SGBV WG and Livelihoods WG on common areas of interest and identify key areas of intervention for YTF in collaboration with the two groups. | [5 empty] | Identified areas of focus are Livelihoods as it is one of the main concers for youth in the camp and it witnessed many changes in programatic approaches working with youth. The second is protection to continuo the coolaboration and work with SGBV working group on sexual harassment and on child marriage.
|  | Provide support for WG's in developing youth friendly messages and provide guidance on approaching youth in the camp | x | x | x | x | Chairs and FP's from YTF members to respective working groups.
Support Chairs of Working groups in the camp to create youth committees for their working groups. This is upon request from Chairs
Objective 3. Advocate with Donors, implementing agencies, camp and national authorities and advocacy groups for the needs of youth in the camp and for the implementation of activities that respond to those needs through the PSWG and ESWG. | YTF Newsletter | Compile existing information on programming, coverage and best practices (with a newsletter) |  |  | x |  | YTF Chairs to compile and contributions from all YTF members | The Newsletter will be developed in Q3 to be published in IYD 2020. The Newsletter should include inputs from all YTF members. Furthermore, all YTF members should post on their facebook and social media pages respectively.
| YTF Fact sheet | Develop a Fact sheet that includes useful information on youth services in Zaatari camp for 2020 | x |  | x |  | YTF chairs , UNICEF and UNHCR
| Advocacy events and messaging | Collaborate with all coordination groups in the camp to ensure youth are integrated into sector advocacy strategy and share advocacy message summaries by activating the FP's system among coordination structures in the camp | x | x | x | x | Chairs and assigned FP's to different working groups and the Chairs of WG's in the camp level | Include standing agenda point on YTF updates of YTF & other sector meetings
|  | Use advocacy messages from YTF engagment with youth through the "youth engagment structure" and promote them in joint events such as IYD, 16 Days campagin, and reflect them in newsletters and any communication with sectors, with donors and decision makers and review in Q3 for revision as needed. | X |  | x |  | All YTF members respectively | These summaries should be shared with ESWG and PSWG as well on a quarterly basis. In coordination with Amman level Advocacy Group. At Zaaatri level UNHCR external relations will provide support . (best practices, capacity support and youth led projects, work opportunities, and issues related to tertiary education, increased opportunities to volunteer, Advocate for more places for youth in the camp and more opportunities for them to access centers for courses (including transportation support and coordination between existing activities to avoid timing conflicts, Advocate for more diverse and relevant accredited learning and training programmes). Notes: *accreditation of NGO programmes *outreach through home visits- YTF support *establishing a program for youth as volunteers with no needed previous experience *ease the process for employed youth to continue study. *advocate for more outside camp training opportunities.
|  | International Youth Day celebration |  |  | x |  | All YTF members respectively | Organize a joint event for YTF members in the camp celebrating International Youth Day. The event should be high level event engaging with donors and refugees in the camp
Objective 4. Promote youth participation in programme planning, setup and implementation, both in youth and non-youth specific programme responses. | Develop a youth engagment structure for YTF | Develop selection criteria for youth, and a selection committee with clear scope of work | x |  |  |  | co-chairs and YTF members
|  | Develop clear roles and responsibilities for the youth members | x
|  | Provide capacity building for selected youth |  | x
| Activate the engagment of the youth structure | Arrange regular meetings between YTF members and the "Youth Structure" |  | x | x | x | RI with the support of YTF members | Encourging youth to participate in the development of programs based on their needs and aspirations. Identifying techinques to reach out for youth in order to discuss their needs through regular meetings. Individual and group home visits for youth with disabilities. Activating youth initiatives that ensure gender balance and inclusion of youth with disabilities within their communities.
| Promote Youth Innovation in the camp | Organize youth Hakathons at the camp level in coordination with intrested working groups to provide the space for youth innovative ideas in finding solutions in the camp |  | x |  |  | UNICEF
|  | Promote the participation of youth, using their capacities and knowledge to develop and initiate community activities to respond to needs and gaps identified. This would include integration of youth as actors in data collection and research on relevant youth issues taking into consideration of age and disability and including YWD and vulnerable youth. |  |  | x | x | All YTF members | 1.Youth engaged in joint planned events such asIYD, 16 Days ...etc 2.Encourage youth to implement initiatives/civic engagement projects at community level. 3. Motivate Youth by reawarding them

## Sheet3
Conduct joint meeting with SGBV WG on common areas of interest and coordinate with SGBV SWG on training for YTFmembers on referrals around GBV. | x | x | UNFPA