## IS-Coordination
2022 LCRP Sector Workplan - Sector Coordination / Inter-Sector priorities
2022 Timeline
Link to IS Priority/Mainstreaming Area Or link to IS priority | Key Priorities | Main Actions | Q1 | Q2 | Q3 | Q4 | Responsible | Main Partners (optional) | Additional Comments | Status
Coordination | Sector Coordination Effort | Support/facilitate coordination among partners at ground-level to avoid duplication. | X | X | X | X | LCRP Energy Sector Coordinator
|  | Ensure cross attendance and participation in the other sector's working groups and provide important Energy sector updates. | X | X | X | X | LCRP Energy Sector Coordinator
|  | Keep monitoring the impact of the current crisis on the sector. Publish Advise on programme designs according to trends. | X | X | X | X | LCRP Energy Sector Coordinator
|  | Ensure that all partners comply with the guidance of the Ministry of Environment and disseminate any environmental guidance. | X | X | X | X | LCRP Energy Sector Coordinator
| Reporting | Keep ActivityInfo reporting updated | X | X | X | X
|  | Update the interactive dashboards | X | X | X | X
IS Joint Priority 1: Joint Analysis | Sector Advocacy Efforts | Advocate for cross-sector contributions of energy-related interventions to other sectors such as Water, Health, Education and Environment and Tension Mitigation |  | X |  | X | LCRP Energy Sector Coordinator
| Sector Situation Analysis | Update Sector Situation Analysis | X |  | X |  | LCRP Energy Sector Coordinator
Mainstreaming - Conflict Sensitivity | Engage with Conflict Sensitivity Mainstreaming Focal Point to ensure a conflict sensitive approach | Thematic discussions with Conflict Sensitivity focal point | X | X | X | X | Energy Sector Coordinator, Conflict Sensitivity Mainstreaming FP, Social Stability Sector Coordinator

## Logframe Activities
2022 LCRP Energy Sector Workplan - Logframe Activities
2022 Timeline
Sector Output | Key Activities | Q1 | Q2 | Q3 | Q4 | Responsible | Main Partners | Additional Comments | Statute
Outcome 1: Increase renewable energy production and Storage Capacity
Output 1.1 Solutions adopted to improve access to clean, affordable and sustainable energy | Activity 1: Provision of Solar water heater | X | X | X | X | Implementation: Sector partners Coordination: Energy sector lead (MoEW) & co-lead (UNDP) | ACF Spain, RMF, SCI, UN-Habitat, UNDP, URDA
| Activity 2: Provision of off-grid solar street lighting | X | X | X | X
| Activity 3: Provision of solar water pump | X | X | X | X
| Activity 4: Installation of distributed renewable energy power generation system with the battery storage | X | X | X | X
| Activity 5: Blended finance support (partial grant) for communities/institution to unlock private investment in renewable energy systems | X | X | X | X
| Activity 6: Technical support and awareness raising for communities/institutions/HH to help them access to finance (soft-loan, microfinance, crowdfunding, etc) for investment in renewable energy systems | X | X | X | X
Outcome 2: Reduce energy demand due to implementation of energy efficient initiatives
Output 2.1: Households and institutions have access to energy efficient products | Activity 1: Provision of Indoor LED lighting is provided in households | X | X | X | X | Implementation: Sector partners Coordination: Energy sector lead (MoEW) & co-lead (UNDP) | ACF Spain, RMF, SCI, UN-Habitat, UNDP, URDA
| Activity 2: Provision of Solar Cookers are provided in households | X | X | X | X
| Activity 3: Installation of Indoor LED lighting, motion detectors and other EE products are installed in Schools | X | X | X | X
| Activity 4: Implementation of EE measures in hospitals and other public health instituions | X | X | X | X
| Activity 5: Energy audits in public health institutions | X | X | X | X
| Activity 6: Provision of variable speed pumps | X | X | X | X
| Activity 7: Blended finance support (partial grant) for institutions to unlock private investment in energy efficient measures | X | X | X | X
| Activity 8: Technical support and awareness raising for communities/institutions/HH to help them access to finance (soft-loan, microfinance, crowdfunding, etc) for investment in energy efficient measures | X | X | X | X
Outcome 3: Improve access to electricity through Rehabilitation and Reinforcement works on the Transmission and Distribution networks
Output 3.1: Transmission network reinforced through the installation of HV/MV transformers | Activity 1:66 kV outgoing Bays are installed |  | X | X | X | Implementation: Sector partners Coordination: Energy sector lead (MoEW) & co-lead (UNDP) | (no active Partners so far) | Close coordination with MoEW and EDL is mandatory for these actvities.
| Activity 2: 66 kV incoming Bays are installed |  | X | X | X
| Activity 3: 20MVA transformers are installed |  | X | X | X
| Activity 4: 40MVA transformers are installed |  | X | X | X
| Activity 5: MV switchgears are installed |  | X | X | X
Output 3.2: Distribution network reinforced through the installation of MV/LV transformers | Activity 1: Existing MV/LV transformers including LV cables and poles as needed are rehabilitated |  | X | X | X | Implementation: Sector partners Coordination: Energy sector lead (MoEW) & co-lead (UNDP) | UN-Habitat, UNDP
| Activity 2: New transformers including LV cables and poles as needed are provided and installed |  | X | X | X
| Activity 3: Reinforcing MV/LV feeders are provided and installed |  | X | X | X
| Activity 4:Promoting installation of legal electrical connections |  | X | X | X
Outcome 4: Enhance capacity of MoEW to plan, budget and oversee energy sector initiatives
Output 4.1: MoEW staff have improved capacities to oversee implementation and completion of projects and short-term interventions in electricity sector | Activity 1: Staff provided to MoEW to assist in implementation of renewable energy and energy efficient projects |  | X | X | X | Implementation: Sector partners Coordination: Energy sector lead (MoEW) & co-lead (UNDP) | (no active Partners so far) | Close coordination with MoEW and EDL is required for these actvities.
| Activity 2: Staff provided to MoEW to implement works on the transmission network |  | X | X | X
| Activity 3: Staff provided to MoEW to implement works on the distribution network |  | X | X | X