| #### Main Discussion Topics |  | #### Discussions, Suggestions & Action Points |
| --- | --- | --- |
| 1 | 3 RP Resilience plan Key timelines | - 12 Sept.: Submission first draft Results Framework for each sector - 19 Sept.: Appealing partners provide focal point for financial submission - 22 Sept.: Submission of Lebanon draft sector chapters with estimated finances to the Region - 24 Sept.- 1 Oct.: Submission of sector members financial proposals in Activity Info - 14 Oct.: Finalization of sector chapters based on financial submissions / Lebanon Crisis Response Plan (LCRP) - Drafting Timeline |
| 2 | MHPSS Program inclusion in 3RP activities | Suggestions: - The Mental Health and Psychosocial sub working group (MHPSS) co-chair suggested that the taskforce not be split and should remain as one taskforce with separate indicators for protection where required. - Psychosocial First Aid ( PFA) training of trainers was rolled out for all field workers in all sectors - Mental Health gaps need to be scaled up in all PHCs in collaboration with the mental health program - Concerns were raised regarding the shortage in staffing the mental health programs Action Points: - Frank Tyler ( UNHCR-IA): Find out if the Government will be a recipient of funding Answer: The Government can apply if it is has a robust plan within the 3RP plan and if it can guarantee a funding agency. |
| 3 | 3RP results based framework | - It was agreed during the Regional coordinator office ( RCO) workshop that the health sector will have 3 objectives : - Improve access, coverage and quality of primary health care services for target population - Improve coverage and quality of referral (secondary/tertiary) healthcare for target population - Strengthen Disease Prevention and Outbreak Control to targeted areas of high risk - The strategy of the health sector will be to support MOPH network & MOSA’s clinics that have comprehensive services ie (MHPPS, Nutrition, YMCA NCDs, IFS, UHC etc) by reinforcing a sustainable system. Discussions & Suggestions: - A health assessment for the situation in Lebanon will be be completed for 2015/2016 - UNHCR is looking to improve the effectiveness of referral care system (using assessments) - Any immunization campaign and routine vaccination should cover all cohorts all over the country - EWARN system needs more human resources and training on response as part of resilience - Consider the different agricultural areas when targeting for food security and Nutrition - In the Strengthening Disease Prevention and Outbreak Control activities , prioritize the Acute Watery diarrhea (AWD) and vaccine prevention campaigns - Routine vaccination campaigns will be strengthed in the plan Action Points: - Alisar Rady (WHO): Ask Dr. Ammar to provide the model of the standardized package of services at the PHC level ASAP so that it can be used in planning - Health Partners: Comment on the 3RP situation analysis NLT Thursday 11 Sep - After discussion about cohorts and age groups , it was agreed to keep them the same as RRP6 - Partners reporting on activity info : For the Health Centers Equipping, indicate the type of equipment in the comment box – UNICEF to provide details. Completed - Dr. Azzedine (UNICEF) to get back on the vaccination and nutrition categories and sub-categories and the beneficiaries NLT Friday 12 September. Completed |