## Sheet1
Shelter WG Work Plan (3RP/JRP Projects) | [17 empty] | Shelter WG Work Plan (3RP/JRP Projects)
Agency/Partner | no. | Activity | % funded | Location | Sub-activities | Jan | Feb | March | April | May | June | July | Aug | Sep | Oct | Nov | Dec
|  | Provision of emergency shelters to affected Syrian refugees | 100% | Zatari | Distribution of emergency shelter to new arrivals and cases referred to NRC by UNHCR to Zaatari
UNHCR | 1 |  | 100% | Azraq | Provision and / or maintenance of shelters and associated facilities, replaced, improved or upgrade (construction of cooking space and additional window)
Extension of existing village by buildings additional blocks of shelters
Construction of Public area - as extension of the recption area for Asylum seekers coming fro the Berm
| 2 | Construction of 2 more villages in Azraq with associated facilities | 0% | Azraq | Construction of additional village 7
|  |  | 100% |  | Construction of communal facilities such as market in village V & II
|  |  | 100% |  | Secured perimeter around village V - used asTransit Area
| 3 | Improving living conditions in Camps | 100% | Azraq | Maintenanceteam undertaken request for camps maintenance and infrastructure as requested by UNHCR and other humanitarian agencies in the camps;
maintenance of road and drainage
Maintenance of Green space
maintenance/repairs to transitional shelter (Quick Fix Team)
|  |  | 100% | Zatari | construction of road between the camp's ring road to the various gendarmerie observation post around the camp
Rodent and Vector control sweeps in camps
|  |  | 100% | Berms In Hadalat and Ruqban | Construction of services area for the UN agencies and NGOS to operate aand bring addequate safe live activities
| 4 | Post evaluation occupancy of shelters | 0% | Zaatari & Azraq | Preperation of questionnaire
Agreement with Partner to conduct assessment
Conduct assessment
Results and recommendations
Design response
INTERSOS | 1 | Cash for Rent for extremely Vulnerable Syrians and Jordanians | 0% | Irbid, Karak and Ma'an | Selection of beneficiaries
tripartite agreement with landors and beneficiaries
procurement (ATM, money dealer, other modalities)
cash distribution
PDM
| 2 | Upgrading of shelters to adequate standards | 0% | Irbid, Karak and Ma'an | assessment and identification of beneficiaries
BoQ
tripartite agreement with landors and beneficiaries
tender and selection of contractors
rehabilitation
technical acceptance
hand over to beneficiaries
beneficiaries satisfaction surveys
JHAS | 1 | Upgrading of shelters to adequate standards | 0% | IRBID | Fund raising
Mafraq ,Ajlion and Jaresh
Amman, Zarqa and Balqa
LWF | 1 | Cash for shelter rehabiliation (in practise unconditional cash assistance) for 321 Syrian HH and 140 Jordanian HH (November 2015 - April 2016) | 100% | Irbid Governorate | creation of ATM cards and bank customer profiles
ATM cards distribution
|  | Sessions on fiscal responsibility and legal awareness for 642 Syrian refugees and 280 vulnerable Jordanians | 100% | Irbid Governorate | Monitoring and Evaluation
Legal awareness sessions
| 2 | Cash for rent (in practise unconditional cash assistance) for 800 Syrian HH (June 2016 - November 2016) | 30% | Irbid, Mafraq and Zarqa Governorate | MoPIC approval
beneficiary selection (home visits)
creation of ATM cards and bank customer profiles (considering Iris scan method)
ATM cards distribution
Monitoring and evaluation
|  | Sessions on fiscal responsibility and budget training for 800 Syrian HH | 30% | Irbid, Mafraq and Zarqa Governorate | MoPIC approval
Beneficiary Selection (home visits)
Pre- and Post-Test
Evaluation
PU-AMI | 1 | Conditional cash for rent 500 households | 0% | Amman, Zarqa, Balqa, And Jarash | Fund raising
IOCC | 1 | Cash for Rent for extremely Vulnerable Syrians and Jordanians | 100% funded from March to June (1000 HH) | Amman, Mafraq, Zarqa, Ma'an, Karak, Madaba, Irbid | Beneficiaires selection (Home visits)
negotiation with landlords
review of current agreements IOCC-tenant-landlord- distirbution of checks for 3 months contribution towards rent (average 140 JOD per/month per family) .
| 2 | Shelter Upgrading, Average Level of assistance is 1500 USD per HH (In total around 100 HH will be assisted) | 100% (Pending MOPIC Approval) | Amman, Mafraq, Zarqa, Irbid (60% Syrians -40% Jordanians) | Assessment at HH level selection of beneficiaires
signing agreement with landlords
upgrading of units
ICMC | 1 | rental assistance for extremeley vulnerable households (Cash for Rent); Syrians and Jordanians | 100% (funded until Aug 2015) | Irbid, Mafraq, Zarqa, Ajloun, Balqa, Madaba, Jerash (70% Syrians, 30% Jordanians) | Beneficiary selection-- outreach home visit, second verficiation visit
Lease negotiations and agreement signing
Dispursement of first installment of funds
Mid-assistance monitoring
Dispursement of second installment of funds
Post-distribution monitoring
NRC | 1 | Renovation of sub-standard shelters | 46% | Ajloun, Jerash, and Irbid | Beneficiary selection and technical assessment
Lease negotiations and agreement signing
Disbursement of funds and progress monitoring
Dispute resolution and eviction monitoring
| 2 | Creation of Additional HUs | 46% | Ajloun, Jerash, and Irbid | Beneficiary selection and technical assessment
Disbursement of funds and progress monitoring
Relocation of Syrian HHs to new shelter; signing lease agreement
Dispute resolution and eviction monitoring
| 3 | Cash for Rent | unfunded to date | tbc | As per revised technical guidelines
| 4 | Monitoring and Evaluation |  |  | Monitoring and Evaluation
Habitat for Humaity | 1 | Cash for Rent for Vulnerable Syrians and Jordanians | 0% | Irbid, Jarash, Madaba, Salt (Jordan Valley) | a) Assessment (Home Visits)
b) Selection according to criteria;
c) distribution
d) Monitoring & Reporting during the process
e) Evaluation of the project
UN Habitat | 1 | Jordan Affordable Housing (JAH) Project - Phase 1 | 100 | Ramtha and Amman | 1. JAH project awareness and outreach activites
2. Build demonstration JAH units
3. Initiating a pilot project in Ramtha
4. Developing the JAH Entity Options
June 2016