## HSWG 2014 Workplan
Urgent
Needs Attention
Reproductive Health Sub Working Group Work Plan 2015 | [7 empty] | On track
Done
| TASKS | Focal person | 1st Quarter | 2nd Quarter | 3rd Quarter | 4th Quarter | Notes | Status
1. Coordination
1.1 | National RH SWG coordination meetings | UNFPA | ✓ | ✓ | ✓ | ✓ | monthly | on going
1.2 | National health sector coordination meetings | All leads | ✓ | ✓ | ✓ | ✓ | monthly | on going
1.3 | Zatrai level reproductive health meeting | UNFPA/JHAS | ✓ | ✓ | ✓ | ✓ | Bi-weekly | on going
1.4 | Coordinate with Zaatari Health coordination meetings | UNHCR/MoH | ✓ | ✓ | ✓ | ✓ | weekly | on going
1.5 | Azraq level reproductive health meeting | UNFPA |  |  | ✓ | ✓ | Bi-weekly | planned
1.6 | Coordinate with Azraq level health sector coordination meetings | UNHCR/MoH | ✓ | ✓ | ✓ | ✓ | weekly | on going
1.7 | Mafraq level health sector coordination meetings | MoH | ✓ | ✓ | ✓ | ✓ | monthly | in process
1.8 | coordinate with Health Sector meeting | UNHCR/WHO | ✓ | ✓ | ✓ | ✓ | monthly | on going
1.9 | Coordinate with Nutrition SWG | UNICEF/SCJ | ✓ | ✓ | ✓ | ✓ | monthly | on going
1.1 | Coordinate with SAG meetings | UNHCR/WHO | ✓ | ✓ | ✓ | ✓ | As required
1.11 | coordinate with GBV SWG meetings | UNHCR/UNFPA | ✓ | ✓ | ✓ | ✓ | Monthly
2. Strategy and Planning
2.1 | Develop a startegic plan on Sexual Reproductive Health in development and humanaterian programme | RH SWG | ✓ |  |  |  |  | Done
2.2 | Review and finalize RH referral crieteria | RH SWG | ✓ |  |  |  |  | Done
2.4 | Develop RH fact sheet | Leads/ RH SWG |  |  | ✓ |  |  | To be followed
2.5 | Include considerations of SGBV prevention and response in strategic planning processes??? |  | ✓ | ✓ | ✓ | ✓ | 'As required
2.6 | Integeration of nutritional activities within Reproductive health strategy
2.7 | Integeration of community health targeted activities within reproductive health strategy
3. Policy and Guidance
3.1 | Implement refferal guidelines for high risk pregnancy | RH SWG | ✓ | ✓ | ✓ | ✓ |  | Done
3.2 | Review RH indicators | RH SWG | ✓ |  |  |  |  | Done
3.3 | Implement RH surviallance system
3.4 | Development of standardized RH messages | RH SWG | ✓ |  |  |  |  | Done
3.5 | Implemntaion of Misscariage new log book | RH SWG | ✓ | ✓ | ✓ | ✓
3.6 | RH guidelines revised and adapted into charts, Awareness manual | UNFPA and IP/Ad Hoc Technical group | ✓ | ✓ | ✓ | ✓
4. Assessments
4.1 | Update and maintain register of RH health related assessments | Leads | ✓ | ✓ | ✓ | ✓ |  | on track
4.2 | Desk review of existing RH health related assessments | RH SWG |  |  | ✓
4.3 | Review proposed assessements to ensure consideration of SGBV | HSWG,RH SWG | ✓ | ✓ | ✓ | ✓
4.5 | utilize partcipatory approach in involving beneficiries to strenghten health services responding to SGBV survivors needs | UNFPA | ✓ | ✓ | ✓ | ✓ |  | on going
5. Monitoring and Reporting
5.1 | Finalise indicator definitions for Activity Info | UNHCR/WHO/UNFPA | ✓ |  |  |  |  | Done
5.2 | Develop RH monitoring framework | RH SWG | ✓ |  |  |  |  | Done
5.3 | Review 2015 Jordan Response Sector Monitoring Dashboard | UNFPA/UNHCR | ✓ | ✓ | ✓ | ✓ | ✓ | Done
5.4 | Activity info reporting | All sector members/partners | ✓ | ✓ | ✓ | ✓ | monthly | On track
5.5 | Improve information collection and sharing of HIS | RH SWG/Health sector | ✓ | ✓ | ✓ | ✓ | monthly | On track
5.4 | Monitoring of SGBV health facility management in the health information system and other tools | UNHCR/UNFPA | ✓ | ✓ | ✓ | ✓ | monthly | On track
5.6 | Report on progress and challenges during RH SWG meetings | RH SWG members | ✓ | ✓ | ✓ | ✓ | Monthly
6. Mapping and Analysis
6.1 | Develop RH services Mapping template(produce Reproductive health services map including CMR services through reprodutive health coordination) | UNFPA/RH SWG and partners | ✓ | ✓ | ✓ | ✓ |  | Done
6.3 | Produce charts, tables, maps from Activity Info data | UNHCR IM | ✓ | ✓ | ✓ | ✓ | as needed | planned
7. Emergency Preparedness
7.1 | Update contingency stock list of RH | UNFPA | ✓ | ✓ | ✓ | ✓ | quarterly or after use | On track
7.2 | Inter-Agency Contingency Plan - (RH Health component) | UNFPA/RH SWG | ✓ |  |  | ✓ | six moonthly | On track
7.3 | Include SGBV supplies in contingency planning | UNFPA | ✓ | ✓ | ✓ | ✓
7.4 | Conduct MISP and CMR training to strenghten capacity and enhance prepardness | UNFPA | ✓ | ✓ | ✓ | ✓
8. Advocacy and Resource Mobilisation
8.1 | Jordan Response Plan (RRP) review, update etc. | Leads/ RH SWG |  | ✓ |  | ✓ |  | On track
8.2 | Emergency Response Fund (ERF) proposals | RH SWG |  |  |  |  | as required | On track
8.3 | ERF review of proposals | Leads | ✓ |  |  | ✓ | as required
8.4 | Central Emergency Response Fund (CERF) proposals | Leads |  |  |  |  | as required
8.5 | Advocacy papers | Leads | ✓ |  |  |  | and as required
8.7 | Include considerations of SGBV prevention and response in funding proposals | HSWG,RH SWG |  |  |  |  | as required
8.8 | Joint advocacy and resource mobilisation for adequate resources to address SGBV | HSWG, RH SWG,PWG and SGBV WG |  |  |  |  | Continuously
8.9 | Joint advovcacy to increase access to reproductive health services for Syrian refugees and vulnarable Jordanian | RH SWG | ✓ | ✓ | ✓ | ✓ | Continuously
9. Inter-Sector Coordination
9.2 | Health Information System (HIS) dissemination | Leads/ focal points | ✓ | ✓ | ✓ | ✓ | monthly
9.3 | GBV IMS report dissemination | SGVB SWG.RH SWG | ✓ |  |  |  | WHEN AVAILABLE
10. Cross-Cutting (Gender, Disability, Youth)
10.1 | Appointment of Gender Focal Point | Leads | ✓ | ✓ | ✓ | ✓ |  | Needs Attention
10.2 | Ensure disability issues are covered in strategy documents | RH SWG |  |  | ✓ |  |  | Needs Attention
10.3 | address sexual reproductive health needs for Youth and improve youth participation | RH SWG | ✓ | ✓ | ✓ | ✓ |  | Needs Attention
11. Other
11.1 | Maintain inter-agency data sharing portal updated | leads | ✓ | ✓ | ✓ | ✓
11.2 | Training in SGBV and Child protection SOPs | UNFPA,UNHCR,SCI,UNICEF |  | ✓ |  | ✓ | Programme managers
11.3 | Document best practices and lessons learnt including on SGBV programming | Sector leads | ✓ | ✓ | ✓ | ✓ | Ongoing sector leads and programme managers responsible
11.4 | Confidentiality clause in staff contracts | HSWG,RH SWG | ✓ | ✓ | ✓ | ✓ | Programme managers
11.5 | Capacity Development on SGBV for health care providers | RH SWG |  | ✓ |  | ✓ |  | On track
11.6 | RH campaign | RH SWG and Partners |  |  | ✓ | ✓ |  | On track

## Done (hidden)
Urgent
Needs Attention
Completed tasks: Health Working Group on Iraqi and non-Iraqi Refugees - 2012 Workplan |  |  |  | On track
Done
| Item | Focal person | Date | Status
Programmatic issues/Strategic direction
IMC to contact UNFPA for shortage of RH kits in Arshad and Amel | Joe (IMC) | 2012-12-10 | Done
Ensure that registered refugees know at registration where to go/who to contact | Carla (UNHCR) | 2012-12-10 | Done
| IMC will share the results of the survey. | Lina | 2012-03-01 | Done
| Nominate participants from IMC, MF and CLMC to participate in the regional health workshop/workshop postponed | MF, IMC | 2012-05-04 | Done
| UNHCR will share the research proposal and tool with WHO. | Carol |  | Done
Primary health care
| Revise YMCA Letter of Exchange for 2012. | Carol |  | Done
| CLMC to inquire on the 8 remaining PHC centers on the price list and procedures. | Isabelle |  | Done
| Ask the PHC centers to add the disease based on the doctor’s report or list provided by the centers. Add diagnosis to Annex 1. | Carol |  | Done
| YMCA to send the pre-approved price list. Cynthia inquire further and revert back. Joe had promised that during a meeting with UNHCR. IMC will sign with YMCA the agreement upon receipt of the pre-approved form for pricing. | Cynthia |  | Done
| Set an urgent meeting with YMCA to find solutions given the urgency of ensure non-stop chronic medication provision; | Hanan | 2012-04-24 | Done
| Set bi weekly meetings between YMCA and HWG | UNHCR | 2012-06-20 | Done
| For emergency care: stabilize for the first 24 hours and the agree on terms of emergency care | HWG |  | Done
| IMC will arrange for visits to Abou Jaoude and Baabda Government Hospital (IMC) | Fadi Aoun |  | Needs attention
| WHO to advise on date/time for training for medical coordinators and consultants of the Ips on Disease code( ICD10) | WHO |  | Done
| Set ceiling for prosthesis and inform hospital. | HWG |  | Done
| Set a meeting with Baabda Government Hospital; | Dr. Aoun (IMC) | 2012-05-03 | Done
| List of what is primary and what is secondary care will be shared with HWG; | Hanan (UNHCR), Rita (WHO) | 2012-05-11 | Done
| Health Info note and 4W matrix for health mapping developed | IMC/UNHCR | ongoing | Done | IMC to provide update final health note on 09-10-12
| Incorporating education on SGBV and other forms of abuses/violence in awareness raising campaigns. | UNFPA | Nov | Done | UNICEF and UNFPA to coordinate with UNHCR on SGBV education campaign. The same is discussed in PCG meeting and as a first step training is being scheduled for Nov. 2012
| Crticial cases (cancer , renal failure and thalasemic patients etc.) are not covered | UNHCR |  | Done | Japanese funds available for limited number of cases
| WASH conditions need to be assessed in collective shelters, schools etc | ACF | now | Done | WASH conditions need to be assessed in collective shelters, schools etc
| Medication for chronic illnesses | IMC | 2012-09-30 | Done | IMC has 2 months medication supply i.e. to suffice till end of Sep.
| A Study on access of displaced Syrians to reproductive health services and current RH status is conducted by UNFPA. | UNFPA | 2012-10-09 | Done | to be shared with HCG and relevant agencies
Secondary and tertiary health care
| CLMC will arrange visits to Hayek and Haroun . Visits to be made. | Isabelle , Hanan, Lina |  | Done
| Unify claim form between CLMC and MF. | Isabelle, Lina |  | Done
| Print copies through IMC recommended printing house (1000 copies = 100 USD) | Isabelle |  | Done
| Add ICD10 to claim form | Lina |  | Done
| UNHCR to add clause to the hospital agreements in relation to monitoring visits | Carol |  | Done
| Rita (WHO) will send list of hospitals in Lebanon; | Rita (WHO) | 2012-04-27 | Done
| Set a meeting with Jeitawi for special rates (burned cases), Levant Hospital together with Sister Hanan of Mar Antonious, as well as Hayek; | Hanan (UNHCR) | 2012-05-04 | Done
| Set a meeting with Middle East Institute of Health; | Isabelle (CLMC) | 2012-05-07 | Done
| Send the contract form to Jeitawi Hospital | Lina |  | Done