3RP 2017-2018 PLANNING

GUIDANCE NOTE 4

Setting Objectives, Outputs & Indicators at the Sector Level

# 1 Introduction

Each Sector Working Group (SWG) should develop a Sector Response Plan with up to five Objectives, six Outputs per Objective (three in each of the refugee and resilience components), and up to three indictors per Output. Each SWG should seek synergies with other sectors and between the Refugee and Resilience Components.

Sector and Inter-Sector coordinators should review the 2016 3RP plan to assess what worked well and what did not work well in 2016. Look at which Objectives, Outputs and Indicators have or have not been well used (including for planning, monitoring and reporting), and consider removing or revising those which were not well used.  Some sectors have undertaken a regional sectoral indicator review process, and standard indicators and their definitions will be provided as annex to this guidance. Where country context allows each sector is encouraged to adopt such standardized indicators.

The Objectives should, as far as possible, include Outputs in both the refugee and resilience components.  There may be specific instances where an Objective has Outputs in only one or the other component, and in this case the objectives should   embody the key goals of the respective components, as per Guidance Note 2.

# 2. Setting Objectives

For the purposes of the 3RP process, the common definition of an Objective is: a statement of desired results (and impacts) on the well-being of the people of concern that contributes to effecting the positive change expected to occur as a consequence, at least in part, of a set of outputs and activities. Objectives should follow the results based logic, with a complementary set of outputs contributing to the overall objective. However these objectives may be set at a level above which 3RP partners have full control, and will have inputs from partners outside the 3RP.

When setting the objective, 3RP partners should use Results-Based language (Attached annex for Definition of Key Results Based Programming Terms), using positive verbs that express a change, i.e. Increase, Enhance, or Reinforce. Objectives should also demonstrate what change they would expect to see at the end of the planning period.

# Examples of Objectives

- Sustainable and gender appropriate access to adequate shelter and infrastructure is available, improved and maintained in Camps.

- Affected populations have improved hygiene practices through access to hygiene items and hygiene promotion activities on a sustainable and equitable basis.

- Self-reliance and safe livelihoods for vulnerable groups improved;

- The capacity of the national health care system to provide services to Syrian refugees and members of impacted communities in the most affected governorates strengthened.

# Setting Objective Indicator, Baseline & Target

Each Objective should have one Indicator, Baseline and Targets for 2017 and 2018 - to measure the progress towards the objective. Objective indicators should, as far as possible, be population or process based depending on the nature of the sector and objective. The indicator selected might measure changes in knowledge, skill, behavior, health or living conditions for children, adults, families or communities. These effects can be economic, socio-cultural, institutional, environmental, technological or of other types. The Objective Indicator and Baseline should be expressed in terms of a percentage or extent against a defined target population or process. Population targets may be expressed such as the national population or the registered refugees. Resilience targets may include a focus on changes in development outcomes, institutional support and development, adaptive and absorptive capacities, and legislation.

# Examples of Objective Indicators

- % (#) of children (3-17 years, g/b) accessing formal and non-formal/informal quality education [Numerator = # of Syrian refugee children enrolled// Denominator = Total # of school-age Syrian refugee children]

- % (#) of severely economically vulnerable HH (MHH/FHH) received multi-sector cash transfers [Numerator = # of Syrian refugees and members of impacted communities targeted who receive multi-sector cash  transfers// # targeted]

- # of youth, men and women engaged in gainful employment or have established their own businesses

- % of affected public health facilities supported. [Numerator = # of public health facilities supported in affected areas//Total targeted]

- % (#) of targeted Syrians with increased access to vocational training and livelihoods opportunities

# Setting a Baseline for Objective Indicators

Each Objective indicator should have a baseline where possible by which progressive change can be measured over the time period. The baseline for 2017 may be considered on the basis of a) assessments/evaluation data collected; or b) what has been achieved in 2016.  For example, # of community organizations identified and assessed for mitigating tensions and preventing conflict can be a baseline for resilience oriented objectives.

# 3 Setting Outputs

Each Objective will contain up to six Outputs (up to three each under the Refugee or Resilience Components).

Outputs are changes in skills or abilities and capacities of individuals or institutions, or the availability of new products and services that result from the completion of activities within an intervention within the control of the organization. They are achieved with the resources provided and within the time period specified.

Outputs are a pre-condition for the subsequent achievement of Objectives. Outputs should be almost entirely within the control of the implementing organizations and less influenced by external factors.

The realization of outputs should, as far as possible be measured through quantitative indicators.

Each output will have a budget for 2017 and 2018, and any requirements that go toward Youth and Adolescents programming are noted here, for the purpose of giving better visibility to programming for these groups as well as for calculating the No Lost Generation (NLG) budget within the 3RP.

# Setting Output Indicators

Each Output should have a maximum of three Output Indicators which are the specific units that are produced by the activities making up the Output. The output indicator statement should be clear and include the unit of measurement. The indicator statement should not be repeated within one result framework for the sector. Targets of the indicator should be feasible within the two years of time, capacity and resources available.

Objectives in any sector may include Outputs that fall under the Resilience component. Output indicators in this section will be specific to each Output and developed in order to measure the Output’s level of achievement/completion. Resilience Output indicators should also, in a concrete manner, capture the means through which the relevant Output:

- Reinforces and/or uses local systems in provision of goods and services to programme beneficiaries

- Involves partnerships with local actors

- Supports self-sufficiency

- Contributes to social cohesion/stability

Inter-sector/ sector coordinators should consider how partners report into the plan (ActivityInfo or other tools) and aggregation process from partners against indicators.

# Examples of Output Indicators

- # of children (5-17 years, g/b) enrolled in formal general education

- # of children (5-17 years, g/b) benefitting from classrooms constructed, established or rehabilitated# of HH (MHH/FHH) received multi-purpose cash assistance# of HH (MHH/FHH) benefited from shelter structures maintenance and repair# of beneficiaries disaggregated by sex & age that have increased homestead farming production in host communities# of health workers (government, CBOs and national NGOs)  trained disaggregated by sex;

- # of deficient wastewater systems rehabilitated;

- # of targeted vulnerable persons (M/F) employed through public infrastructure and environmental assets improvement

# Disaggregation

# In ActivityInfo at the country level you should aim to include age and gender disaggregation for your indicators. When considering which indicators could be disaggregated consider where disaggregation has been useful operationally in 2016. Also consider disaggregation where it would be useful to know if youth and adolescents are being targeted so that we can build a better picture of activities benefiting these groups (see Guidance Notes 8 and 9 for more information.

# If there is no or little operational benefit to disaggregate then consider not requesting this in 2017-2018 to save energy on partner reporting.

# M&E Framework

As part of good practice in response planning and implementation, each country and sector should have an M&E Framework in place. These frameworks should be briefly summarized in the appropriate sections of the Country and Sector Narrative (Template A).

Annex: DEFINITION OF KEY RESULTS BASED PROGRAMMING TERMS

Adapted from: i) UNDG Results Based Management Handbook, October 2011; ii) DFID Tools for Development handbook (2012); and iii) SOAS, Project Planning and Management, London University, 2014.

Results based management (RBM)

Results-based management is a strategy by which all actors, contributing directly or indirectly to achieving a set of concrete and measurable results, ensure that their processes, products and services contribute to desired results (outputs, objectives, higher level goals and impacts) and use information and evidence to inform decision making on the design, resourcing and delivery of programmes and activities as well as for accountability and reporting. That means:

- There is a concrete RESULT linked to MEASURABLE indicators and to specific monetary inputs.

- There is an evident link between funds used and achievements reached

- Funds should be used on a cost-effective approach (what is the BEST use of the funds we can provide? Why is it better to provide the funds to a specific project?)

It is recognized that many actors are using different RBM definitions and terminologies, even though the concepts are, in many cases, similar. The use of common terminology will help actors move toward a common ground for supporting programming. When agreed, these definitions can contribute to greater coherence and consistency and help when communicating RBM issues with other stakeholders including governments.

Results

Results are changes in a state or condition that derive from a cause-effect relationship. The Results Chain is a causal sequence which lays out the sequence to achieve desired results – beginning with inputs, moving through activities and outputs, and culminating in individual outcomes and those that influence outcomes for the community, through goals, and end in a higher level impact to which a range of partners across sectors contribute. This results chain is based on a theory of change, including underlying assumptions.

Impact

Impact implies changes in people’s lives. This might include changes in knowledge, skill, behavior, health or living conditions for children, adults, families or communities. Such changes are positive or negative long-term effects on identifiable population groups produced by an intervention, directly or indirectly, intended or unintended. These effects can be economic, socio-cultural, institutional, environmental, technological or of other types.  In many frameworks Impact is connected to the higher level of change that occurs as the mid and long-term result of a set of interventions. In UNHCR logframes impact is connected to the Objective level.

Objective (also described as Outcome)

A statement of desired results (and impacts) on the well-being of the people of concern that contributes to effecting a positive change and achieving the overall goal, expected to occur as a consequence, at least in part, of a set of interventions or activities. It should describe the desired state which the project is expected to achieve/contribute to, and provide the reason for undertaking a programme or project. An objective can occur as the result of a combination of outputs, and may also be the result of additional factors not related to the outputs.

Guiding questions for setting an objective:

What specific effect is the project to achieve as a direct result of the project outputs? If the project is completed successfully, what improvements or changes could be expected in the group, organization or area towards which the project is immediately directed?

Guiding questions for setting Achievement indicators at objective level:

What are the quantitative measures or qualitative judgments, to assess whether the project purpose has been achieved?

Outputs

Outputs are changes in skills or abilities and capacities of individuals or institutions, or the availability of new products and services that result from the completion of activities within an intervention within the control of the organization. They are achieved with the resources provided and within the time period specified. They are a pre-condition for the subsequent achievement of purposes and goals. Production of outputs should be managed by the project and less influenced by external factors that the project management cannot directly control.

As most projects have more than one output, their sequential ordering is essential, because the output of one activity is likely to be required for the production of another output. The outputs of a project need to be stated in such a way that:

• Their realization can be identified, in terms of quantity, quality, time and place.

• As for objectives, a target is specified for the magnitude of output to be produced and the timescale for this.

• It is clear if a certain output is a prerequisite for other outputs.

• Necessary outputs for achieving the Objective to be achieved are listed and they relate to the objective.

• They are feasible within the resources available.

By definition outputs are separate from objectives. Unfortunately confusion between them is a common design error. Outputs are also commonly confused with activities. Remember that an output is the result of an action or activity. For example:

- The output of a training activity is trained people

- Training a group of beneficiaries is an activity

- The output of a research activity is the research results

- Research conducted on xxx topic is an activity

- Research findings on  the xxx topic  is an output

Guiding questions for setting an output:

What outputs (type, quality and number) will need to be produced (by activities undertaken with inputs provided) in order for the project purpose to be achieved?

Guiding questions for setting an Achievement indicator at Output level:

What type, quality and number of outputs would be produced by certain dates? (Performance)

Activities and Inputs are not part of the 3RP planning processes. However individual organization should plan based upon the activities and inputs required to achieve their Outputs and Objectives.

Activities: Actions taken or work performed through which inputs, such as funds, technical assistance and other types of resources, are mobilized to produce specific outputs. Each activity should contribute to at least one larger output.

Inputs: The 3RP coordination process does not look at the input level, however individual organization should plan based upon their required inputs, including the financial, human, material, technological and information resources.

Achievement indicators: Indicators are a qualitative or quantitative means of measuring an output or objective, with the intention of gauging the performance of a programme or investment.

Baseline: Information gathered at the beginning of a project or programme against which variations that occur in the project or programme are measured.

Target: Specifies a particular value that an indicator should reach by a specific date in the future.

Note objectives and outcomes are used synonymous for the purposes of the 3RP.