## Slide 1
Donor: BPRM
Implementing partner: ACTED
Location: Mafraq and Irbid
Duration: 01/09/2017 – 31/08/2019
Providing sustainable work opportunities to Syrian refugees and vulnerable Jordanians in the agricultural sector in northern Jordan

## Slide 2
Direct beneficiaries: 8 cooperatives, 560 Syrian refugees, 240 Jordanians
Indirect beneficiaries: 4000 individuals
Project goal: To enhance integration and participation of Syrian refugees and vulnerable Jordanians in agricultural livelihoods opportunities through 8 cooperatives in northern Jordan
Providing sustainable work opportunities to Syrian refugees and vulnerable Jordanians in the agricultural sector in northern Jordan

## Slide 3
Objective 1: Improve capacity of 8 cooperatives in Mafraq and Irbid Governorates to engage the market and support the involvement of Syrian refugee and Jordanian farmers in income-generating activities
Objective 2: Equip 560 Syrian refugees and 240 Jordanians with the necessary skills to engage in microbusinesses
Objective 3: Effective support mechanisms in place for agricultural market entry for Syrian refugees and vulnerable Jordanians
Providing sustainable work opportunities to Syrian refugees and vulnerable Jordanians in the agricultural sector in northern Jordan

## Slide 4
STATUS:
The assessment tool for selecting the cooperatives has been developed and approved.
The 23 cooperatives belonging to the ILO network have been assessed.
8 permanent cooperatives have been selected (5 in Mafraq and 3 in Irbid).
4 additional backup cooperatives have been identified (2 from each governorate).
Providing sustainable work opportunities to Syrian refugees and vulnerable Jordanians in the agricultural sector in northern Jordan

## Slide 5
STATUS:
The procurement of a business development consultant, trainer and climate smart agriculture consultant for My.COOP is on process (interview stage).
The tool to assess 1,600 individuals and select 800 beneficiaries has been developed.
The holding of the first Supervisory Committee has been organized, and will take place on 13th Dec. 2017
Providing sustainable work opportunities to Syrian refugees and vulnerable Jordanians in the agricultural sector in northern Jordan

## Slide 6
Providing sustainable work opportunities to Syrian refugees and vulnerable Jordanians in the agricultural sector in northern Jordan
NEXT STEPS:
Conduct the assessment of 1,600 individuals and the selection of 800 beneficiaries.
Conduct the cooperatives capacity assessment.
Adapt My.COOP training package to the Jordanian context and deliver 5-day training on methodology.
Create the local TREE committees to select the successful business plans.

## Slide 7
Providing sustainable work opportunities to Syrian refugees and vulnerable Jordanians in the agricultural sector in northern Jordan
NEXT STEPS:
Procurement of consultancy services – ACTED is urgently looking for the following:
  Business development/trainer for My.COOP: https://www.bayt.com/en/jordan/jobs/consultancy-services-technical-training-3744660/
  Climate smart agriculture for My.COOP: : https://www.bayt.com/en/jordan/jobs/consultancy-services-climate-smart-agriculture-3744718/
  YOU ARE WELCOME TO DISSEMINATE THE ABOVE LINKS AND TO APPLY!

## Slide 8
Providing sustainable work opportunities to Syrian refugees and vulnerable Jordanians in the agricultural sector in northern Jordan
  Climate smart agriculture for FFS: https://www.bayt.com/en/jordan/jobs/climate-smart-agriculture-consultancy-services-ffs-trainings-3749378/?from_email=1&utm_source=mailer&utm_medium=viral&utm_campaign=Viral_Share_Job
  Value chain analysis: https://www.bayt.com/en/jordan/jobs/value-chain-analysis-consultancy-services-3749384/?from_email=1&utm_source=mailer&utm_medium=viral&utm_campaign=Viral_Share_Job
  YOU ARE WELCOME TO DISSEMINATE THE ABOVE LINKS AND TO APPLY!

## Slide 9
Providing sustainable work opportunities to Syrian refugees and vulnerable Jordanians in the agricultural sector in northern Jordan
THANK YOU ALL FOR YOUR ATTENTION!