## Slide 1
LCRP 2017 Health Sector Updates

## Slide 2: Financial Tracking Updates
Chart: LCRP 2017 Funding Coverage (Received/Appeal) (in USD)
Important:
Updates from Inter-Agency Financial Tracking for Q3 (Jan-Aug 2017) is of 67 M representing 21.7% of total appeal

## Slide 3: Financial Tracking Updates
# of partners who have received funding from January-July 2017: 18 out of 43 LCRP 2017 Health Sector partners
Is your NGO missing?
Please contact Aung Thu Win directly: wina@unhcr.org SAMS? QRCS? RI? MEDAIR?

## Slide 4: Progress on Key Indicators (Jan-July 2017)
Refer to published Health Sector 2nd Dashboard
# of subsidized PHC consultations: 1,062,401 (48% of LCRP target)
Breakdown: 75% through PHCs and 25% through MMUs
# of persons supported in access to hospital care: 52,857 (40% of target)
Reminder: Activity Info Dynamic Dashboard updated MONTHLY on the portal

## Slide 5: LCRP 2018 Planning
A Planning Process draft timeline has already been shared by Inter-Agency
Oct 4th: Health Sector Core Group meeting to update the Situational Analysis & discuss the Strategy
Oct 5th: Results of the 2017 VASyR will be presented to the HCT and then shared with all sector working groups
Oct 6th: 1st LCRP 2018 Planning Workshop
Oct 17th: Deadline for Initial Draft Sector response plan to be updated and submitted to Inter-Sector
Oct 27th: Deadline for sectors to submit revised sector response plan to Sector Steering Committees (SSCs)
Nov 10th: Deadline for all sectors chapters to be approved by their respective SSCs.

## Slide 6: IASC GBV Guidelines roll-out within the Health Sector
1) A first training tool place at national level of Aug 10th.
2) Next week trainings are planned at field level:
Oct 2nd: South
Oct 3rd : North
Oct 4th : Bekaa
Oct 5th : Mt Lebanon
3) Once trainings are finalized, the action plan for integration of GBV guidelines is to be endorsed by the sector

## Slide 7: PHC Prioritization meetings
In light of changing support to PHC landscape, PHC prioritization meetings took place at field level; B/ML, North, South, Bekaa.
- It is expected that the selection of PHC for support will rely on the outcome of this exercise in addition to joint final selection of PHCs.
 Next month, the Health Gateways Visual Map will also display date until which support for each PHC is secured.

## Slide 8: Preparation for the Annual PIST report – Public Institutions Strengthening under LCRP
Compilation of staffing support  Done. (Map is an annex of the 2nd sector dashboard)
We will be contacting you to compile:
Support in equipment during 2017 per facility
Support in trainings in 2017 per type of training
Any other support in line with Institutional Strengthening

## Slide 9
Thank you.