## Slide 1: Rayak Airbase Eviction response
Health Sector
June 29th, 2017

## Slide 2: Response action to date
All NGOs supporting PHCs in the destination areas are observing the capacity of the centers to absorb more patients;
Health frontline staff and Health outreach volunteers are monitoring the health situation and the environmental health aspects;
Brochures on access to health services distributed by front line staff, OVs;
MTI had provided the ROV leaders with the eviction hotline to communicate eviction messages and destinations. Concerning the supported Youth PHC in Saadnayel, a bit increase in the number of patients supported in May compared to the month of April. ROVs (destination areas) are all informed to report new families arrivals.

## Slide 3: Response action to date
Humedica: Ready to respond to any referral or concerns related to the evictions;
Medair’s health community teams and OVs participated in the monitoring of the health situation and information sharing on the access to health services. Moreover they are supporting in disseminating the hotline for the affected population, checking if new comers in the destination sites and if any informal settlement is partially or completely evicted and reporting back to UNHCR.

## Slide 4: Findings from the inter-sector needs assessment
In both areas where interviews happened (Zahle and Baalbeck) and in reference to residents accommodated in both IS and Substandard buildings, only 42.47% responded accessing easily PHC and 32.82% accessing easily hospitals. The main obstacles listed were distance (45.95%) and transportation costs (46.72%). It worth to mention that 1.93% don’t know where to access a PHC and 4.63% don t know where to access hospitals in these areas.

## Slide 5: Findings from the inter-sector needs assessment
In Baalbeck area (36 interviews/259) and for residents accommodated in both IS+ Substandard buildings, the findings are as following:
47.22% access easily PHC and 27.78% access easily hospitals; noting that access to PHC among refugees accommodated in substandard buildings decreases to 25%;
Only 8.33% don t know where to access hospitals; to note that the % decreases to 3.57% for refugees living in ISs and it is higher within refugees accommodated in substandard buildings whereby 25% don’t know where to access hospitals;
Main obstacles: distance (58.33%) transportation costs (25%), fees doctor visit (8.33%), cost of drugs/treatment (5.56%). Refugees accommodated in substandard buildings raised no issues in reference to obstacles related to doctors’ fees and cost of treatment/drugs

## Slide 6: Findings from the inter-sector needs assessment
In Zahle area (223 interviews/259) and for residents accommodated in both IS+ Substandard buildings, the findings are as following:
41.70% access easily PHC and 33.63% access easily hospitals; To note that access of refuges accommodated in substandard buildings is better for PHC and Hospitals (68.75% for both);
Only 4.04% don t know where to access hosp, and 2.24% don’t know where to access to PHC
Main obstacles: distance (43.95%), transportation costs (50.22%),fees doctor visit (7.62%), cost of drugs/treatment (5.83%). Refuges accommodated in substandard buildings mentioned lower % of obstacles for transportation, distance and cost of treatment than the one accommodated in IS but included a factor of non-acceptance (6.25%)

## Slide 7: Findings from the inter-sector needs assessment
Correlation between regions and issue of accessibility to PHCs:
Access to PHC (hard, very hard, don’t know): N=89
  62.92% in Dalhamiyeh-Zahleh (n=56)
  15.7% in Bar Elias (n=14)
  7.8% in Terbol (n=7)
Could be that the participants mainly were selected in both areas
The others are from Taybeh Baalbeck n=2, Taraya n= 1, Mossaryeh n=1, Seriin Tahta n=1, temnine Fawaa n= 2, Nabi Chit n=1, Ksarnaba n=2, Tamnine Tahta n=1 and Hawch ref2a n=1)

## Slide 8: Findings from the inter-sector needs assessment
Correlation between regions and issue of accessibility to hospitals:
Access hard to SHC: N=119
56.3% in Dalhamiyeh-Zahleh (n=67)
15.9% in Bar Elias (n=19)
6.7% in Terbol (n=8)
Could be that the participants mainly were selected in both areas
The others are from Taybeh Baalbeck n=2, Taraya n=1, Mossaryeh n=2, Seriin Tahta n=1, temnine Fawaa n=4, Nabi Chit n=1, Ksarnaba n=6, Tamnine Tahta n=2, Hawch ref2a n=1, Chaat n=1, Ain Kfarzabad n=1, Anjar Hawch Moussa n=2, and Taanayel n=1)

## Slide 9: Envisioned changes in the sector’s Riyak response action plan
Medical Mobile Units to be dispatched based on the calculation of the distance from the IS to the supported health centres;
Enhancing the information sharing on the access to health services;
Enhancing the community surveillance and the reporting of communicable diseases;
Keep on monitoring the health centers capacities in the destination areas;
Monitoring the Economical loss impact on the health spending by the refugees and their ability to cover both Primary and secondary health care refugee’s financial sharing cost;
Dispatching MMUs to respond to potential health events/outbreaks;
Cross cutting with other sectors:
*Cash assistance for severely vulnerable

## Slide 10
Thank you