| TITLE OF THE COORDINATION MEETING : Rayak Airbase eviction-Health sector Coordination Meeting |  |  |  |
| --- | --- | --- | --- |
| Date | 03 July 2017 | Time | 13:00-14:30 |
| Location | UNHCR Zahle premises | Duration | 1 h 30min |
| Chair | Mona Kiwan-UNHCR |  |  |
| Attendance |  |  |  |

| Name | Organization | Email address | Phone Number |
| --- | --- | --- | --- |
| Hiba El Hassan | MoPH | Hiba-lu@hotmail.com | 03513348 |
| Hiba Araji | MdM | mdm.healthofficer1@gmail.com | 70464103 |
| Dr Wael Harb | Medair | healthmanager-leb@medair.org | 81728854 |
| Farah Darwich | Medair | healthco-leb@medair.org | 70 635 305 |
| Zeina Tarchichi | Medair | Healthcom-officer1-zah@medair.org | 70882905 |
| Amer Sleiman | Beyond | ammarjef@yahoo.com | 76 886582 |
| Ali Assi | Beyond | ali.a.assi.89@gmail.com | 03687536 |
| Omar Ajamy | IMC | oajamy@InternationalMedicalCorps.org | 81 312143 |
| Abir Toufaily | HI | dvfpref.bk@hi-emergency.org | 79101563 |
| Samira Youssef | MTI | CHP7@medicalteams.com | 71330295 |
| Mona Kiwan | UNHCR | kiwanm@unhcr.org | 79160198 |

| 1.0 | INTRODUCTION/ PURPOSE OF MEETING | ACTION | DUE DATE |
| --- | --- | --- | --- |
| 1.1 | Review the Needs Assessment findings and adjust the action Plan of the health sector |  |  |
| 2.0 | Rayak eviction-updates | ACTION | DUE DATE |
| 2.1 | -The total potentially impacted population is 12,665 individuals living in 2,160 tents. This comprises persons in ITS in the eviction area, having or not received eviction notices, as well as persons in ITS outside of the eviction area but having received eviction notices for the same reasons; -As of 27 June 2017, 797 households have been verified as having left the eviction area although this is being currently verified. 1,650 households have been estimated as remaining in the eviction area / under eviction notices for the same reasons even if outside of the eviction area; - Evictions have ground to a halt during Ramadan. After Eid, and once LAF has verified who is allowed to stay according to local agreements with landowners, evictions will resume; -joint needs assessment in Riyak eviction relocation areas conducted 7 – 13 June 2017. The assessment has been conducted with two data collection methodologies setting out to document impact at household and community-level respectively (259 HH) and household level survey and Focus group discussions (15) and key informant interviews (5) |  |  |
| 3.0 | Review and update of the Action Plan | ACTION | DUE DATE |
| 3.1 | Review the below Action plan |  |  |
| 4.0 | Reporting | ACTION | DUE DATE |
| 4.1 | The attendees agreed to share each Wednesday by noon an update of the: -PHC capacities and any observed increase of vulnerability; -Main activities implemented in the field through MMU and outreach activities; -Pressing Needs observed; -Any related important concern | Health sectors partners will report on a weekly basis to UNHCR PHU UNHCR will compile and provide a feedback to the TF each Thursday | Each Wednesday at noon |

| What/Response action | When/Timeline | Who/Roles and responsibilities | Resources needed and available | Extra resources needed |
| --- | --- | --- | --- | --- |
| 1-Observation PHCs capacities in the destination areas *Medair supporting: Kfarzabad- Talia-Britel- Marj and Kab Elias MOSA SDCs *MTI: Youth Saannayel PHC *MdM: Kab Elias PHC *IMC: Maj-Bar elias and Farouk PHCs / Terbol support may be terminated by the end of the month due to the decrease in the patients load following the eviction Update: all PHCs are able to absorb more patients. There is only a slight increase in the number of consultations in the youth Saadnayel PHC so far. | Each week based on the weekly statistical data | IMC/Medair/MTI/MdM |  |  |
| 2-The health partners will continue monitoring the Economical loss impact on the health spending by the refugees and their ability to cover both Primary and secondary health care refugee’s financial sharing cost; | Each week based on the reports from the supported PHCs | IMC/Medair/MTI/MdM |  |  |
| 3-MMU are running in the locations where there is a difficulties to reach a PHC: Update: -So far Beyond and Humedica are running MMU in central Bekaa -Beyond is running MMUs mainly in Dalhamiyeh and Zahle and is able to include more IS in case the need arise | All week days except weekends | Beyond Humedica |  |  |
| 4-Dispatching MMUs to respond to potential health events/outbreaks | In case a suspected or confirmed health event/outbreak is reported | Beyond Humedica |  |  |
| 5- Enhancing the information sharing on the access to health services through OV, CHW and MMU actors: *Medair CHW and CH midwives supports IS in: Dalhamiyeh (all ISs)- Terbol (in 2 days will start) - Bar Elias- Talia- Hawch Refqa-Hawch Ghanam-Kab elais- Kfarzabad-Saadnayel-Marj(Medair *IMC: OVs supports in the catchment areas of the PHCs *MTI: OVs support Dalhamieyh (7 IS) and Terbol (3 IS) Update: -The main concern expressed by pocs so far shared is the non-stability in relocating and the need to relocate again -UNHCR will distribute health info brochures to the partners in order to be used; -Concern raised about increase in the lice and scabies issues; -OVs and CHW will ensure referring the pocs to PHC for vaccination and ANC/PNC | All week days except week end | -OV/CHW related to IMC, Medair and MTI -MMU actors (Beyond and Humedica) |  |  |
| 6- Enhancing the community epidemiological surveillance Update: -All OVs were trained on the reporting of communicable diseases by MoPH and UNHCR; -The health partners will ensure that the OVs/CHW/MMU partners will report accordingly any suspected CD. | Regularly | IMC/Medair/MTI/MdM/Beyond/Humedica |  |  |
| 7-Linking the pocs with MHPSS services and training the OV/CHW and front line staff on the detection and referrals. Update: -MTI: working closely with MdM and will refer accordingly the cases in need for MHPSS support; -Medair: recruited a psychologist and working according to the referral mechanism; -IMC:* able to accept referrals in the PHC and the case managers able to receive more cases for follow up and management *IMC is reviewing the budget in order to evaluate the capacity to do trainings for OVs/CHW and front line staff on the detection and referrals of cases in need for MHPSS services | Regularly | IMC/Medair/MTI/MdM/Beyond/Humedica |  |  |