## Workplan
Cash-based Interventions Technical Working Group: 2017 Workplan
# | ACTIVITY | Lead | Support | Comments | January | February | March | April | May | June | July | August | September | October | November
Information sharing and knowledge management | bar: October to November
1 | Submit 4Ws information on CBI to enable a holistic overview of CBI in Turkey to be reviewed | WFP | All member agencies
2 | Review 4Ws and identify areas of potential duplication and gaps - discuss in meetings and feed information to sector leads | UNHCR | All member agencies
3 | Quarterly updates on the CBI TWG & members' achievements / challenges | WFP & UNHCR | CARE
4 | Promote collection, appropriate storage/info management of, and sharing of key monitoring data - analysis should be undertaken by Sectoral WGs | WFP | iMMAP
5 | Identify, and share information on and examples of, good practice in CBI - including encouraging presentations in meetings by TWG members / relevant external stakeholders | WFP | All member agencies
6 | Identify, and share information on and examples of, innovative approaches in CBI | WFP | All member agencies
7 | Facilitate learning exchange visits between TWG members | CARE | WFP, UNHCR
8 | Facilitate learning review workshops | CARE | WFP, UNHCR,, all actors
9 | Foster linkages and complementarities between activities in CBI-TWG and the Inter-Sector Working Group (ISWG). | WFP, UNHCR, CARE | All member agencies
10 | Ensure regular communication and linkages with the other Cash TWGs in the region | WFP, UNHCR, CARE | All member agencies
11 | Ensure regular communication and linkages with the XB CBRTWG | WFP, UNHCR, CARE | All member agencies
Programme Quality and Cross-Cutting Issues
10 | Review existing CBI post-distribution (PDM) tools and methodologies and seek opportunities for harmonisation | IOM | UNHCR
11 | Undertake a review of gender and protection-related consequences of CBI for refugees in Turkey and develop recommendations on improvements to CBI programme design | UNFPA, UNHCR | CARE
12 | Identify opportunities, technical challenges, risks and strengths for undertaking cash-based responses for sudden-onset emergency response, such as potential large-scale population movements within/into Turkey; link to Inter-Sector WG work on contingency planning and emergency preparedness - link this activity with the modality decision-making tree activity. | WFP | To check with (REACH) if they can support on this
13 | Adapt existing modality decision trees for use in the Turkish context | IOM
14 | Periodically review Survival and Minimum Expenditure Basket Guidelines and collect evidence informing changes in agency transfer values and lessons learned. | CARE, WFP, UNHCR | all member agencies
15 | Review existing price monitoring/tracking tools and methodologies and seek opportunities for harmonisation | CARE, Mercy Corps | Task Force | Work on NFIs is still needed
16 | Review existing CBI post-distribution (PDM) tools and methodologies and seek opportunities for harmonisation | IOM | UNHCR | To be redefined based on the types of cash programming the group decides to focus on after ad hoc meeting
Capacity Development | bar: October to November
15 | Share capacity building tools with TWG members | WFP / UNHCR | All member agencies
16 | Share information on external capacity building opportunties with TWG members | WFP | All member agencies
17 | Review TWG member resources for capacity building on CBI (in-country; regionally; globally). Before this look to agency capacity needs assessment | WFP | All member agencies
18 | Develop a capacity building plan for TWG members | WFP | UNHCR & CARE
19 | Liaise with sectoral working group leads to arrange necessary training for TWG member staff in initiatives / minimum standards etc. developed by the TWG | WFP | UNHCR & CARE
Technical Support to Advocacy
20 | Advocate with service providers as needed by Working Group members | WFP, UNHCR, CARE | All member agencies
21 | Explore opportunities for new and improved approaches to CBI, researching and developing tools (including through emerging technologies) that will enhance the appropriateness and quality of delivery mechanisms | UNICEF | WFP
22 | Work with sectoral leads to advocate for acceptance of new/alternative CBI modalities with relevant stakeholders as needed | WFP & UNHCR
23 | Ensure that humanitarian CBI actors, including NGOs are kept up to date on developments/discussions on national social safety nets; seek participation for TWG members in appropriate discussions; link to ESSN Coordination Body | WFP & UNHCR
24 | Develop standard operating procedure (SOP) and terms of reference for impact evaluation. | WFP
25 | Facilitate the impact evaluations. | WFP
26 | Foster linkages and complementarities between activities in CBI-TWG and the Inter-Sector Working Group (ISWG). | WFP, UNHCR, CARE | All member agencies