| Refugee Health and Nutrition coordination meeting MoH boardroom 03rd July 2018 Agenda - Communication from the chair - Review of previous minutes - UNHCR - Update on Health sector Integrated Refugee Response plan – MoH - Updates from Nutrition in Emergency working group - MoH - Presentation of the Health facility solid waste management assessment in West Nile - UNHCR - Community health interventions in the refugee settlements - UNHCR Chair: Dr. Alfred– Assistant commissioner Clinical services– Ministry of Health Attendance: Refer to the attendance list attached. Attendance list. Sno.; Name; Org/Dept/Inst; Contact tel; Contact email. 1; Ahmed Abdi; UNFPA; 0793334161; ahmedoxfordian@gmail.com. 2; Nalugwa Caroline; AAH; 0776882285; cnalugwa@actionafricahelp.org. 3; Ronald Nyakoojo; UNHCR; 0783365587; nyakoojo@unhcr.org. 4; Ritah Nagudde; DFID; 0772880814; r-nagudde@dfid.gov.uk. 5; Peter Kivanika; UNFPA; 0772422396; mukasa@unfpa.org. 6; Agnes kihamia; UNICEF; 0778740175; akihamia@unicef.org. 7; Geofrey Wandira; AFOD; 0772498459; Gwandira2016@gmail.com. 8; Njoroge Stephen; UNHCR; njorogest@unhcr.org. 9; Dr. Julius Kasozi; UNHCR; 0772701123; kasozi@unhcr.org. 10; Driwale Alfred; MoH; driwalealfred@yahoo.co.uk. 11; Wadembere Ibrahim; UNHCR; 0775254437; wadembere@unhcr.org. 12; Emmanuel Omwony; UNHCR; 0783354172; omwonyi@unhcr.org. 13; Scholastica Adong; IOM; 0781631625; sadong@iom.int. |
| --- |
| Minute 1: Introductions - Self-introductions were made and was left open for those who arrived later to also introduces themselves | Actions/Way forward - Attendance list should be shared together with minutes of the meeting |
| Minute 2: Communication from chair - Welcomed all members present - Refugee response is big and many actors involved in the operation |  |
| Review of Previous minutes - The numbers have reduced to less than 100 per day in Kyangwali - 4w matrix has been generated - A training on EPI was conducted in west Nile and other locations will be covered as well - The outbreaks in Kyaka II and Kyangwali were closed and 2 rounds of oral cholera vaccines have been conducted - Measles cases are in a few settlements - Anthrax outbreak in West Nile – outside the settlements but it’s in control - With the presence of one health in Arua - A total of 1220 cases registered with 44 deaths and most of the deaths were on arrival at lake sides and a few were registered - Other interventions such as hygiene improvement, sanitation, water trucking were also done | - Print the 4w matrix and share with partners - Expired nutrition stocks at health facilities should be documented |
| Updates from the Nutrition in Emergency working group - Integrated management of Acute malnutrition thematic working group and has started working - Terms of reference for the group has been developed - The group also embarked on the response strategy adopting the integration of response in the IRRP - Reviewed the minimum nutrition in emergencies and all stake holders must use the document - Next meeting is on 17th and all are invited to attend | - Active participation of all stakeholders - Strengthen the link with the OPM - Need to direct the response to refugee response - Reactivation of the nutrition working group at MoH is needed - Need for a document showing a global view of nutrition coordination mechanisms |
| Solid waste management - Developing and environmental strategies including water, environmental health, solid waste and energy - Improper disposal of health care wastes - Different many forms of incinerators - An assessment was conducted in refugee health facilities and results shared | - Partners in the operation should - One standard form of incinerator should be identified constructed in all health facilities - Training of partner staff on waste management should be conducted - Standard design for placenta pit should be adopted - Laisse with ENABEL in west Nile to help handle waste - Come up with a brief on Waste findings and share - Explore other funding mechanisms for waste and involve other key players interested - Involve green label to train the health workers to be able to manage wastes - UNHCR to realign partner budgets during mid-term review to capture waste management |
| Community health | - All community health interventions should be in line with the Chews - Need to harmonize the CHT motivation/remuneration - Need for a meeting with partners to present the RHIP - RHIP has been approved by OPM |