| PUBLIC HEALTH SECTOR – UNHCR WEEKLY TEAM MEETING 25TH JUNE 2018 Time: 8:30 AM Monday Venue: UNHCR office Attendance: Dr. Julius, Dr. Ronald, Isaac, Ahmed, Emmanuel Chaired by: Dr. Julius |  |
| --- | --- |
| Sub-sector updates | Actions & way forward |
| Nutrition & Food security – Isaac - Arrived/reported for work on 18th/06 2018 - Attended a meeting with the Nutrition technical group and issues of Lack of SFP data for Palabek came up - Reviewed related Nutrition documents - Oriented on HIS and reporting requirements | - SMART survey for nutrition needs to be conducted in Kyangwali – Isaac to laisse with UNICEF/ACF - AAH country director should be contacted to enable field team implementing SFP in Palabek share reports with IRC in Palabek - Need for a further assessment into the proposed nutrition supplements for HIV/TB patients due to pill burden – Ronald Nyakoojo |
| RH & HIV – Ronald - Participated in a training by IGAD on revised reporting tools targeting PHO’s and HIV focal persons from settlements in West Nile - All partners implementing IGAD activities/projects received funds by end of week 25 - Complains on Viral load data - Stock outs of anti – TB medicines and ARV regiments in West Nile settlements - Will attend a meeting with UNAIDs during the week on HIV/AIDS activities implementation - PEPFAR meeting with UNHCR representative scheduled for this week at UNHCR office | - Gaps on stock ordered and stock received should be documented and communicated from Health facilities - Ahmed - More emphasis should be directed towards RH activities such as Family planning, SGBV, Fistula, Cervical cancer screening & Treatment - Ronald - Should carry out a study on family planning in settlements to have a more informed course of action - Ronald - Update family planning data in the registers at health facilities – Emmanuel - Actions recommended in Felicia mission report should be taken and feedback provided - Need to track HPV vaccination implementation in settlements –Ronald |
| Pharmacy & Medical logistics – Ahmed - Currently UNHCR facilities have 9 months stock on average - Stock out of anti – biotics is being experienced across settlements - Low stocks of RDTs & disposable gloves across settlements - Much stocks of ORS and need to redistribute - Transport challenges experienced during movement of mosquito nets to settlements but only Bidibidi has received less than 100% - Will follow up with NDA payments with the programme team - Will initiate weekly reviews of prescriptions using SPARS tools | - Medicines will be redistributed - Ahmed - Ahmed to provide summary indicators for Pharmacy to be included on the monthly indicators - Julius |
| Health Information – Emmanuel - HIS reports analysed and shared - Referral database compiled but a few settlements have not yet been submitted - Rolled out VHT data collection tools in Urban program for piloting - Attended a PEPFAR meeting - Weekly work plan template designed on in L drive under Public health section for all t input | - Organise monthly meetings to discuss Monthly reports - PEPFAR monthly reports validation will be done during the week and analysis shared - Gaps analysis matrix will be updated from all locations and shared - Need to audit data quality and provide support for health information for West Nile locations especially Bidibidi |
| Public health – Julius - CRRF health document approved by management - Launched LLINs distribution with MoH - Second round of Cholera vaccine will be conducted in Kyangwali starting 27th – 1st July 2018 - Health coordination meeting is planned for this week but no invitation has been sent out yet by MoH - Meeting to plan for the meeting with World bank will be held during the week and presentations will be next Tuesday – 3rd July at World bank | - Need to plan for JAM – Julius/Isaac - Declaration of end of cholera outbreak by MoH - Julius - MoU has been signed by the country representative and will be sent to MOH for approval - Julius - Wednesday presentation of health sector response plan to the steering group at OPM - MoH |

Compiled by : Emmanuel Omwony