## LWF CONSTRUCTION
LWF ADJUMANI CONSTRUCTION UPDATE (29/02/2016)
UNHCR FUNDED PROJECTS
S/No. | Type of Activity | Donor | Location | Contract Start Date | Contract End Date | Physical Progress % | Payments made to-date | Remarks | Pictorial View
1 | Expansion of waiting area at Mungula HC IV. | DFID | Mungula Health Centre IV | 2014-11-14 | 2015-01-15 | 100% | 100% | Works complete
2 | Construction of Nutritional centre at Ayilo HC III. | DFID | Ayilo 1 Health Centre III | 2014-11-26 | 2014-12-31 | 100% | 100% | Works complete
3 | Rehabilitation of Elema OPD Block | DFID | Elema Health Centre II | 2014-11-14 | 2014-12-31 | 100% | 100% | Works complete
4 | Construction of four (04) blocks of Semi detached staff accomodation, 2-stance latrine & outside kitchen | DFID | Nyuamnzi Health Centre III | 2014-10-13 | 2014-12-31 | 100% | 100% | Works complete
5 | Construct 4 units of 5 stance drainable latrines | DFID | Adjumani Hospital, Kocoa Health Centre III, Elema Health Centre II & Mungula Health Centre IV | 2014-10-13 | 2014-12-31 | 100% | 100% | Works complete
6 | Construction of Semi detached staff accomodation, 2-stance latrine & outside kitchen | DFID | Dzaipi Health Centre III | 2014-10-13 | 2014-12-31 | 100% | 100% | Works complete
7 | Construction of three (03) blocks of staff accomodation with 2-stance latrine & outside kitchen | DFID | Mungula Health Centre IV | 2014-10-13 | 2014-12-31 | 100% | 100% | Works complete
8 | Construction of General ward ( Male, female, children) plus 4-stance bath shelter | DFID | Nyuamnzi Health Centre III | 2014-10-13 | 2014-12-31 | 100% | 100% | Works complete
9 | Construction of Nutritional centre | DFID | Nyuamnzi Health Centre III | 2014-11-24 | 2014-12-15 | 100% | 100% | Works complete
10 | Construction of four (04) blocks of Semi detached staff accomodation, 2-stance latrine & outside kitchen | DFID | Ayilo 1 Health Centre III | 2014-10-13 | 2014-12-31 | 100% | 100% | Works complete
11 | Construction of general ward ( male, female, children) plus 4-stance latrine and 4- stance bath shelter. | DFID | Ayilo 1 Health Centre III | 2014-10-13 | 2014-12-31 | 100% | 100% | Works complete
12 | Construction of OPD, laboratory, antenatal clinic & immunization room with 4-stance latrines | DFID | Ayilo 1 Health Centre III | 2014-10-13 | 2014-12-31 | 100% | 100% | Works complete
13 | Construction of Semi detached staff accomodation & outside kitchen at | DFID | Alere Primary School | 2014-10-13 | 2014-12-31 | 100% | 100% | Works complete
14 |  | DFID |  |  |  | 100% | 100%
15 | Installation of Rain water harvesting systems for | DFID | Bira Health Centre III | 2014-11-14 | 2014-12-30 | 100% | 100% | Works complete
16 | Construction of 2 blocks of 4-stance drainable latrines | DFID | Mungula Health Centre IV |  | 2014-12-31 | 100% | 100% | Works complete
17 | Construction of 3 permanent blocks of 3- classrooms | UNHCR | Ayilo 1A Primary school | 2014-10-13 | 2014-11-15 | 100% | 100% | Works complete
18 | Construction of one block 4- classrooms with office plus 2 block 5-stance latrine, 1 blcok 2-stance latrine at Lewa selp help secondary school | UNHCR | Lewa S.S | 2014-11-10 | 2015-01-15 | 100% | 100% | Works complete
19 | Construction of 4 semi detached teachers accomodation & 2- stance latrine and outside kitchen | UNHCR | Ayilo 1 A & Nyumanzi Primary Schools | 2014-10-20 | 31/01/2015 (25/03/2016) | 90% | 83% | All civil works completed at Nyumanzi and painting started. Civil works in Ayilo almost complete
20 | Construction of 4 semi detached teachers accomodation & 2- stance latrine and outside kitchen in Mungula PS, Miniki, PS, Boroli PS and Elema PS | UNHCR | Mungula, Miniki, Boroli and Elema Primary Schools | 2014-10-20 | 2015-01-31 | 100% | 100% | Works complete
21 | Construction of one block dormitory plus 2 block 5-stance latrine for students at Beza Self Help Secondary School |  | Site: Adjumani - Camp | 2014-11-10 | 2015-01-31 | 100% | 100% | Works complete
22 | Construct 3 classroom blocks ( 2 in Ayilo II, 1 in Ayilo 2) | UNHCR / RAIN BUDGET | Site: Adjumani - Camp | 2014-10-13 | 31/11/2014 | 100% | 100% | Works complete
23 | Construct four (04) blocks of 5-stance drainable latrines | UNHCR / RAIN BUDGET | Adjumani Hospital (01), Kocoa Health Centre (01) & Ayilo 2 Primary School |  | 2014-11-15 | 100% | 100% | Works complete
24 | Construct four (04) blocks of 2-stance drainable latrines for teachers | UNHCR / RAIN BUDGET | Dzaipi Primary School (01), Ayilo 1 Protection houses (02) & Ayilo 2 Primary School (01) | 2014-09-12 | 2014-11-15 | 100% | 100% | Works complete
25 | Construct 2 blocks of 2- classrooms with Office | UNHCR / RAIN BUDGET | Ayilo 1 A & Ayilo 2 Primary Schools | 2014-09-12 | 31/11/2014 | 100% | 100% | Works complete
26 | Construction of ONE block of Protection houses | ECHO | Ayilo 1 Settlement | 2014-09-12 | 2014-12-31 | 100% | 100% | Works complete
27 | Construction of UNHCR office, interview rooms, latrines, registration centres and waiting area in Nyumanzi, Mungula and Ayilo I | DFID | Nyumanzi, Ayilo 1 and Mungula Base Camps | 2014-11-03 | 2015-01-15 | 100% | 100% | Works complete
28 | Construction of one block of Protection house in Settlements | DFID | Ayilo 1 Settlement | 2014-09-12 | 2014-12-31 | 100% | 100% | Works complete
29 | Construction of IP office block | UNHCR | OPM Office compound, Pakele | 2014-10-28 | 2015-01-15 | 100% | 100% | Works complete
30 | Construction of community centres in Nyumanzi, Boroli and Olua | DFID | Site: Adjumani - Camp | 2014-10-13 | 2014-12-31 | 100% | 100% | Works complete
31 | Construction of nine (09) blocks of OPM accomodation in Settlements | DFID | Nyumanzi (2), Ayilo 1 (4), Olua 1 (01), Boroli (01) & Mungula (01) Settlements | 2014-10-20 | 2014-12-31 | 100% | 100% | Works complete
32 | Construction of six (06) OPM Offices in settlements | DFID | Boroli, Nyumanzi, Ayilo 1, Ayilo 2, Maaji1& Mungula Settlements | 2014-10-13 | 2014-12-31 | 100% | 100% | Works complete
33 | Construction of new RDO (OPM) Office Block | UNHCR | OPM Office compound, Pakele | 2014-10-20 | 2014-12-31 | 100% | 100% | Works complete
UNHCR ADDITIONAL PROJECTS
34 | Construction of 20 classrooms in schools | Not sure | Mungula, Lewa, Elema, Miniki, Nyumanzi and Ayilo 1C Primary Schools | 2015-12-29 | 2015-03-15 | 100% | 100% | Works complete
35 | Construction of 03 blocks of school dormitories at Beza, St.Mary Assumpta and Mungula ss | Not sure | Bezza Al-Hiji, St. Mary Assumpta Girls and Mungula Secondary Schools | 2015-12-03 | 2015-03-03 | 100% | 100% | Works complete
36 | Construction of two room juvenile detention rooms at Adjumani police station | Not sure | Central Police Station, Adjumani | 2014-12-09 | 2015-03-09 | 100% | 100% | Works complete
37 | Construction of three (03) Community Centers | Not sure | Ayilo 1, Mungula and Alere Settlements | 2014-12-18 | 2015-12-20 | 100% | 100% | Works complete
38 | Construction of UNHCR conference room and renovation of office space | Not sure | UNHCR office compound, Pakele | 2014-12-16 | 2015-12-17 | 100% | 100% | Works complete
39 | Construction of four (04) blocks of Semi detached staff accomodation & outside kitchen | Not sure | Mireyi, Mungula, Aliwara & Boroli Primary Schools | 2014-12-17 | 2015-12-20 | 100% | 100% | Works complete
40 | Construction of eight (08) blocks of 5- stance VIP latrines | Not sure | Ayilo 1A P.S (03), Ayilo 1 Community Centre (01), St. Luke Nyumanzi P>S (01) & Nyumanzi 2 P>S | 2014-12-05 | 2015-03-03 | 100% | 90% | Works complete
41 | Construction of two (02) blocksSemi detached staff accomodation with 2-stance VIP latrine & outside kitchen | Not sure | Lewa Primary School and Melijo Primary School | 2014-12-17 | 2014-12-20 | 100% | 100% | Works complete
42 | Construction of Administration block Lewa SS | Not sure | Lewa Secondary School | 23/1/2015 | 14/3/2015 | 100% | 100% | Works complete
43 | Construction of three blocks of institutional kitchens at health centres | Not sure | Nyumanzi, Ayilo 1 and Mungula Health Centres | 2015-02-02 | 14/03/2015 | 100% | 100% | Works complete
44 | Construction of four isolation wards | Not sure | Numanzi Health Centre III, Ayilo 1 Health Centre III, Bira Health Centre III & Mungula Health Centre IV | 22/1/2015 | 15/3/2015 | 100% | 100% | Works complete
45 | Construction SNE unit ( block moved to Ayilo 1C primary school) | Not sure | Ayilo 1C Primary School | 30/1/2015 | 14/3/2015 | 100% | 100% | Works complete
46 | Construction of 06 blocks of semi-detached staff accomodation | Not sure | Nyumanzi P.S (01), St. Luke Nyumanzi P.S (02), Nyumanzi 2 P.S (02) and Miniki P.S (01) | 2014-12-17 | 2015-03-20 | 100% | 100% | Works complete
UNICEF FUNDED PROJECTS (EDUCATION INFRASTRUCTURE)
47 | Construction of two (2) blocks of 2-classrooms each | DFID | Lewa Primary School | 17/10/2014 | 28/2/2015 | 100% | 100% | Works complete
48 | Construction of two (2) blocks of 2-classrooms each | DFID | Elema Primary School | 17/10/2015 | 28/2/2016 | 100% | 100% | Works complete
49 | Construction of two (2) blocks of 2-classrooms each | DFID | Miniki Primary School | 17/10/2014 | 28/2/2015 | 100% | 100% | Works complete
50 | Construction of one (01) block of 2-classrooms | US GOVERNMENT | Nyamanzi II primary school | 28/10/2014 | 28/2/2015 | 100% | 100% | Works complete
51 | Construction of one (01) block of 2-classrooms with office and store | US GOVERNMENT | Nyamanzi II primary school | 28/10/2014 | 28/2/2015 | 100% | 100% | Works complete
52 | Construction of one (01) block of 2-classrooms with office and store | DFID | Melijo primary school | 28/10/2014 | 28/2/2015 | 100% | 100% | Works complete
53 | Construction of one (01) block of 2-classrooms | US GOVERNMENT | Boroli Primary School | 28/10/2015 | 28/2/2016 | 100% | 100% | Works complete
54 | Construction of one (01) block of 2-classrooms | DFID | Boroli Primary School | 17/10/2014 | 28/2/2015 | 100% | 100% | Works complete
55 | Construction of one (01) block of 2-classrooms | DFID | Mireyi Primary School | 17/10/2014 | 28/2/2015 | 100% | 100% | Works complete
56 | Construction of two (02) blocks of 2-classrooms | DFID | Mungula Primary School | 17/10/2014 | 28/2/2015 | 100% | 100% | Works complete
57 | Construction of one (01) block of 2-classrooms | DFID | Alere primary school | 28/10/2014 | 28/2/2015 | 100% | 100% | Works complete
58 | Construction of three (03) blocks of 2-classrooms each | DFID | St Luke Primary School | 28/10/2014 | 28/2/2015 | 100% | 100% | Works complete
59 | Construction of one (01) block of 2-classrooms with office and store | DFID | Alere Primary School | 28/10/2014 | 28/2/2015 | 100% | 100% | Works complete
60 | Construction of eight (08) blocks of 5-stnce VIP latrines at Melijo,lewa,Minik,Nyumanzi II primary school | DFID | Melijo (02),Lewa (02), Miniki (02) and Nyumanzi II (02) Primary Schools | 2014-12-01 | 28/2/2015 | 100% | 100% | Works complete
61 | Construction of latrines at Mungula , Alere, St.luke, Oligi Primary School | DFID | construction of latrines at Mungula , Alere, St.luke, Oligi Primary School | 2014-12-01 | 2015-03-03 | 100% | 100% | Works complete
FINN CHURCH AID PROJECT. FCA. (EDUCATION INFRASTRUCTURE)
62 | Construction of three (03) blocks of 2-classrooms each | FCA | Nyumanzi 2 Primary School | 2014-10-30 | 2015-02-16 | 100% | 100% | Works complete