## LWF CONSTRUCTION
2015 LWF CONSTRUCTION PROJECTS
REPORTING PERIOD: 1st - 29th February 2016
Type of Activity | Donor | Number of Beneficiaries | Location | Contract Start Date | Expected Completion Date | Physical Progress % | Payments made to-date (%) | Remarks | Pictorial View | Retention Payment Due Date
Rehabiltation of Adjumani Airstrip | UNHCR |  | Openzinzi, Adropi Sub-County, Adjumani | 2015-08-03 | 03/11/2015 (05/02/2016) | 100% | 90% | Works completed |  | 2016-05-03
Rehabilitation of the Airstrip Waiting Shed | UNHCR |  | Openzinzi, Adropi Sub-County, Adjumani | 2015-10-05 | 2015-11-13 | 100% | 90% | Works completed |  | 2016-02-13
Construction of office block with conference room at LWF Pakele compound | UNHCR | 150 | LWF compound, Pakele, Adjumani | 2015-07-15 | 2015-10-15 | 100% | 90% | Works completed |  | 2016-04-15
Construction of IP and RDO Septic tanks | UNHCR | 200 | OPM premises, Pakele, Adjumani | 2015-09-11 | 2015-10-30 | 100% | 100% | Works complete |  | 2016-01-30
Construction of 02 blocks of classrooms at Dzaipi SS | UNHCR |  | Dzaipi Sub-County, Adjumani | 2015-08-24 | 2015-11-24 | 100% | 90% | Works complete |  | 2016-05-24
Construction of 02 community centers. Elema and Baratuku | UNHCR |  | Elema and Baratuku Settlements | 2015-08-24 | 2015-11-24 | 100% | 90% | All works completed |  | 2016-05-24
Construction of 02 blocks of primary classrooms | UNHCR | 100 | Zoka Central Primary School, Maaji Settlement | 2015-08-24 | 2015-11-24 | 100% | 90% | All works completed |  | 2016-05-24
Construction of 03 blocks of primary classrooms | UNHCR | 150 | Ayilo 1B Primary School, Ayilo Settlemtent | 2015-08-24 | 2015-11-24 | 100% | 90% | All works completed |  | 2016-05-24
Construction of 02 blocks of primary classrooms | UNHCR | 100 | Ayilo 1B Primary School, Ayilo Settlemtent | 2015-11-10 | 2015-12-31 | 100% | 90% | All works completed |  | 2016-06-30
Construction of Maternity Ward at Ayilo H/C | UNHCR |  | Ayilo 1 Health Centre III | 2015-08-23 | 2015-11-24 | 99% | 90% | All other works except rectifying of solar electrical system completed |  | 2016-05-24
Construction of IP accomodation, payot, interview rooms | UNHCR |  | Ayilo 1 Base Camp, Nyumanzi Base Camp and Maaji 2 Settlement (site 9) | 2015-08-24 | 2015-09-15 | 100% | 90% | Works completed |  | 2016-05-29
Construction of interview rooms at Boroli Settlement | UNHCR |  | Boroli Settlement | 2015-10-12 | 2015-12-31 | 100% | 90% | Works completed |  | 2016-06-30
Construction of Isolation Ward at Adjumani Hospital | UNHCR | 20 patients | Adjumani Town | 2015-08-02 | 2015-12-02 | 100% | 90% | All works completed |  | 2016-06-02
Fencing Nyumanzi Base camp and T70 tank | UNHCR |  | Nyumanzi and Ayilo 2 Settlements | 2015-07-15 | 2015-09-15 | 100% | 90% | Works complete |  | 2016-03-15
Fencing Ayilo police post, Ayilo primary school, Ayilo h/c staff houses, protection house and T70 tank | UNHCR |  | Ayilo 1 Police Post, Ayilo 1 Primary School, Ayilo1 Health Centre, Ayilo 2 and Ayilo Base Camp | 2015-07-22 | 2015-10-22 | 100% | 100% | Works completed |  | 2016-04-22
Fencing of primary school. Lewa SS and Ayilo 2 Primary School | UNHCR |  | Lewa S.S and Ayilo 2 Primary School | 2015-08-24 | 2015-11-24 | 100% | 100% | Works completed |  | 2016-05-24
Fencing of St. Luke Primary School, Nyumanzi, Adjumani District | UNHCR |  | Nyumanzi Settlement | 2015-09-22 | 2015-10-13 | 100% | 100% | Works completed |  | 2016-04-13
Fencing of Community centers at Baratuku, Boroli and Ayilo I | UNHCR |  | Baratuku, Boroli and Ayilo 1 Settlements | 2015-08-24 | 2015-11-24 | 100% | 100% | All works completed |  | 2016-06-05
Fencing of Nyumanzi Community Centre | UNHCR |  | Nyumanzi Settlement | 2015-11-16 | 2015-12-31 | 100% | 100% | All works completed |  | 2016-06-30
Construction of 06 Food Distribution Point / NFI centers | UNHCR |  | Ayilo 1A, Ayilo 1B, Ayilo 2, Nyumanzi, Baratuku and Boroli | 2015-08-24 | 2015-11-24 | 100% | 90% | All works completed |  | 2016-05-24
Construction of 01 Food Distribution Point / NFI centers | UNHCR |  | Elema Settlement | 2015-10-12 | 2015-12-31 | 100% | 90% | All works completed. |  | 2016-06-30
Construction of 02 Dormitories in Pakele Girls Primary and Lewa secondary schools | UNHCR |  | Pakele Girls Primary School and Lewa Secondary School | 2015-10-24 | 2015-12-03 | 100% | 90% | All works completed. |  | 2016-06-03
Construction of 01 block of Dormitories in Alere secondary school | UNHCR | 72 | Alere Secondary School | 2015-09-18 | 2015-12-20 | 100% | 90% | All works completed. |  | 2016-06-10
Construction of one 2-classroom block (Secondary) at Alere Secondary School | UNHCR | 100 | Alere Secondary School | 2015-09-18 | 2015-12-20 | 100% | 90% | All works completed. |  | 2016-06-11
Construction of 02 septic tanks at IP and RDO Office Blocks | UNHCR | 400 | UNHCR and LWF compounds, Pakele | 2015-07-26 | 2015-08-31 | 100% | 100% | Works completed |  | 2015-11-30
Construction of 02 septic tanks at UNHCR and LWF premises | UNHCR | 400 | OPM premises, Pakele | 2015-09-11 | 2015-10-30 | 100% | 100% | Works completed |  | 2016-06-12
Construction of a 10-stall bath shelter and one block of 5-stance VIP latrines at Elegu Collection Point | UNHCR |  | Elegu Transit Centre | 2015-09-10 | 2016-03-10 | 100% | 90% | Works completed |  | 2016-06-10
Renovation of Walkways, Kitchen and Generator house | UNHCR | 200 | LWF compound, Pakele, Adjumani | 2015-06-16 | 2015-08-03 | 100% | 100% | Works completed |  | 2016-06-14
Construction of RDO car parking Shed | UNHCR | 6 cars | OPM premises, Pakele, Adjumani | 2015-09-07 | 2015-09-30 | 100% | 100% | Works completed |  | 2016-06-15
Construction of RDO Office Waiting Payot | UNHCR | 20 | OPM residences, Adjumani Town | 2015-09-07 | 2015-09-30 | 100% | 90% | Works completed. |  | 2016-06-16
Renovation of AAH offices | UNHCR |  | LWF/UNHCR Warehouses, Adjumani Town | 2015-09-09 | 2015-10-09 | 100% | 90% | Works completed |  | 2016-01-09
Installation of Lightning Conductors on 27 blocks of classrooms and 2 health centres | UNHCR | 3300 | Pakele Girls P/S, Pakele HC III, Magara P/S, Amuru P/S, Pereci P/S, Bezza-Al-Hijji S.S, Lewa HC II, Dzaipi S.S, Amelo P/S, Paluga P/S, Jurumini P/S, Meliaderi P/S and LWF offices | 2015-07-07 | 2015-08-31 | 100% | 100% | Works completed |  | 31/11/2015
Installation of four (08) rainwater harvesting systems at selected primary schools in Adjumani District | UNHCR |  |  | 2015-08-04 | 2015-10-04 | 100% | 90% | Works completed |  | 2016-01-04
Construction of 10 blocks of 5-Stance VIP latrines in schools and other facilities | UNHCR |  | Boroli Market, Lewa S.S, Alere S.S, Pakele Girls P/S, Ayilo 1B P/S (2), Baratuku P/S (2), Baratuku Community Centre, Pakele HCIII | 2015-09-28 | 2015-11-30 | 100% | 90% | Works completed |  | 2016-02-29
Installation of four (04) rainwater harvesting systems at selected health centres and schools | UNHCR |  | Nyumanzi II P/S (2), Nyumanzi HC III, Pakele HC III | 2015-09-15 | 2015-11-15 | 100% | 100% | Works completed |  | 2016-02-15
Construction of 4 blocks of 5-Stance VIP latrines | UNHCR |  | Baratuku Market, Nyumanzi Distribution Point, Ayilo1A distibution point and Adjumani Airstrip | 2015-09-25 | 2015-11-10 | 100% | 90% | Works completed |  | 2016-02-10
Completion of Immigration Office in Elegu | UNHCR |  | Elegu Border Town | 2015-09-25 | 2015-11-10 | 100% | 90% | Works completed |  | 2016-02-10
Construction of 2 blocks of 2-Stance VIP latrines Primary schools | UNHCR |  | Ayilo 1B and Baratuku Primary Schools | 2015-10-06 | 2015-11-10 | 100% | 90% | Works completed |  | 2016-06-24
Fitting of Insect proof wiremesh on staff accomodations constructed in 2014 | UNHCR |  | 32 blocks of teacher and doctor accomodations around Adjumani District | 2015-10-05 | 2015-11-13 | 85% | 90% | Works on-going with less than 5 teachers' houses remaining |  | 2016-02-13
Construction of seven (7) Garbage Collection Points in Adjumani | UNHCR |  | Ayilo 1 (2), Nyumanzi (2), Elema (1), Baratuku (1) and Boroli (1) | 2015-08-17 | 2015-09-17 | 100% | 100% | Works completed |  | 2015-12-17
Construction of four (4) Garbage Collection Points in Adjumani | BPRM |  | Elegu Collection Centre, Pakele Market, LWF compound & Dzaipi Market | 2015-10-07 | 2015-10-23 | 100% | 100% | Works completed |  | 2016-01-23
Construction of three (3) blocks of 2-stance VIP latrines in selected schools | UNHCR | 90 | Ayilo 1C, St. Luke and Nyumanzi 2 Primary Schools | 2015-07-07 | 2015-08-31 | 100% | 100% | Works completed |  | 2015-11-30
Construction of 211 PSN latrines in Refugee Settlements in Adjumani District | BPRM | 211 households | Ayilo 1 Settlement | 2015-05-07 | 2015-08-31 | 100% | 100% | Works completed |  | 2015-09-30
Construction of 70 PSN huts in Refugee Settlements in Adjumani District | UNHCR | 70 households | Boroli and Ayilo 1 Settlements | 2015-09-15 | 2016-03-15 | 100% | 90% | Works completed |  | 2016-06-15
Construction of 70 PSN huts in Refugee Settlements in Adjumani District | BPRM | 70 households | Nyumanzi, Baratuku and Ayilo 1 Settlements | 2015-09-15 | 2016-03-15 | 100% | 90% | Works completed |  | 2016-06-15
Construction of 185 PSN huts in Refugee Settlements in Adjumani District | UNHCR (160), BPRM (25) | 185 households | Nyumanzi, Ayilo1, Boroli, Baratuku and Elema | 2015-06-26 | 2015-08-31 | 100% | 100% | Works completed |  | 2015-11-30
Construction of forty (40) PSN huts in refugee settlements in Adjumani | CLWR | 40 | Nyumanzi Settlement | 2015-06-26 | 2015-08-31 | 100% | 90% | Works completed |  | 2015-11-30
Construction of four (04) blocks comprising a saloon, phone charging room and a pool table shed in Adjumani District | UNHCR |  | Ayilo 1, Nyumanzi, Boroli and Baratuku Settlements | 2015-10-05 | 2015-11-10 | 100% | 90% | Works completed |  | 2016-02-10
Maintenance / expansion of LWF Offices | UNHCR | 120 | LWF compound, Pakele, Adjumani | 2015-10-17 | 2015-11-30 | 100% | 90% | All works completed |  | 2016-05-30
Rehabilitation of a classroom block at Melijo Primary School | UNHCR/DFID | 200 | Melijo Primary School | 2015-09-28 | 2015-10-29 | 100% | 90% | Works completed |  | 2016-01-29
Construction of a Drug Store in Adjumani District | UNHCR |  | OPM premises, Pakele, Adjumani | 2015-10-22 | 2015-12-31 | 90% | 80% | All building and compound landscaping complete; pending re-allocation of the fencing |  | 2016-06-30
Renoation of UAM shelters and partitioning of the mental health ward | UNHCR |  | Boroli and Nyumanzi Settlements (UAM Shelters); Adjumani Hospital Mental Unit | 00/11/2015 | 2015-12-31 | 100% | 100% | Works completed |  | 2016-03-31
Installation of solar power at Ayilo 1 Police Post | UNHCR | 30 | Ayilo 1 Police Post | 2015-12-22 | 2015-12-28 | 100% | 100% | Works completed |  | 2016-01-31
Construction of a generator and power house at Ayilo 1 Post | UNHCR |  | Ayilo 1 Health Centre III | 2015-12-10 | 2015-12-31 | 100% | 100% | Works completed |  | 2016-03-31
Construction of 228 PSN latrines in Refugee Settlements in Adjumani District | UNICEF | 228 households | Ayilo 1, Boroli, Baratuku and Nyumanzi Settlements | 2015-11-23 | 2016-02-23 | 100% | 90% | Works completed |  | 2015-05-23
Construction of seven (7) Garbage Collection Points in Adjumani District | UNICEF |  | Adjumani Hospital (1), Adjumani Police Station (1), Jepaku Market (1), Adjumani Bus Park (1), Alere S.S (1), Lewa S.S (1) and Dzaipi S.S (1) | 2015-12-02 | 2016-02-08 | 80% | 0% | 5 of the collection points are complete waiting fixing of doors while the remaining two are at substructure stage |  | 2016-08-08
Compiled by :
Aaron Ali Butti
Construction Engineer
LWF Uganda Program
Note on B4: Aaron Ali: Charnelle to provide information for this and the following two columns: SHE'S BEEN QUITE BUSY...
Note on H4: Aaron Ali: Most of these payments include those that we have already cleared for payment next week